## Sheet1
Activity ID | Planned Start | Planned Finish | Resources | WBS Category | WBS Path | Project Name | Project ID | Activity Name | WBS | Original Duration | WBS Name | Duration Type | Actual Duration | Physical % Complete | Performance % Complete | BL Project Duration | Remaining Duration | Schedule % Complete | Budgeted Total Cost | Earned Value Cost | Actual Total Cost | Total Float | Start | Finish | Budgeted Expense Cost | Actual Expense Cost
MJ-MSBL-INT-1.14 Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | 2017-01-02 | 1936-08-19 | [7 empty] | 6120 |  |  | 1043 |  | 0.01% | 6120 | 5301 | 0.14% | $8,706,602,273.61 | $640,000.00 | $640,000.00 | 0 | 05-Apr-16 A | 1936-08-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.11 (New WBS) | [9 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.8 Project Completion Date | 2018-12-16 | 1936-08-19 | [7 empty] | 5428 |  |  | 0 |  | 0% | 5428 | 2005 | 0% | $0.00 | $0.00 | $0.00 | 0 | 07-Jun-18 A | 1936-08-19 | $0.00 | $0.00
M1000 | 2018-12-16 |  |  |  | 8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | MS Start | MJ-MSBL-INT-1.14.8 | 0 | Project Completion Date | Fixed Duration and Units/Time | 0 | 100% | 100% | 0 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 07-Jun-18 A |  | $0.00 | $0.00
M1250 |  | 1930-03-19 |  |  | 8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Effective Project Finish | MJ-MSBL-INT-1.14.8 | 0 | Project Completion Date | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2005 |  | 1930-03-19 | $0.00 | $0.00
M1260 |  | 1936-08-19 |  |  | 8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Project Finish & Contract Closure | MJ-MSBL-INT-1.14.8 | 0 | Project Completion Date | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  | 1936-08-19 | $0.00 | $0.00 | 2018-01-01
MJ-MSBL-INT-1.14.1 Milestones | 2018-12-02 | 1936-08-19 | [7 empty] | 5539 |  |  | 285 |  | 0% | 5539 | 5301 | 0% | $755,000.00 | $0.00 | $0.00 | 0 | 07-Jun-18 A | 1936-08-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.1.7 Partners [SH/JDURC] | 2018-12-03 | 2019-09-15 | [7 empty] | 196 |  |  | 142 |  | 0% | 196 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4338 | 30-Oct-18 A | 2019-09-15 | $0.00 | $0.00
M1630 |  | 2019-05-26 |  |  | 1.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [SH/JDURC] Approve & Sign Contract Agreement Addendum no. (04) | MJ-MSBL-INT-1.14.1.7 | 0 | Partners [SH/JDURC] | Fixed Duration and Units/Time | 0 | 100% | 100% | 0 | 0 | 100% | $0.00 | $0.00 | $0.00 |  |  | 16-May-19 A | $0.00 | $0.00
M1640 | 2019-09-15 |  |  |  | 1.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [JDURC] Activate Capital Contribution | MJ-MSBL-INT-1.14.1.7 | 0 | Partners [SH/JDURC] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4338 | 2019-09-15 |  | $0.00 | $0.00
M1650 | 2019-09-15 |  |  |  | 1.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [JDURC] Transfer Land Deeds as Scheduled | MJ-MSBL-INT-1.14.1.7 | 0 | Partners [SH/JDURC] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4338 | 2019-09-15 |  | $0.00 | $0.00
M1660 | 2019-09-15 |  |  |  | 1.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [SH] Transfer Cash Installments as Scheduled | MJ-MSBL-INT-1.14.1.7 | 0 | Partners [SH/JDURC] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4338 | 2019-09-15 |  | $0.00 | $0.00
M1680 |  | 2018-12-03 |  |  | 1.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [SH/JDURC] Approve Signing MOU with MOH | MJ-MSBL-INT-1.14.1.7 | 0 | Partners [SH/JDURC] | Fixed Duration and Units/Time | 0 | 100% | 100% | 0 | 0 | 100% | $0.00 | $0.00 | $0.00 |  |  | 30-Oct-18 A | $0.00 | $0.00
MJ-MSBL-INT-1.14.1.9 Master Plan & Infrastructure [Authorites] | 2019-12-12 | 2020-06-07 | [7 empty] | 121 |  |  | 0 |  | 0% | 121 | 121 | 0% | $0.00 | $0.00 | $0.00 | 4153 | 2019-12-12 | 2020-06-07 | $0.00 | $0.00
M1690 |  | 2019-12-12 |  |  | 1.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [Authorities] Approval of Remaining Main Infrastructure Utilities | MJ-MSBL-INT-1.14.1.9 | 0 | Master Plan & Infrastructure [Authorites] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2538 |  | 2019-12-12 | $0.00 | $0.00
M1700 |  | 2020-06-07 |  |  | 1.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [Authorities] Approval of Secondary Infrastructure Utilities | MJ-MSBL-INT-1.14.1.9 | 0 | Master Plan & Infrastructure [Authorites] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4153 |  | 2020-06-07 | $0.00 | $0.00
M1850 |  | 2020-01-28 |  |  | 1.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [Municipality] Approval of Secondary Master Plan | MJ-MSBL-INT-1.14.1.9 | 0 | Master Plan & Infrastructure [Authorites] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2213 |  | 2020-01-28 | $0.00 | $0.00
MJ-MSBL-INT-1.14.1.5 Superstructure (MOH / WAFI] | 2018-12-02 | 2023-08-20 | [7 empty] | 1194 |  |  | 107 |  | 0% | 1194 | 830 | 0% | $0.00 | $0.00 | $0.00 | 3342 | 07-Jun-18 A | 2023-08-20 | $0.00 | $0.00
M1010 | 2018-12-02 |  |  |  | 1.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [MOH] مذكرة التفاهم | MJ-MSBL-INT-1.14.1.5 | 0 | Superstructure (MOH / WAFI] | Fixed Duration and Units/Time | 0 | 100% | 100% | 0 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 07-Jun-18 A |  | $0.00 | $0.00
M1050 | 2019-01-01 |  |  |  | 1.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [MOH] مذكرة الإعلان | MJ-MSBL-INT-1.14.1.5 | 0 | Superstructure (MOH / WAFI] | Fixed Duration and Units/Time | 0 | 100% | 100% | 0 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 15-Nov-18 A |  | $0.00 | $0.00
M1070 | 2020-09-06 |  |  |  | 1.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [MOH] توقيع إتفاقية الشراكة للتطوير | MJ-MSBL-INT-1.14.1.5 | 0 | Superstructure (MOH / WAFI] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3923 | 2020-09-06 |  | $0.00 | $0.00
M1100 | 2020-05-05 |  |  |  | 1.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [ITMAM] إصدار رخصة البناء | MJ-MSBL-INT-1.14.1.5 | 0 | Superstructure (MOH / WAFI] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 588 | 2020-05-05 |  | $0.00 | $0.00
M1150 | 2020-08-19 |  |  |  | 1.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [WAFI] إصدار رخصة البيع على الخارطة - عام 1 | MJ-MSBL-INT-1.14.1.5 | 0 | Superstructure (MOH / WAFI] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 529 | 2020-08-19 |  | $0.00 | $0.00
M1190 | 2020-08-19 |  |  |  | 1.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [MOH] إصدار تصريح بدء أعمال التنفيذ | MJ-MSBL-INT-1.14.1.5 | 0 | Superstructure (MOH / WAFI] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4103 | 2020-08-19 |  | $0.00 | $0.00
M13590 | 2021-08-19 |  |  |  | 1.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [WAFI] تجديد رخصة البيع على الخارطة - عام 2 | MJ-MSBL-INT-1.14.1.5 | 0 | Superstructure (MOH / WAFI] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3341 | 2021-08-19 |  | $0.00 | $0.00
M13600 | 2022-08-22 |  |  |  | 1.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [WAFI] تجديد رخصة البيع على الخارطة - عام 3 | MJ-MSBL-INT-1.14.1.5 | 0 | Superstructure (MOH / WAFI] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3341 | 2022-08-22 |  | $0.00 | $0.00
M13610 | 2023-08-20 |  |  |  | 1.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [WAFI] تجديد رخصة البيع على الخارطة - عام 4 | MJ-MSBL-INT-1.14.1.5 | 0 | Superstructure (MOH / WAFI] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3341 | 2023-08-20 |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.1.1 Contractual Milestones | 2018-12-17 | 2020-08-05 | [7 empty] | 412 |  |  | 12 |  | 0% | 412 | 225 | 0% | $0.00 | $0.00 | $0.00 | 3945 | 30-Oct-18 A | 2020-08-05 | $0.00 | $0.00
M1020 | 2018-12-17 |  |  |  | 1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [DMO] إعتماد العرض الفني | MJ-MSBL-INT-1.14.1.1 | 0 | Contractual Milestones | Fixed Duration and Units/Time | 0 | 100% | 100% | 0 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 30-Oct-18 A |  | $0.00 | $0.00
M1030 | 2018-12-17 |  |  |  | 1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [DMO] إعتماد العرض المالي | MJ-MSBL-INT-1.14.1.1 | 0 | Contractual Milestones | Fixed Duration and Units/Time | 0 | 100% | 100% | 0 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 30-Oct-18 A |  | $0.00 | $0.00
M1040 | 2018-12-24 |  |  |  | 1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [DMO] إستلام خطة إدارة المشروع والتنفيذ | MJ-MSBL-INT-1.14.1.1 | 0 | Contractual Milestones | Fixed Duration and Units/Time | 0 | 100% | 100% | 0 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 15-Nov-18 A |  | $0.00 | $0.00
M1060 | 2019-09-15 |  |  |  | 1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [SRE] التقييم العقاري المعتمد لأرض المشروع | MJ-MSBL-INT-1.14.1.1 | 0 | Contractual Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4170 | 2019-09-15 |  | $0.00 | $0.00
M1080 | 2019-09-15 |  |  |  | 1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [WAFI] إستلام دراسة الجدوى الإقتصادية للمشروع | MJ-MSBL-INT-1.14.1.1 | 0 | Contractual Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 754 | 2019-09-15 |  | $0.00 | $0.00
M1090 |  | 2020-05-04 |  |  | 1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [DMO] إعتماد التصاميم التفصيلية للمشروع | MJ-MSBL-INT-1.14.1.1 | 0 | Contractual Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 588 |  | 2020-05-04 | $0.00 | $0.00
M1105 | 2019-09-15 |  |  |  | 1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [SRE] تعميد شركة التسويق العقاري | MJ-MSBL-INT-1.14.1.1 | 0 | Contractual Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 694 | 2019-09-15 |  | $0.00 | $0.00
M1110 | 2020-07-12 |  |  |  | 1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [SRE] تعميد المحاسب القانوني | MJ-MSBL-INT-1.14.1.1 | 0 | Contractual Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 529 | 2020-07-12 |  | $0.00 | $0.00
M1120 | 2020-08-05 |  |  |  | 1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [SRE] تعميد امين الحساب | MJ-MSBL-INT-1.14.1.1 | 0 | Contractual Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 529 | 2020-08-05 |  | $0.00 | $0.00
M1130 | 2019-09-15 |  |  |  | 1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [SRE] تعميد إستشاري الإشراف على التنفيذ | MJ-MSBL-INT-1.14.1.1 | 0 | Contractual Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 754 | 2019-09-15 |  | $0.00 | $0.00
M1140 | 2020-08-05 |  |  |  | 1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [SRE] تعميد مقاول التنفيذ للمباني السكنية | MJ-MSBL-INT-1.14.1.1 | 0 | Contractual Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 529 | 2020-08-05 |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.1.2 Commercial Milestones | 2019-09-15 | 1936-08-19 | [7 empty] | 5301 |  |  | 0 |  | 0% | 5301 | 5301 | 0% | $755,000.00 | $0.00 | $0.00 | 0 | 2019-09-15 | 1936-08-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.1.2.1 MOH | 2019-09-15 | 1936-08-19 | [7 empty] | 5301 |  |  | 0 |  | 0% | 5301 | 5301 | 0% | $755,000.00 | $0.00 | $0.00 | 0 | 2019-09-15 | 1936-08-19 | $0.00 | $0.00
P1000 | 2020-08-19 | 2020-08-19 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (01) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 1906 | 2020-08-19 | 2020-08-19 | $0.00 | $0.00
P1070 | 2021-02-15 | 2021-02-15 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (02) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 1906 | 2021-02-15 | 2021-02-15 | $0.00 | $0.00
P1080 | 2021-08-19 | 2021-08-19 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (03) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 1906 | 2021-08-19 | 2021-08-19 | $0.00 | $0.00
P1090 | 2022-02-16 | 2022-02-16 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (04) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 1906 | 2022-02-16 | 2022-02-16 | $0.00 | $0.00
P1110 | 1930-02-24 | 1930-02-24 | Cost Loading - CASH IN |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (05) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1930-02-24 | 1930-02-24 | $0.00 | $0.00
P1200 | 2020-08-19 | 2020-08-19 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [WAFI] دفعة إصدار رخصة التسويق والبيع - عام 1 | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $50,000.00 | $0.00 | $0.00 | 4919 | 2020-08-19 | 2020-08-19 | $0.00 | $0.00
P1210 | 2021-08-19 | 2021-08-19 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [WAFI] دفعة تجديد رخصة التسويق والبيع - عام 2 | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $50,000.00 | $0.00 | $0.00 | 4614 | 2021-08-19 | 2021-08-19 | $0.00 | $0.00
P1220 | 2022-08-22 | 2022-08-22 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [WAFI] دفعة تجديد رخصة التسويق والبيع - عام 3 | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $50,000.00 | $0.00 | $0.00 | 4308 | 2022-08-22 | 2022-08-22 | $0.00 | $0.00
P1230 | 2023-08-20 | 2023-08-20 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [WAFI] دفعة تجديد رخصة التسويق والبيع - عام 4 | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $50,000.00 | $0.00 | $0.00 | 4006 | 2023-08-20 | 2023-08-20 | $0.00 | $0.00
P1240 | 2019-09-15 | 2019-09-15 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | دفعة التقييم العقاري لأرض المشروع | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $15,000.00 | $0.00 | $0.00 | 5201 | 2019-09-15 | 2019-09-15 | $0.00 | $0.00
P1250 | 1930-08-22 | 1930-08-22 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (06) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1930-08-22 | 1930-08-22 | $0.00 | $0.00
P1260 | 1931-02-18 | 1931-02-18 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (07) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1931-02-18 | 1931-02-18 | $0.00 | $0.00
P1270 | 1931-08-19 | 1931-08-19 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (08) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1931-08-19 | 1931-08-19 | $0.00 | $0.00
P1280 | 1932-02-17 | 1932-02-17 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (09) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1932-02-17 | 1932-02-17 | $0.00 | $0.00
P1290 | 1932-08-18 | 1932-08-18 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (10) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1932-08-18 | 1932-08-18 | $0.00 | $0.00
P1300 | 1933-02-17 | 1933-02-17 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (11) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1933-02-17 | 1933-02-17 | $0.00 | $0.00
P1310 | 1933-08-18 | 1933-08-18 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (12) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1933-08-18 | 1933-08-18 | $0.00 | $0.00
P1320 | 1934-02-19 | 1934-02-19 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (13) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1934-02-19 | 1934-02-19 | $0.00 | $0.00
P1330 | 1934-08-20 | 1934-08-20 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (14) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1934-08-20 | 1934-08-20 | $0.00 | $0.00
P1340 | 1935-02-19 | 1935-02-19 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (15) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1935-02-19 | 1935-02-19 | $0.00 | $0.00
P1350 | 1935-08-20 | 1935-08-20 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (16) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1935-08-20 | 1935-08-20 | $0.00 | $0.00
P1360 | 1936-02-19 | 1936-02-19 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (17) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1936-02-19 | 1936-02-19 | $0.00 | $0.00
P1370 | 1936-08-19 | 1936-08-19 | Cost Loading - CASH OUT |  | 1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الدفعة رقم (18) المحاسب القانوني | MJ-MSBL-INT-1.14.1.2.1 | 1 | MOH | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $30,000.00 | $0.00 | $0.00 | 0 | 1936-08-19 | 1936-08-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.1.2.2 SRE | 2025-01-22 | 1936-08-19 | [7 empty] | 2976 |  |  | 0 |  | 0% | 2976 | 2976 | 0% | $0.00 | $0.00 | $0.00 | 0 | 2025-01-22 | 1936-08-19 | $0.00 | $0.00
L1120 | 2025-01-22 | 1936-08-19 | Cost Loading - CASH IN |  | 1.2.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | (%5) صرف ضمان اللأعمال | MJ-MSBL-INT-1.14.1.2.2 | 2976 | SRE | Fixed Duration & Units | 0 | 0% | 0% | 2976 | 2976 | 0% | $0.00 | $0.00 | $0.00 | 0 | 2025-01-22 | 1936-08-19 | $0.00 | $0.00
P1010 | 2025-02-13 | 2025-02-16 | Cost Loading - CASH OUT |  | 1.2.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | (%20) الضمان البنكي للدفعة المقدمة لتنفيذ الأعمال | MJ-MSBL-INT-1.14.1.2.2 | 1 | SRE | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $0.00 | $0.00 | $0.00 | 2791 | 2025-02-13 | 2025-02-16 | $0.00 | $0.00
P1020 | 2025-02-16 | 2025-02-17 | Cost Loading - CASH IN |  | 1.2.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | (%20) دفعة مقدمة لتنفيذ الأعمال | MJ-MSBL-INT-1.14.1.2.2 | 1 | SRE | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $0.00 | $0.00 | $0.00 | 2791 | 2025-02-16 | 2025-02-17 | $0.00 | $0.00
P1030 | 2025-05-08 | 2025-05-11 | Cost Loading - CASH IN |  | 1.2.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | (%15) الدفعة رقم (02) من الأعمال | MJ-MSBL-INT-1.14.1.2.2 | 1 | SRE | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $0.00 | $0.00 | $0.00 | 2791 | 2025-05-08 | 2025-05-11 | $0.00 | $0.00
P1040 | 2025-07-14 | 2025-07-15 | Cost Loading - CASH IN |  | 1.2.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | (%10) الدفعة رقم (03) من الأعمال | MJ-MSBL-INT-1.14.1.2.2 | 1 | SRE | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $0.00 | $0.00 | $0.00 | 2791 | 2025-07-14 | 2025-07-15 | $0.00 | $0.00
P1050 | 2025-08-13 | 2025-08-14 | Cost Loading - CASH IN |  | 1.2.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | (%10) الدفعة رقم (04) من الأعمال | MJ-MSBL-INT-1.14.1.2.2 | 1 | SRE | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $0.00 | $0.00 | $0.00 | 2791 | 2025-08-13 | 2025-08-14 | $0.00 | $0.00
P1060 | 2025-09-15 | 2025-09-16 | Cost Loading - CASH IN |  | 1.2.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | (%30) الدفعة رقم (05) من الأعمال | MJ-MSBL-INT-1.14.1.2.2 | 1 | SRE | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $0.00 | $0.00 | $0.00 | 2791 | 2025-09-15 | 2025-09-16 | $0.00 | $0.00
P1100 | 1930-02-24 | 1930-02-24 | Cost Loading - CASH IN |  | 1.2.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | (%10) الدفعة رقم (18) للتسليم الإبتدائي للأعمال | MJ-MSBL-INT-1.14.1.2.2 | 1 | SRE | Fixed Duration & Units | 0 | 0% | 0% | 1 | 1 | 0% | $0.00 | $0.00 | $0.00 | 1688 | 1930-02-24 | 1930-02-24 | $0.00 | $0.00
MJ-MSBL-INT-1.14.1.3 Sales Milestones | 2019-12-30 | 2025-02-13 | [7 empty] | 1304 |  |  | 0 |  | 0% | 1304 | 1304 | 0% | $0.00 | $0.00 | $0.00 | 2791 | 2019-12-30 | 2025-02-13 | $0.00 | $0.00
M1160 | 2019-12-30 |  |  |  | 1.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | بدء مرحلة التحضيرية للتسويق | MJ-MSBL-INT-1.14.1.3 | 0 | Sales Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 619 | 2019-12-30 |  | $0.00 | $0.00
M1170 |  | 2020-04-06 |  |  | 1.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | إنتهاء المرحلة التحضيرية للتسويق | MJ-MSBL-INT-1.14.1.3 | 0 | Sales Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 619 |  | 2020-04-06 | $0.00 | $0.00
M1180 |  | 2025-02-13 |  |  | 1.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | إنتهاء التسويق والمبيعات المشروع | MJ-MSBL-INT-1.14.1.3 | 0 | Sales Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2791 |  | 2025-02-13 | $0.00 | $0.00
MJ-MSBL-INT-1.14.1.6 Construction Milestones | 2020-09-28 | 1930-02-21 | [7 empty] | 2859 |  |  | 0 |  | 0% | 2859 | 2859 | 0% | $0.00 | $0.00 | $0.00 | 2027 | 2020-09-28 | 1930-02-21 | $0.00 | $0.00
M1200 | 2020-10-20 |  |  |  | 1.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start Superstructure | MJ-MSBL-INT-1.14.1.6 | 0 | Construction Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4868 | 2020-10-20 |  | $0.00 | $0.00
M1210 |  | 1930-02-21 |  |  | 1.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Superstructure | MJ-MSBL-INT-1.14.1.6 | 0 | Construction Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2027 |  | 1930-02-21 | $0.00 | $0.00
M1760 | 2021-11-25 |  |  |  | 1.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start Infrastructure | MJ-MSBL-INT-1.14.1.6 | 0 | Construction Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4532 | 2021-11-25 |  | $0.00 | $0.00
M1770 |  | 2027-11-18 |  |  | 1.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Infrastructure | MJ-MSBL-INT-1.14.1.6 | 0 | Construction Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2714 |  | 2027-11-18 | $0.00 | $0.00
M1780 | 2022-05-25 |  |  |  | 1.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start Landscape | MJ-MSBL-INT-1.14.1.6 | 0 | Construction Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4381 | 2022-05-25 |  | $0.00 | $0.00
M1860 |  | 2025-10-12 |  |  | 1.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Landscape | MJ-MSBL-INT-1.14.1.6 | 0 | Construction Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3353 |  | 2025-10-12 | $0.00 | $0.00
MJ-MSBL-INT-1.14.1.6.1 Infrastructure Work | 2020-09-28 | 2027-11-18 | [7 empty] | 2172 |  |  | 0 |  | 0% | 2172 | 2172 | 0% | $0.00 | $0.00 | $0.00 | 2714 | 2020-09-28 | 2027-11-18 | $0.00 | $0.00
M12210 |  | 2020-09-28 |  |  | 1.6.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Rough Grading Completion | MJ-MSBL-INT-1.14.1.6.1 | 0 | Infrastructure Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4886 |  | 2020-09-28 | $0.00 | $0.00
M12750 |  | 2023-05-30 |  |  | 1.6.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Concrete Structures Completion | MJ-MSBL-INT-1.14.1.6.1 | 0 | Infrastructure Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4072 |  | 2023-05-30 | $0.00 | $0.00
M12760 |  | 2025-01-21 |  |  | 1.6.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | HV S/S Completion | MJ-MSBL-INT-1.14.1.6.1 | 0 | Infrastructure Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3570 |  | 2025-01-21 | $0.00 | $0.00
M12770 |  | 2024-07-06 |  |  | 1.6.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | STP Completion | MJ-MSBL-INT-1.14.1.6.1 | 0 | Infrastructure Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3740 |  | 2024-07-06 | $0.00 | $0.00
M12780 |  | 2025-01-16 |  |  | 1.6.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Open Channel Completion | MJ-MSBL-INT-1.14.1.6.1 | 0 | Infrastructure Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3574 |  | 2025-01-16 | $0.00 | $0.00
M12790 |  | 2025-01-19 |  |  | 1.6.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | RD&St.L. Completion | MJ-MSBL-INT-1.14.1.6.1 | 0 | Infrastructure Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3572 |  | 2025-01-19 | $0.00 | $0.00
M12800 |  | 2027-11-18 |  |  | 1.6.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Secondary Infrastructure Networks Completion | MJ-MSBL-INT-1.14.1.6.1 | 0 | Infrastructure Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2714 |  | 2027-11-18 | $0.00 | $0.00
M1810 |  | 2025-10-12 |  |  | 1.6.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Landscape Completion | MJ-MSBL-INT-1.14.1.6.1 | 0 | Infrastructure Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3353 |  | 2025-10-12 | $0.00 | $0.00
M6050 |  | 2024-02-29 |  |  | 1.6.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Main Infrastructure Networks Completion | MJ-MSBL-INT-1.14.1.6.1 | 0 | Infrastructure Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3841 |  | 2024-02-29 | $0.00 | $0.00
MJ-MSBL-INT-1.14.1.6.2 Superstructure Work | 1930-02-21 | 1930-02-21 | [7 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2027 | 1930-02-21 | 1930-02-21 | $0.00 | $0.00
M12200 |  | 1930-02-21 |  |  | 1.6.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Superstructure Completion | MJ-MSBL-INT-1.14.1.6.2 | 0 | Superstructure Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2027 |  | 1930-02-21 | $0.00 | $0.00
MJ-MSBL-INT-1.14.1.4 DLP Milestones | 2021-11-25 | 1930-03-20 | [7 empty] | 2527 |  |  | 0 |  | 0% | 2527 | 2527 | 0% | $0.00 | $0.00 | $0.00 | 2005 | 2021-11-25 | 1930-03-20 | $0.00 | $0.00
M1220 | 1930-03-20 |  |  |  | 1.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start DLP [M. Infrastructure] | MJ-MSBL-INT-1.14.1.4 | 0 | DLP Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2005 | 1930-03-20 |  | $0.00 | $0.00
M1230 |  | 1930-03-20 |  |  | 1.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish DLP [M. Infrastructure] | MJ-MSBL-INT-1.14.1.4 | 0 | DLP Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2005 |  | 1930-03-20 | $0.00 | $0.00
M1870 | 1930-02-23 |  |  |  | 1.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start DLP [Superstructure] | MJ-MSBL-INT-1.14.1.4 | 0 | DLP Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2027 | 1930-02-23 |  | $0.00 | $0.00
M1880 |  | 1930-02-23 |  |  | 1.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish DLP [Superstructure] | MJ-MSBL-INT-1.14.1.4 | 0 | DLP Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2027 |  | 1930-02-23 | $0.00 | $0.00
M1910 | 2021-11-25 |  |  |  | 1.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start DLP [S. Infrastructure] | MJ-MSBL-INT-1.14.1.4 | 0 | DLP Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4532 | 2021-11-25 |  | $0.00 | $0.00
M1920 |  | 2028-01-27 |  |  | 1.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish DLP [S. Infrastructure] | MJ-MSBL-INT-1.14.1.4 | 0 | DLP Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2654 |  | 2028-01-27 | $0.00 | $0.00
M1930 | 2022-05-25 |  |  |  | 1.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start DLP [Landscape] | MJ-MSBL-INT-1.14.1.4 | 0 | DLP Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4381 | 2022-05-25 |  | $0.00 | $0.00
M1950 |  | 2026-10-21 |  |  | 1.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish DLP [Landscape] | MJ-MSBL-INT-1.14.1.4 | 0 | DLP Milestones | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3041 |  | 2026-10-21 | $0.00 | $0.00
MJ-MSBL-INT-1.14.10 Risk Assessment Phase | 2019-09-15 | 2019-09-15 | [7 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 5202 | 2019-09-15 | 2019-09-15 | $0.00 | $0.00
MJ-MSBL-INT-1.14.10.9 Threats | 2019-09-15 | 2019-09-15 | [7 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 5202 | 2019-09-15 | 2019-09-15 | $0.00 | $0.00
R1000 | 2019-09-15 |  |  |  | 10.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | تمويل وإنشاء محطة الكهرباء الرئيسية للمشروع 380 ك ف أ - الشركة السعودية للكهرباء | MJ-MSBL-INT-1.14.10.9 | 0 | Threats | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3655 | 2019-09-15 |  | $0.00 | $0.00
R1010 | 2019-09-15 |  |  |  | 10.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | تأمين خط تغذية مياه الشرب للمشروع - شركة المياه الوطنية | MJ-MSBL-INT-1.14.10.9 | 0 | Threats | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 5202 | 2019-09-15 |  | $0.00 | $0.00
R1020 | 2019-09-15 |  |  |  | 10.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | انشاء محطة معالجة الصرف الصحي للمشروع - شركة المياه الوطنية | MJ-MSBL-INT-1.14.10.9 | 0 | Threats | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3891 | 2019-09-15 |  | $0.00 | $0.00
R1030 | 2019-09-15 |  |  |  | 10.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | تداخل خط البترول الناقل والذي يتقاطع مع قناة تصريف السيول - أرامكو السعودية | MJ-MSBL-INT-1.14.10.9 | 0 | Threats | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 5202 | 2019-09-15 |  | $0.00 | $0.00
R1040 | 2019-09-15 |  |  |  | 10.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | تامين مداخل ومخارج المشروع أثناء التنفيذ - وزارة النقل | MJ-MSBL-INT-1.14.10.9 | 0 | Threats | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3954 | 2019-09-15 |  | $0.00 | $0.00
R1060 | 2019-09-15 |  |  |  | 10.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | تزويد المشروع بالطاقة الكهربائية اللازمة وتوصيلها على محطة الكهرباء الرئيسية - الشركة السعودية للكهرباء | MJ-MSBL-INT-1.14.10.9 | 0 | Threats | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 5202 | 2019-09-15 |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.10.11 Opportunities | 2019-09-15 | 2019-09-15 | [7 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 5202 | 2019-09-15 | 2019-09-15 | $0.00 | $0.00
R1070 | 2019-09-15 |  |  |  | 10.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | إدارة التسويق والبيع للمخرجات النهائية من المشروع - شركة أدير | MJ-MSBL-INT-1.14.10.11 | 0 | Opportunities | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 5202 | 2019-09-15 |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.12 Development Management / General Supervision | 2019-07-04 | 2029-12-03 | [7 empty] | 3168 |  |  | 96 |  | 0% | 3168 | 3197 | 1.83% | $638,116,219.00 | $0.00 | $0.00 | 2005 | 16-May-19 A | 1930-03-19 | $0.00 | $0.00
L2960 | 2019-07-04 | 2029-12-03 | Cost Loading - CASH OUT |  | 12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Development Management | MJ-MSBL-INT-1.14.12 | 3168 | Development Management / General Supervision | Fixed Duration & Units | 96 | 0% | 0% | 3168 | 3197 | 1.83% | $398,822,637.00 | $0.00 | $0.00 | 2005 | 16-May-19 A | 1930-03-19 | $0.00 | $0.00
L2965 | 2019-07-04 | 2029-12-03 | Cost Loading - CASH OUT |  | 12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | General Supervision | MJ-MSBL-INT-1.14.12 | 3168 | Development Management / General Supervision | Fixed Duration & Units | 96 | 0% | 0% | 3168 | 3197 | 1.83% | $239,293,582.00 | $0.00 | $0.00 | 2005 | 16-May-19 A | 1930-03-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.7 Pre-Design Phase | 2018-12-16 | 2019-09-15 | [7 empty] | 188 |  |  | 136 |  | 0% | 188 | 0 | 0% | $0.00 | $0.00 | $0.00 | 1 | 15-Nov-18 A | 2019-09-15 | $0.00 | $0.00
A11800 | 2018-12-16 | 2018-12-30 |  |  | 7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Consultants Prequalifications / Invitations | MJ-MSBL-INT-1.14.7 | 11 | Pre-Design Phase | Fixed Duration & Units | 5 | 100% | 100% | 11 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 15-Nov-18 A | 22-Nov-18 A | $0.00 | $0.00
A11810 | 2018-12-30 | 2019-02-27 |  |  | 7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding | MJ-MSBL-INT-1.14.7 | 43 | Pre-Design Phase | Fixed Duration and Units/Time | 130 | 100% | 100% | 43 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 25-Nov-18 A | 26-May-19 A | $0.00 | $0.00
A13660 |  | 2019-09-15 |  |  | 7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sign Consultancy Contract Agreement (AAW) | MJ-MSBL-INT-1.14.7 | 0 | Pre-Design Phase | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 1 |  | 2019-09-15 | $0.00 | $0.00
MJ-MSBL-INT-1.14.2 Design Phase | 2018-11-29 | 2021-11-24 | [7 empty] | 757 |  |  | 274 |  | 8.33% | 757 | 558 | 8.33% | $7,680,000.00 | $640,000.00 | $640,000.00 | 3362 | 09-Aug-18 A | 2021-11-24 | $0.00 | $0.00
A12800 | 2019-12-01 | 2021-11-24 | Cost Loading - CASH OUT |  | 2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Design Secondary MP, Infrastructure, Roads, Landscape & Superstucture | MJ-MSBL-INT-1.14.2 | 504 | Design Phase | Fixed Duration & Units | 0 | 0% | 0% | 504 | 504 | 0% | $0.00 | $0.00 | $0.00 | 3362 | 2019-12-01 | 2021-11-24 | $0.00 | $0.00
MJ-MSBL-INT-1.14.2.2 Main Infrastructure Networks, Roads & Landscape | 2019-09-15 | 2020-01-13 | [7 empty] | 86 |  |  | 0 |  | 0% | 86 | 86 | 0% | $2,280,000.00 | $0.00 | $0.00 | 2538 | 2019-09-15 | 2020-01-13 | $0.00 | $0.00
A12140 | 2019-12-15 | 2020-01-13 | Cost Loading - CASH OUT |  | 2.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Packages & Documents [M. Infra.] | MJ-MSBL-INT-1.14.2.2 | 22 | Main Infrastructure Networks, Roads & Landscape | Fixed Duration & Units | 0 | 0% | 0% | 22 | 22 | 0% | $360,000.00 | $0.00 | $0.00 | 2538 | 2019-12-15 | 2020-01-13 | $0.00 | $0.00
A6140 | 2019-09-15 | 2019-11-12 | Cost Loading - CASH OUT |  | 2.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare & Submit Remaining Infrastructure Utilities Design to Related Authorities | MJ-MSBL-INT-1.14.2.2 | 42 | Main Infrastructure Networks, Roads & Landscape | Fixed Duration & Units | 0 | 0% | 0% | 42 | 42 | 0% | $1,200,000.00 | $0.00 | $0.00 | 2538 | 2019-09-15 | 2019-11-12 | $0.00 | $0.00
A6150 | 2019-11-13 | 2019-12-12 | Cost Loading - CASH OUT |  | 2.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [Authorities] Review / Approve Remaining Main Infrastructure Utilities | MJ-MSBL-INT-1.14.2.2 | 22 | Main Infrastructure Networks, Roads & Landscape | Fixed Duration & Units | 0 | 0% | 0% | 22 | 22 | 0% | $720,000.00 | $0.00 | $0.00 | 2538 | 2019-11-13 | 2019-12-12 | $0.00 | $0.00
MJ-MSBL-INT-1.14.2.MP1 Secondary Master Plan | 2019-09-15 | 2020-01-28 | [7 empty] | 96 |  |  | 0 |  | 0% | 96 | 96 | 0% | $1,600,000.00 | $0.00 | $0.00 | 2213 | 2019-09-15 | 2020-01-28 | $0.00 | $0.00
A1300 | 2019-12-01 | 2019-12-29 | Cost Loading - CASH OUT |  | 2.MP1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare & Submit Detailed Master Plan to Municipality | MJ-MSBL-INT-1.14.2.MP1 | 20 | Secondary Master Plan | Fixed Duration & Units | 0 | 0% | 0% | 20 | 20 | 0% | $160,000.00 | $0.00 | $0.00 | 2213 | 2019-12-01 | 2019-12-29 | $0.00 | $0.00
A1320 | 2019-12-29 | 2020-01-28 | Cost Loading - CASH OUT |  | 2.MP1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [Municipality] Review/Approval of Detailed Master Plan | MJ-MSBL-INT-1.14.2.MP1 | 22 | Secondary Master Plan | Fixed Duration & Units | 0 | 0% | 0% | 22 | 22 | 0% | $240,000.00 | $0.00 | $0.00 | 2213 | 2019-12-29 | 2020-01-28 | $0.00 | $0.00
A1360 | 2019-10-02 | 2019-11-13 | Cost Loading - CASH OUT |  | 2.MP1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare & Submit Concept Secondary Master Plan to Municipality | MJ-MSBL-INT-1.14.2.MP1 | 30 | Secondary Master Plan | Fixed Duration & Units | 0 | 0% | 0% | 30 | 30 | 0% | $560,000.00 | $0.00 | $0.00 | 2213 | 2019-10-02 | 2019-11-13 | $0.00 | $0.00
A1370 | 2019-11-13 | 2019-12-01 | Cost Loading - CASH OUT |  | 2.MP1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [Municipality] Review/Approval of Concept Secondary Master Plan | MJ-MSBL-INT-1.14.2.MP1 | 12 | Secondary Master Plan | Fixed Duration & Units | 0 | 0% | 0% | 12 | 12 | 0% | $480,000.00 | $0.00 | $0.00 | 2213 | 2019-11-13 | 2019-12-01 | $0.00 | $0.00
M6260 |  | 2019-12-01 |  |  | 2.MP1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [Municipality] Approval of Concept Master Plan | MJ-MSBL-INT-1.14.2.MP1 | 0 | Secondary Master Plan | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2213 |  | 2019-12-01 | $0.00 | $0.00
T2910 | 2019-09-15 | 2019-10-06 | Cost Loading - CASH OUT |  | 2.MP1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare Soil Profile Study Report | MJ-MSBL-INT-1.14.2.MP1 | 15 | Secondary Master Plan | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $48,000.00 | $0.00 | $0.00 | 2213 | 2019-09-15 | 2019-10-06 | $0.00 | $0.00
T2940 | 2019-09-15 | 2019-10-06 | Cost Loading - CASH OUT |  | 2.MP1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare Hydrological Impact Study | MJ-MSBL-INT-1.14.2.MP1 | 15 | Secondary Master Plan | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $48,000.00 | $0.00 | $0.00 | 2213 | 2019-09-15 | 2019-10-06 | $0.00 | $0.00
T3110 | 2019-09-22 | 2019-10-14 | Cost Loading - CASH OUT |  | 2.MP1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare Traffic Impact Study | MJ-MSBL-INT-1.14.2.MP1 | 15 | Secondary Master Plan | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $64,000.00 | $0.00 | $0.00 | 2213 | 2019-09-22 | 2019-10-14 | $0.00 | $0.00
MJ-MSBL-INT-1.14.2.1 Secondary Infrastructure Networks | 2020-01-28 | 2020-07-08 | [7 empty] | 112 |  |  | 0 |  | 0% | 112 | 112 | 0% | $2,280,000.00 | $0.00 | $0.00 | 2213 | 2020-01-28 | 2020-07-08 | $0.00 | $0.00
A12810 | 2020-01-28 | 2020-04-20 | Cost Loading - CASH OUT |  | 2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare & Submit Secondary Infrastructure Utilities Design to Related Authorities | MJ-MSBL-INT-1.14.2.1 | 59 | Secondary Infrastructure Networks | Fixed Duration & Units | 0 | 0% | 0% | 59 | 59 | 0% | $1,080,000.00 | $0.00 | $0.00 | 2213 | 2020-01-28 | 2020-04-20 | $0.00 | $0.00
A12830 | 2020-06-07 | 2020-07-08 | Cost Loading - CASH OUT |  | 2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Packages & Documents [S. Infra.] | MJ-MSBL-INT-1.14.2.1 | 23 | Secondary Infrastructure Networks | Fixed Duration & Units | 0 | 0% | 0% | 23 | 23 | 0% | $360,000.00 | $0.00 | $0.00 | 2213 | 2020-06-07 | 2020-07-08 | $0.00 | $0.00
A12860 | 2020-04-20 | 2020-06-07 | Cost Loading - CASH OUT |  | 2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [Authorities] Review / Approve Secondary Infrastructure Utilities | MJ-MSBL-INT-1.14.2.1 | 30 | Secondary Infrastructure Networks | Fixed Duration & Units | 0 | 0% | 0% | 30 | 30 | 0% | $840,000.00 | $0.00 | $0.00 | 2213 | 2020-04-20 | 2020-06-07 | $0.00 | $0.00
MJ-MSBL-INT-1.14.2.11 Superstructure Work | 2018-11-29 | 2020-07-09 | [7 empty] | 409 |  |  | 274 |  | 42.11% | 409 | 210 | 42.11% | $1,520,000.00 | $640,000.00 | $640,000.00 | 590 | 09-Aug-18 A | 2020-07-09 | $0.00 | $0.00
A9630 | 2019-02-27 | 2019-05-01 | Cost Loading - CASH OUT |  | 2.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Concept Design [DM/Developer] | MJ-MSBL-INT-1.14.2.11 | 45 | Superstructure Work | Fixed Duration & Units | 32 | 100% | 100% | 45 | 0 | 100% | $240,000.00 | $240,000.00 | $240,000.00 |  | 09-Aug-18 A | 01-Oct-18 A | $0.00 | $0.00
A9640 | 2019-05-01 | 2019-05-07 | Cost Loading - CASH OUT |  | 2.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Workshop / Review / Approve Concept Design [Municipality] | MJ-MSBL-INT-1.14.2.11 | 4 | Superstructure Work | Fixed Duration & Units | 8 | 100% | 100% | 4 | 0 | 100% | $400,000.00 | $400,000.00 | $400,000.00 |  | 02-Oct-18 A | 14-Oct-18 A | $0.00 | $0.00
A9650 | 2019-09-15 | 2019-12-29 | Cost Loading - CASH OUT |  | 2.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Schematic Design | MJ-MSBL-INT-1.14.2.11 | 75 | Superstructure Work | Fixed Duration & Units | 0 | 0% | 0% | 75 | 75 | 0% | $400,000.00 | $0.00 | $0.00 | 1 | 2019-09-15 | 2019-12-29 | $0.00 | $0.00
A9670 | 2019-12-30 | 2020-05-04 | Cost Loading - CASH OUT |  | 2.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Detailed Design | MJ-MSBL-INT-1.14.2.11 | 91 | Superstructure Work | Fixed Duration & Units | 0 | 0% | 0% | 91 | 91 | 0% | $320,000.00 | $0.00 | $0.00 | 1 | 2019-12-30 | 2020-05-04 | $0.00 | $0.00
A9690 | 2020-05-05 | 2020-07-09 | Cost Loading - CASH OUT |  | 2.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Tender Documents | MJ-MSBL-INT-1.14.2.11 | 44 | Superstructure Work | Fixed Duration & Units | 0 | 0% | 0% | 44 | 44 | 0% | $160,000.00 | $0.00 | $0.00 | 1 | 2020-05-05 | 2020-07-09 | $0.00 | $0.00
T1040 | 2018-11-29 | 2018-12-17 | Cost Loading - CASH OUT |  | 2.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | إعداد التصاميم الأولية والمساقط والوجهات للمشروع | MJ-MSBL-INT-1.14.2.11 | 12 | Superstructure Work | Fixed Duration & Units | 42 | 100% | 100% | 12 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 09-Aug-18 A | 15-Oct-18 A | $0.00 | $0.00
T1050 | 2018-12-17 | 2019-01-20 | Cost Loading - CASH OUT |  | 2.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | إعداد التصاميم التفصيلية والمواصفات وجداول الكميات للمشروع | MJ-MSBL-INT-1.14.2.11 | 25 | Superstructure Work | Fixed Duration & Units | 208 | 0% | 0% | 25 | 25 | 100% | $0.00 | $0.00 | $0.00 | 776 | 18-Nov-18 A | 2019-10-20 | $0.00 | $0.00
T1060 | 2019-09-15 | 2019-10-06 | Cost Loading - CASH OUT |  | 2.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | إعداد مستندات الطرح لمقاولي التنفيذ | MJ-MSBL-INT-1.14.2.11 | 15 | Superstructure Work | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 776 | 2019-09-15 | 2019-10-06 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3 Marketing & Sales | 2019-12-30 | 2025-02-13 | [7 empty] | 1606 |  |  | 0 |  | 0% | 1606 | 1606 | 0% | $0.00 | $0.00 | $0.00 | 3402 | 2019-12-30 | 2025-02-13 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.1 Branding | 2019-12-30 | 2020-03-23 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $0.00 | $0.00 | $0.00 | 629 | 2019-12-30 | 2020-03-23 | $0.00 | $0.00
T1100 | 2019-12-30 | 2020-01-29 | Cost Loading - CASH OUT |  | 3.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | انشاء الهوية | MJ-MSBL-INT-1.14.3.1 | 23 | Branding | Fixed Duration & Units | 0 | 0% | 0% | 23 | 23 | 0% | $0.00 | $0.00 | $0.00 | 619 | 2019-12-30 | 2020-01-29 | $0.00 | $0.00
T1110 | 2019-12-30 | 2020-02-02 | Cost Loading - CASH OUT |  | 3.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | المواد الترويجية | MJ-MSBL-INT-1.14.3.1 | 25 | Branding | Fixed Duration & Units | 0 | 0% | 0% | 25 | 25 | 0% | $0.00 | $0.00 | $0.00 | 619 | 2019-12-30 | 2020-02-02 | $0.00 | $0.00
T1120 | 2020-02-23 | 2020-03-12 |  |  | 3.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | طباعة العقود | MJ-MSBL-INT-1.14.3.1 | 15 | Branding | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 633 | 2020-02-23 | 2020-03-12 | $0.00 | $0.00
T1130 | 2020-02-10 | 2020-03-23 |  |  | 3.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | طباعة البروشور | MJ-MSBL-INT-1.14.3.1 | 30 | Branding | Fixed Duration & Units | 0 | 0% | 0% | 30 | 30 | 0% | $0.00 | $0.00 | $0.00 | 619 | 2020-02-10 | 2020-03-23 | $0.00 | $0.00
T1140 | 2020-02-10 | 2020-03-02 | Cost Loading - CASH OUT |  | 3.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | القرطاسية | MJ-MSBL-INT-1.14.3.1 | 15 | Branding | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 619 | 2020-02-10 | 2020-03-02 | $0.00 | $0.00
T1150 | 2020-02-10 | 2020-03-22 | Cost Loading - CASH OUT |  | 3.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الحقائب | MJ-MSBL-INT-1.14.3.1 | 30 | Branding | Fixed Duration & Units | 0 | 0% | 0% | 30 | 30 | 0% | $0.00 | $0.00 | $0.00 | 629 | 2020-02-10 | 2020-03-22 | $0.00 | $0.00
T1160 | 2020-01-26 | 2020-03-22 | Cost Loading - CASH OUT |  | 3.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | هدايا الزوار | MJ-MSBL-INT-1.14.3.1 | 40 | Branding | Fixed Duration & Units | 0 | 0% | 0% | 40 | 40 | 0% | $0.00 | $0.00 | $0.00 | 629 | 2020-01-26 | 2020-03-22 | $0.00 | $0.00
T1170 | 2020-01-26 | 2020-03-22 | Cost Loading - CASH OUT |  | 3.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | هدايا العملاء | MJ-MSBL-INT-1.14.3.1 | 40 | Branding | Fixed Duration & Units | 0 | 0% | 0% | 40 | 40 | 0% | $0.00 | $0.00 | $0.00 | 629 | 2020-01-26 | 2020-03-22 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.4 Advertising Campaign | 2020-02-23 | 2020-03-16 | [7 empty] | 20 |  |  | 0 |  | 0% | 20 | 20 | 0% | $0.00 | $0.00 | $0.00 | 761 | 2020-02-23 | 2020-03-16 | $0.00 | $0.00
T1200 | 2020-02-23 | 2020-03-16 | Cost Loading - CASH OUT |  | 3.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الأعلام | MJ-MSBL-INT-1.14.3.4 | 20 | Advertising Campaign | Fixed Duration & Units | 0 | 0% | 0% | 20 | 20 | 0% | $0.00 | $0.00 | $0.00 | 761 | 2020-02-23 | 2020-03-16 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.5 Digital Marketing | 2020-02-13 | 2020-05-10 | [7 empty] | 61 |  |  | 0 |  | 0% | 61 | 61 | 0% | $0.00 | $0.00 | $0.00 | 639 | 2020-02-13 | 2020-05-10 | $0.00 | $0.00
T1300 | 2020-02-13 | 2020-03-19 | Cost Loading - CASH OUT |  | 3.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الموقع الالكتروني | MJ-MSBL-INT-1.14.3.5 | 25 | Digital Marketing | Fixed Duration & Units | 0 | 0% | 0% | 25 | 25 | 0% | $0.00 | $0.00 | $0.00 | 621 | 2020-02-13 | 2020-03-19 | $0.00 | $0.00
T1310 | 2020-03-12 | 2020-04-02 | Cost Loading - CASH OUT |  | 3.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | وسائل التواصل الاجتماعي - مرحلة ما قبل البيع | MJ-MSBL-INT-1.14.3.5 | 15 | Digital Marketing | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 621 | 2020-03-12 | 2020-04-02 | $0.00 | $0.00
T1320 | 2020-04-19 | 2020-04-23 | Cost Loading - CASH OUT |  | 3.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | وسائل التواصل الاجتماعي - مرحلة البيع | MJ-MSBL-INT-1.14.3.5 | 5 | Digital Marketing | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 639 | 2020-04-19 | 2020-04-23 | $0.00 | $0.00
T1330 | 2020-05-03 | 2020-05-10 | Cost Loading - CASH OUT |  | 3.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | وسائل التواصل الاجتماعي - مرحلة البيع التكميلية | MJ-MSBL-INT-1.14.3.5 | 5 | Digital Marketing | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 639 | 2020-05-03 | 2020-05-10 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.2 Sales Center | 2020-02-13 | 2020-05-02 | [7 empty] | 67 |  |  | 0 |  | 0% | 67 | 67 | 0% | $0.00 | $0.00 | $0.00 | 774 | 2020-02-13 | 2020-05-02 | $0.00 | $0.00
T1400 | 2020-02-13 | 2020-03-14 | Cost Loading - CASH OUT |  | 3.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | تأثيث مركز المبيعات | MJ-MSBL-INT-1.14.3.2 | 25 | Sales Center | Fixed Duration & Units | 0 | 0% | 0% | 25 | 25 | 0% | $0.00 | $0.00 | $0.00 | 763 | 2020-02-13 | 2020-03-14 | $0.00 | $0.00
T1410 | 2020-02-29 | 2020-03-16 | Cost Loading - CASH OUT |  | 3.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الديكورات وشاشات العرض | MJ-MSBL-INT-1.14.3.2 | 15 | Sales Center | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 761 | 2020-02-29 | 2020-03-16 | $0.00 | $0.00
T1420 | 2020-04-06 | 2020-05-02 | Cost Loading - CASH OUT |  | 3.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | التموينات | MJ-MSBL-INT-1.14.3.2 | 22 | Sales Center | Fixed Duration & Units | 0 | 0% | 0% | 22 | 22 | 0% | $0.00 | $0.00 | $0.00 | 774 | 2020-04-06 | 2020-05-02 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.7 Engineering Display Tools Production | 2020-02-10 | 2020-04-06 | [7 empty] | 40 |  |  | 0 |  | 0% | 40 | 40 | 0% | $0.00 | $0.00 | $0.00 | 619 | 2020-02-10 | 2020-04-06 | $0.00 | $0.00
T1500 | 2020-02-10 | 2020-04-06 | Cost Loading - CASH OUT |  | 3.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | النمذج ثلاثية الأبعاد | MJ-MSBL-INT-1.14.3.7 | 40 | Engineering Display Tools Production | Fixed Duration & Units | 0 | 0% | 0% | 40 | 40 | 0% | $0.00 | $0.00 | $0.00 | 619 | 2020-02-10 | 2020-04-06 | $0.00 | $0.00
T1510 | 2020-02-10 | 2020-04-06 | Cost Loading - CASH OUT |  | 3.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | الفيديو الدعائي | MJ-MSBL-INT-1.14.3.7 | 40 | Engineering Display Tools Production | Fixed Duration & Units | 0 | 0% | 0% | 40 | 40 | 0% | $0.00 | $0.00 | $0.00 | 619 | 2020-02-10 | 2020-04-06 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.6 Sales | 2020-08-19 | 2025-02-13 | [7 empty] | 1370 |  |  | 0 |  | 0% | 1370 | 1370 | 0% | $0.00 | $0.00 | $0.00 | 3348 | 2020-08-19 | 2025-02-13 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.6.9 Commercial Land Plots | 2020-08-19 | 2025-02-13 | [7 empty] | 1370 |  |  | 0 |  | 0% | 1370 | 1370 | 0% | $0.00 | $0.00 | $0.00 | 3348 | 2020-08-19 | 2025-02-13 | $0.00 | $0.00
L7020 | 2020-08-19 | 2025-02-13 | Cost Loading - CASH IN |  | 3.6.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Land Plots | MJ-MSBL-INT-1.14.3.6.9 | 1370 | Commercial Land Plots | Fixed Duration and Units/Time | 0 | 0% | 0% | 1370 | 1370 | 0% | $0.00 | $0.00 | $0.00 | 3348 | 2020-08-19 | 2025-02-13 | $0.00 | $0.00
M3020 | 2020-08-19 |  | Cost Loading - CASH IN, Cost Loading - CASH OUT |  | 3.6.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prep. & Support for Sales | MJ-MSBL-INT-1.14.3.6.9 | 0 | Commercial Land Plots | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3669 | 2020-08-19 |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.6.9.2 Launch Event | 2020-08-19 | 2020-10-19 | [7 empty] | 52 |  |  | 0 |  | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 3669 | 2020-08-19 | 2020-10-19 | $0.00 | $0.00
T7590 | 2020-08-19 | 2020-10-19 | Cost Loading - CASH IN |  | 3.6.9.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [Launch Event-LD 04] | MJ-MSBL-INT-1.14.3.6.9.2 | 52 | Launch Event | Fixed Duration and Units/Time | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 3669 | 19-Aug-20* | 2020-10-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.6.9.3 Further Events | 2020-10-20 | 2025-02-13 | [7 empty] | 1318 |  |  | 0 |  | 0% | 1318 | 1318 | 0% | $0.00 | $0.00 | $0.00 | 3348 | 2020-10-20 | 2025-02-13 | $0.00 | $0.00
T7600 | 2020-10-20 | 2020-12-14 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [2nd Event-LD 07] | MJ-MSBL-INT-1.14.3.6.9.3 | 48 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 48 | 48 | 0% | $0.00 | $0.00 | $0.00 | 3669 | 20-Oct-20* | 2020-12-14 | $0.00 | $0.00
T7610 | 2020-12-15 | 2021-02-23 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [3rd Event-LD 10] | MJ-MSBL-INT-1.14.3.6.9.3 | 61 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 61 | 61 | 0% | $0.00 | $0.00 | $0.00 | 3669 | 15-Dec-20* | 2021-02-23 | $0.00 | $0.00
T7620 | 2021-02-23 | 2021-04-25 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [4th Event-LD 13] | MJ-MSBL-INT-1.14.3.6.9.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 3669 | 23-Feb-21* | 2021-04-25 | $0.00 | $0.00
T7630 | 2024-12-01 | 2025-02-13 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [19th Event-LD 03] | MJ-MSBL-INT-1.14.3.6.9.3 | 65 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 65 | 65 | 0% | $0.00 | $0.00 | $0.00 | 3348 | 01-Dec-24* | 2025-02-13 | $0.00 | $0.00
T7640 | 2021-04-25 | 2021-06-28 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [5th Event-LD 01] | MJ-MSBL-INT-1.14.3.6.9.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 3669 | 25-Apr-21* | 2021-06-28 | $0.00 | $0.00
T7650 | 2021-06-28 | 2021-08-31 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [6th Event-LD 05] | MJ-MSBL-INT-1.14.3.6.9.3 | 51 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 3669 | 28-Jun-21* | 2021-08-31 | $0.00 | $0.00
T7660 | 2021-08-31 | 2021-11-13 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [7th Event-LD 08] | MJ-MSBL-INT-1.14.3.6.9.3 | 62 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 62 | 62 | 0% | $0.00 | $0.00 | $0.00 | 3669 | 31-Aug-21* | 2021-11-13 | $0.00 | $0.00
T7670 | 2021-11-13 | 2022-01-12 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [8th Event-LD 11] | MJ-MSBL-INT-1.14.3.6.9.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 3669 | 13-Nov-21* | 2022-01-12 | $0.00 | $0.00
T7680 | 2022-01-12 | 2022-03-14 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [9th Event-LD 14] | MJ-MSBL-INT-1.14.3.6.9.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 3669 | 12-Jan-22* | 2022-03-14 | $0.00 | $0.00
T7690 | 2022-03-14 | 2022-06-01 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [10th Event-LD 15] | MJ-MSBL-INT-1.14.3.6.9.3 | 65 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 65 | 65 | 0% | $0.00 | $0.00 | $0.00 | 3669 | 14-Mar-22* | 2022-06-01 | $0.00 | $0.00
T7700 | 2022-10-01 | 2022-11-30 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [11th Event-LD 16] | MJ-MSBL-INT-1.14.3.6.9.3 | 53 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 53 | 53 | 0% | $0.00 | $0.00 | $0.00 | 3571 | 01-Oct-22* | 2022-11-30 | $0.00 | $0.00
T7710 | 2022-12-01 | 2023-01-30 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [12th Event-LD 17] | MJ-MSBL-INT-1.14.3.6.9.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 3571 | 01-Dec-22* | 2023-01-30 | $0.00 | $0.00
T7720 | 2023-02-01 | 2023-04-17 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [13th Event-LD 18] | MJ-MSBL-INT-1.14.3.6.9.3 | 65 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 65 | 65 | 0% | $0.00 | $0.00 | $0.00 | 3570 | 01-Feb-23* | 2023-04-17 | $0.00 | $0.00
T7730 | 2023-10-01 | 2023-11-30 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [14th Event-LD 19] | MJ-MSBL-INT-1.14.3.6.9.3 | 53 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 53 | 53 | 0% | $0.00 | $0.00 | $0.00 | 3437 | 01-Oct-23* | 2023-11-30 | $0.00 | $0.00
T7740 | 2023-12-02 | 2024-01-30 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [15th Event-LD 09] | MJ-MSBL-INT-1.14.3.6.9.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 3437 | 02-Dec-23* | 2024-01-30 | $0.00 | $0.00
T7750 | 2024-02-01 | 2024-03-31 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [16th Event-LD 12] | MJ-MSBL-INT-1.14.3.6.9.3 | 51 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 3436 | 01-Feb-24* | 2024-03-31 | $0.00 | $0.00
T7760 | 2024-04-01 | 2024-06-13 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [17th Event-LD 06] | MJ-MSBL-INT-1.14.3.6.9.3 | 60 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $0.00 | $0.00 | $0.00 | 3436 | 01-Apr-24* | 2024-06-13 | $0.00 | $0.00
T7770 | 2024-10-01 | 2024-11-30 | Cost Loading - CASH IN |  | 3.6.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Commercial Units [18th Event-LD 02] | MJ-MSBL-INT-1.14.3.6.9.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 3348 | 01-Oct-24* | 2024-11-30 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.6.20 Residential Units - MOH Beneficiaries | 2020-08-19 | 2023-04-02 | [7 empty] | 802 |  |  | 0 |  | 0% | 802 | 802 | 0% | $0.00 | $0.00 | $0.00 | 978 | 2020-08-19 | 2023-04-02 | $0.00 | $0.00
L1600 | 2020-08-19 | 2023-04-02 | Cost Loading - CASH IN |  | 3.6.20 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH Units | MJ-MSBL-INT-1.14.3.6.20 | 802 | Residential Units - MOH Beneficiaries | Fixed Duration and Units/Time | 0 | 0% | 0% | 802 | 802 | 0% | $0.00 | $0.00 | $0.00 | 978 | 2020-08-19 | 2023-04-02 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.6.20.2 Launch Event | 2020-08-19 | 2020-10-19 | [7 empty] | 52 |  |  | 0 |  | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 636 | 2020-08-19 | 2020-10-19 | $0.00 | $0.00
T7030 | 2020-08-19 | 2020-10-19 | Cost Loading - CASH IN |  | 3.6.20.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH [Launch Event-LD 04] | MJ-MSBL-INT-1.14.3.6.20.2 | 52 | Launch Event | Fixed Duration and Units/Time | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 636 | 19-Aug-20* | 2020-10-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.6.20.3 Further Events | 2020-10-20 | 2023-04-02 | [7 empty] | 750 |  |  | 0 |  | 0% | 750 | 750 | 0% | $0.00 | $0.00 | $0.00 | 978 | 2020-10-20 | 2023-04-02 | $0.00 | $0.00
T7410 | 2020-10-20 | 2020-12-14 | Cost Loading - CASH IN |  | 3.6.20.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH [2nd Event-LD 07] | MJ-MSBL-INT-1.14.3.6.20.3 | 48 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 48 | 48 | 0% | $0.00 | $0.00 | $0.00 | 666 | 20-Oct-20* | 2020-12-14 | $0.00 | $0.00
T7420 | 2020-12-15 | 2021-02-23 | Cost Loading - CASH IN |  | 3.6.20.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH [3rd Event-LD 10] | MJ-MSBL-INT-1.14.3.6.20.3 | 61 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 61 | 61 | 0% | $0.00 | $0.00 | $0.00 | 684 | 15-Dec-20* | 2021-02-23 | $0.00 | $0.00
T7430 | 2021-02-23 | 2021-04-25 | Cost Loading - CASH IN |  | 3.6.20.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH [4th Event-LD 13] | MJ-MSBL-INT-1.14.3.6.20.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 710 | 23-Feb-21* | 2021-04-25 | $0.00 | $0.00
T7450 | 2021-04-25 | 2021-06-28 | Cost Loading - CASH IN |  | 3.6.20.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH [5th Event-LD 01] | MJ-MSBL-INT-1.14.3.6.20.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 736 | 25-Apr-21* | 2021-06-28 | $0.00 | $0.00
T7460 | 2021-06-28 | 2021-08-31 | Cost Loading - CASH IN |  | 3.6.20.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH [6th Event-LD 05] | MJ-MSBL-INT-1.14.3.6.20.3 | 51 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 763 | 28-Jun-21* | 2021-08-31 | $0.00 | $0.00
T7470 | 2021-08-31 | 2021-11-13 | Cost Loading - CASH IN |  | 3.6.20.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH [7th Event-LD 08] | MJ-MSBL-INT-1.14.3.6.20.3 | 62 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 62 | 62 | 0% | $0.00 | $0.00 | $0.00 | 779 | 31-Aug-21* | 2021-11-13 | $0.00 | $0.00
T7480 | 2021-11-13 | 2022-01-12 | Cost Loading - CASH IN |  | 3.6.20.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH [8th Event-LD 11] | MJ-MSBL-INT-1.14.3.6.20.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 805 | 13-Nov-21* | 2022-01-12 | $0.00 | $0.00
T7490 | 2022-01-12 | 2022-03-14 | Cost Loading - CASH IN |  | 3.6.20.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH [9th Event-LD 14] | MJ-MSBL-INT-1.14.3.6.20.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 831 | 12-Jan-22* | 2022-03-14 | $0.00 | $0.00
T7500 | 2022-03-14 | 2022-06-01 | Cost Loading - CASH IN |  | 3.6.20.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH [10th Event-LD 15] | MJ-MSBL-INT-1.14.3.6.20.3 | 65 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 65 | 65 | 0% | $0.00 | $0.00 | $0.00 | 844 | 14-Mar-22* | 2022-06-01 | $0.00 | $0.00
T7510 | 2022-10-01 | 2022-11-30 | Cost Loading - CASH IN |  | 3.6.20.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH [11th Event-LD 16] | MJ-MSBL-INT-1.14.3.6.20.3 | 53 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 53 | 53 | 0% | $0.00 | $0.00 | $0.00 | 771 | 01-Oct-22* | 2022-11-30 | $0.00 | $0.00
T7540 | 2022-12-01 | 2023-01-31 | Cost Loading - CASH IN |  | 3.6.20.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH [12th Event-LD 17] | MJ-MSBL-INT-1.14.3.6.20.3 | 53 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 53 | 53 | 0% | $0.00 | $0.00 | $0.00 | 952 | 01-Dec-22* | 2023-01-31 | $0.00 | $0.00
T7550 | 2023-02-01 | 2023-04-02 | Cost Loading - CASH IN |  | 3.6.20.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units - MOH [13th Event-LD 18] | MJ-MSBL-INT-1.14.3.6.20.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 978 | 01-Feb-23* | 2023-04-02 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.6.21 Residential Units - Other Beneficiaries | 2023-10-01 | 2025-02-13 | [7 empty] | 422 |  |  | 0 |  | 0% | 422 | 422 | 0% | $0.00 | $0.00 | $0.00 | 723 | 2023-10-01 | 2025-02-13 | $0.00 | $0.00
L7010 | 2023-10-01 | 2025-02-13 | Cost Loading - CASH IN |  | 3.6.21 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units | MJ-MSBL-INT-1.14.3.6.21 | 422 | Residential Units - Other Beneficiaries | Fixed Duration and Units/Time | 0 | 0% | 0% | 422 | 422 | 0% | $0.00 | $0.00 | $0.00 | 723 | 2023-10-01 | 2025-02-13 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.6.21.2 Launch Event | 2023-10-01 | 2023-11-29 | [7 empty] | 52 |  |  | 0 |  | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 435 | 2023-10-01 | 2023-11-29 | $0.00 | $0.00
T7370 | 2023-10-01 | 2023-11-29 | Cost Loading - CASH IN |  | 3.6.21.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units [14th Event-LD 019] | MJ-MSBL-INT-1.14.3.6.21.2 | 52 | Launch Event | Fixed Duration and Units/Time | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 435 | 01-Oct-23* | 2023-11-29 | $0.00 | $0.00
MJ-MSBL-INT-1.14.3.6.21.3 Further Events | 2023-12-02 | 2025-02-13 | [7 empty] | 369 |  |  | 0 |  | 0% | 369 | 369 | 0% | $0.00 | $0.00 | $0.00 | 723 | 2023-12-02 | 2025-02-13 | $0.00 | $0.00
T7250 | 2024-12-01 | 2025-02-13 | Cost Loading - CASH IN |  | 3.6.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units [19th Event-LD 03] | MJ-MSBL-INT-1.14.3.6.21.3 | 65 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 65 | 65 | 0% | $0.00 | $0.00 | $0.00 | 723 | 01-Dec-24* | 2025-02-13 | $0.00 | $0.00
T7380 | 2023-12-02 | 2024-02-07 | Cost Loading - CASH IN |  | 3.6.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units [15th Event-LD 09] | MJ-MSBL-INT-1.14.3.6.21.3 | 59 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 59 | 59 | 0% | $0.00 | $0.00 | $0.00 | 434 | 02-Dec-23* | 2024-02-07 | $0.00 | $0.00
T7390 | 2024-10-01 | 2024-11-30 | Cost Loading - CASH IN |  | 3.6.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units [18th Event-LD 02] | MJ-MSBL-INT-1.14.3.6.21.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 709 | 01-Oct-24* | 2024-11-30 | $0.00 | $0.00
T7520 | 2024-02-08 | 2024-04-08 | Cost Loading - CASH IN |  | 3.6.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units [16th Event-LD 12] | MJ-MSBL-INT-1.14.3.6.21.3 | 52 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 52 | 52 | 0% | $0.00 | $0.00 | $0.00 | 434 | 08-Feb-24* | 2024-04-08 | $0.00 | $0.00
T7530 | 2024-04-09 | 2024-07-02 | Cost Loading - CASH IN |  | 3.6.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sales Events for Residential Units [17th Event-LD 06] | MJ-MSBL-INT-1.14.3.6.21.3 | 65 | Further Events | Fixed Duration & Units | 0 | 0% | 0% | 65 | 65 | 0% | $0.00 | $0.00 | $0.00 | 448 | 09-Apr-24* | 2024-07-02 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4 Pre-Construction Phase | 2017-01-02 | 2027-07-05 | [7 empty] | 3263 |  |  | 790 |  | 0% | 3263 | 2444 | 0% | $320,013.00 | $0.00 | $0.00 | 2672 | 05-Apr-16 A | 2027-07-05 | $0.00 | $0.00
A13670 | 2018-12-16 | 2018-12-30 |  |  | 4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Consultants Prequalifications / Invitations | MJ-MSBL-INT-1.14.4 | 11 | Pre-Construction Phase | Fixed Duration & Units | 12 | 100% | 100% | 11 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 05-Apr-16 A | 21-Apr-16 A | $0.00 | $0.00
A13680 | 2018-12-30 | 2019-02-27 |  |  | 4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding | MJ-MSBL-INT-1.14.4 | 43 | Pre-Construction Phase | Fixed Duration and Units/Time | 32 | 100% | 100% | 43 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 15-Nov-16 A | 30-Jul-17 A | $0.00 | $0.00
A13690 |  | 2019-09-15 |  |  | 4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sign Site Supervision Contract Agreement (K&A) | MJ-MSBL-INT-1.14.4 | 0 | Pre-Construction Phase | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 754 |  | 2019-09-15 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.1 Site Offices & Security Center | 2019-05-26 | 2019-09-15 | [7 empty] | 73 |  |  | 146 |  | 0% | 73 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3920 | 01-Jan-17 A | 2019-09-15 | $0.00 | $0.00
A12420 | 2019-06-20 | 2019-07-03 | Cost Loading - CASH OUT |  | 4.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Site Offices & Security Center] | MJ-MSBL-INT-1.14.4.1 | 10 | Site Offices & Security Center | Fixed Duration and Units/Time | 3 | 100% | 100% | 10 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 20-Feb-17 A | 23-Feb-17 A | $0.00 | $0.00
A12430 | 2019-05-26 | 2019-05-30 |  |  | 4.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Prequalifications [Site Offices & Security Center] | MJ-MSBL-INT-1.14.4.1 | 5 | Site Offices & Security Center | Fixed Duration & Units | 7 | 100% | 100% | 5 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 01-Jan-17 A | 10-Jan-17 A | $0.00 | $0.00
A12440 | 2019-06-02 | 2019-06-12 |  |  | 4.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Site Offices & Security Center] | MJ-MSBL-INT-1.14.4.1 | 5 | Site Offices & Security Center | Fixed Duration & Units | 0 | 100% | 100% | 5 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 14-Jan-17 A | 15-Jan-17 A | $0.00 | $0.00
A12450 | 2019-06-13 | 2019-07-03 | Cost Loading - CASH OUT |  | 4.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Site Off. & Sec. Center] | MJ-MSBL-INT-1.14.4.1 | 15 | Site Offices & Security Center | Fixed Duration and Units/Time | 29 | 100% | 100% | 15 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 15-Jan-17 A | 30-Jul-17 A | $0.00 | $0.00
A13710 |  | 2019-09-15 |  |  | 4.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sign Constrcution Contract Agreement [Al-Masha'al] [Site Off. & Sec. Center] | MJ-MSBL-INT-1.14.4.1 | 0 | Site Offices & Security Center | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3920 |  | 2019-09-15 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.9 Main Infrastructure Networks, Roads & Landscape | 2017-01-02 | 2022-05-24 | [7 empty] | 1365 |  |  | 146 |  | 0% | 1365 | 683 | 0% | $120,000.00 | $0.00 | $0.00 | 2749 | 02-Jan-17 A | 2022-05-24 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.9.1 Rough Grading | 2017-01-02 | 2019-09-15 | [7 empty] | 682 |  |  | 146 |  | 0% | 682 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3432 | 02-Jan-17 A | 2019-09-15 | $0.00 | $0.00
A12220 | 2017-06-20 | 2017-07-09 | Cost Loading - CASH OUT |  | 4.9.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Rough Grading] | MJ-MSBL-INT-1.14.4.9.1 | 10 | Rough Grading | Fixed Duration and Units/Time | 2 | 100% | 100% | 10 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 20-Feb-17 A | 22-Feb-17 A | $0.00 | $0.00
A12230 | 2017-01-02 | 2017-01-08 |  |  | 4.9.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Prequalifications [Rough Grading] | MJ-MSBL-INT-1.14.4.9.1 | 5 | Rough Grading | Fixed Duration & Units | 5 | 100% | 100% | 5 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 02-Jan-17 A | 08-Jan-17 A | $0.00 | $0.00
A12240 | 2017-01-15 | 2017-01-19 |  |  | 4.9.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Rough Grading] | MJ-MSBL-INT-1.14.4.9.1 | 5 | Rough Grading | Fixed Duration & Units | 1 | 100% | 100% | 5 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 14-Jan-17 A | 15-Jan-17 A | $0.00 | $0.00
A12250 | 2017-01-15 | 2017-02-22 | Cost Loading - CASH OUT |  | 4.9.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Rough Grading] | MJ-MSBL-INT-1.14.4.9.1 | 29 | Rough Grading | Fixed Duration and Units/Time | 29 | 100% | 100% | 29 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 15-Jan-17 A | 30-Jul-17 A | $0.00 | $0.00
A13700 |  | 2019-09-15 |  |  | 4.9.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Sign Constrcution Contract Agreement [Al-Hayzam] [Rough Grading] | MJ-MSBL-INT-1.14.4.9.1 | 0 | Rough Grading | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3432 |  | 2019-09-15 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.9.2 Main Infrastructure Networks & Roads | 2020-01-14 | 2020-04-01 | [7 empty] | 57 |  |  | 0 |  | 0% | 57 | 57 | 0% | $20,000.00 | $0.00 | $0.00 | 2956 | 2020-01-14 | 2020-04-01 | $0.00 | $0.00
A12150 | 2020-01-14 | 2020-02-03 |  |  | 4.9.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Prequalifications [Main Infra. Networks] | MJ-MSBL-INT-1.14.4.9.2 | 15 | Main Infrastructure Networks & Roads | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 2538 | 2020-01-14 | 2020-02-03 | $0.00 | $0.00
A12160 | 2020-02-04 | 2020-02-10 |  |  | 4.9.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Main Infra. Networks] | MJ-MSBL-INT-1.14.4.9.2 | 5 | Main Infrastructure Networks & Roads | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2538 | 2020-02-04 | 2020-02-10 | $0.00 | $0.00
A12170 | 2020-02-11 | 2020-04-01 | Cost Loading - CASH OUT |  | 4.9.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Main Infra. Networks] | MJ-MSBL-INT-1.14.4.9.2 | 37 | Main Infrastructure Networks & Roads | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2943 | 2020-02-11 | 2020-04-01 | $0.00 | $0.00
A12180 | 2020-03-18 | 2020-04-01 | Cost Loading - CASH OUT |  | 4.9.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Main Infra. Networks] | MJ-MSBL-INT-1.14.4.9.2 | 11 | Main Infrastructure Networks & Roads | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $20,000.00 | $0.00 | $0.00 | 2956 | 2020-03-18 | 2020-04-01 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.9.4 Concrete Structures (Northern Entrances) | 2020-02-04 | 2020-06-30 | [7 empty] | 102 |  |  | 0 |  | 0% | 102 | 102 | 0% | $20,000.00 | $0.00 | $0.00 | 3137 | 2020-02-04 | 2020-06-30 | $0.00 | $0.00
A12460 | 2020-06-16 | 2020-06-30 | Cost Loading - CASH OUT |  | 4.9.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Concrete Structures-N. Entr.] | MJ-MSBL-INT-1.14.4.9.4 | 11 | Concrete Structures (Northern Entrances) | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $20,000.00 | $0.00 | $0.00 | 3137 | 2020-06-16 | 2020-06-30 | $0.00 | $0.00
A12470 | 2020-02-04 | 2020-02-24 |  |  | 4.9.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Prequalifications [Concrete Structures-N. Entr.] | MJ-MSBL-INT-1.14.4.9.4 | 15 | Concrete Structures (Northern Entrances) | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 2573 | 2020-02-04 | 2020-02-24 | $0.00 | $0.00
A12480 | 2020-04-14 | 2020-04-27 |  |  | 4.9.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Concrete Structures-N. Entr.] | MJ-MSBL-INT-1.14.4.9.4 | 10 | Concrete Structures (Northern Entrances) | Fixed Duration & Units | 0 | 0% | 0% | 10 | 10 | 0% | $0.00 | $0.00 | $0.00 | 2538 | 2020-04-14 | 2020-04-27 | $0.00 | $0.00
A12490 | 2020-04-28 | 2020-06-30 |  |  | 4.9.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Conc.Str. preparation/submission of proposals / negotiation & Awarding [Concrete Structures-N. Entr.] | MJ-MSBL-INT-1.14.4.9.4 | 42 | Concrete Structures (Northern Entrances) | Fixed Duration and Units/Time | 0 | 0% | 0% | 42 | 42 | 0% | $0.00 | $0.00 | $0.00 | 3137 | 2020-04-28 | 2020-06-30 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.9.6 HV Substations | 2020-02-25 | 2021-05-19 | [7 empty] | 312 |  |  | 0 |  | 0% | 312 | 312 | 0% | $20,000.00 | $0.00 | $0.00 | 2914 | 2020-02-25 | 2021-05-19 | $0.00 | $0.00
A12540 | 2021-05-03 | 2021-05-19 | Cost Loading - CASH OUT |  | 4.9.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [HV S/S] | MJ-MSBL-INT-1.14.4.9.6 | 11 | HV Substations | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $20,000.00 | $0.00 | $0.00 | 2914 | 2021-05-03 | 2021-05-19 | $0.00 | $0.00
A12550 | 2020-02-25 | 2020-03-16 |  |  | 4.9.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Prequalifications [HV S/S] | MJ-MSBL-INT-1.14.4.9.6 | 15 | HV Substations | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 2753 | 2020-02-25 | 2020-03-16 | $0.00 | $0.00
A12560 | 2021-03-07 | 2021-03-18 |  |  | 4.9.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [HV S/S] | MJ-MSBL-INT-1.14.4.9.6 | 10 | HV Substations | Fixed Duration & Units | 0 | 0% | 0% | 10 | 10 | 0% | $0.00 | $0.00 | $0.00 | 2538 | 2021-03-07 | 2021-03-18 | $0.00 | $0.00
A12570 | 2021-03-21 | 2021-05-19 |  |  | 4.9.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [HV S/S] | MJ-MSBL-INT-1.14.4.9.6 | 42 | HV Substations | Fixed Duration and Units/Time | 0 | 0% | 0% | 42 | 42 | 0% | $0.00 | $0.00 | $0.00 | 2914 | 2021-03-21 | 2021-05-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.9.7 Sewer Water Treatment Plant [STP] | 2020-03-17 | 2021-05-19 | [7 empty] | 297 |  |  | 0 |  | 0% | 297 | 297 | 0% | $0.00 | $0.00 | $0.00 | 2859 | 2020-03-17 | 2021-05-19 | $0.00 | $0.00
A12580 | 2021-05-03 | 2021-05-19 | Cost Loading - CASH OUT |  | 4.9.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [STP] | MJ-MSBL-INT-1.14.4.9.7 | 11 | Sewer Water Treatment Plant [STP] | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $0.00 | $0.00 | $0.00 | 2859 | 2021-05-03 | 2021-05-19 | $0.00 | $0.00
A12590 | 2020-03-17 | 2020-04-06 |  |  | 4.9.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Prequalifications [STP] | MJ-MSBL-INT-1.14.4.9.7 | 15 | Sewer Water Treatment Plant [STP] | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 2753 | 2020-03-17 | 2020-04-06 | $0.00 | $0.00
A12600 | 2021-03-07 | 2021-03-18 |  |  | 4.9.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [STP] | MJ-MSBL-INT-1.14.4.9.7 | 10 | Sewer Water Treatment Plant [STP] | Fixed Duration & Units | 0 | 0% | 0% | 10 | 10 | 0% | $0.00 | $0.00 | $0.00 | 2538 | 2021-03-07 | 2021-03-18 | $0.00 | $0.00
A12610 | 2021-03-21 | 2021-05-19 |  |  | 4.9.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [STP] | MJ-MSBL-INT-1.14.4.9.7 | 42 | Sewer Water Treatment Plant [STP] | Fixed Duration and Units/Time | 0 | 0% | 0% | 42 | 42 | 0% | $0.00 | $0.00 | $0.00 | 2859 | 2021-03-21 | 2021-05-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.9.8 Open Channel [Storm Water Drainage] | 2020-04-07 | 2021-05-19 | [7 empty] | 282 |  |  | 0 |  | 0% | 282 | 282 | 0% | $20,000.00 | $0.00 | $0.00 | 2721 | 2020-04-07 | 2021-05-19 | $0.00 | $0.00
A12620 | 2021-05-03 | 2021-05-19 | Cost Loading - CASH OUT |  | 4.9.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Open Channel] | MJ-MSBL-INT-1.14.4.9.8 | 11 | Open Channel [Storm Water Drainage] | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $20,000.00 | $0.00 | $0.00 | 2721 | 2021-05-03 | 2021-05-19 | $0.00 | $0.00
A12630 | 2020-04-07 | 2020-04-27 |  |  | 4.9.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Prequalifications [Open Channel] | MJ-MSBL-INT-1.14.4.9.8 | 15 | Open Channel [Storm Water Drainage] | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 2753 | 2020-04-07 | 2020-04-27 | $0.00 | $0.00
A12640 | 2021-03-07 | 2021-03-18 |  |  | 4.9.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Open Channel] | MJ-MSBL-INT-1.14.4.9.8 | 10 | Open Channel [Storm Water Drainage] | Fixed Duration & Units | 0 | 0% | 0% | 10 | 10 | 0% | $0.00 | $0.00 | $0.00 | 2538 | 2021-03-07 | 2021-03-18 | $0.00 | $0.00
A12650 | 2021-03-21 | 2021-05-19 |  |  | 4.9.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Open Channel] | MJ-MSBL-INT-1.14.4.9.8 | 42 | Open Channel [Storm Water Drainage] | Fixed Duration and Units/Time | 0 | 0% | 0% | 42 | 42 | 0% | $0.00 | $0.00 | $0.00 | 2721 | 2021-03-21 | 2021-05-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.9.9 Road Finishes & Street Lighting | 2020-04-28 | 2021-11-24 | [7 empty] | 397 |  |  | 0 |  | 0% | 397 | 397 | 0% | $20,000.00 | $0.00 | $0.00 | 2720 | 2020-04-28 | 2021-11-24 | $0.00 | $0.00
A12660 | 2021-11-10 | 2021-11-24 | Cost Loading - CASH OUT |  | 4.9.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [RD & St. L.] | MJ-MSBL-INT-1.14.4.9.9 | 11 | Road Finishes & Street Lighting | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $20,000.00 | $0.00 | $0.00 | 2720 | 2021-11-10 | 2021-11-24 | $0.00 | $0.00
A12670 | 2020-04-28 | 2020-05-18 |  |  | 4.9.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Prequalifications [RD & St. L.] | MJ-MSBL-INT-1.14.4.9.9 | 15 | Road Finishes & Street Lighting | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 2868 | 2020-04-28 | 2020-05-18 | $0.00 | $0.00
A12680 | 2021-09-13 | 2021-09-27 |  |  | 4.9.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [RD & St. L.] | MJ-MSBL-INT-1.14.4.9.9 | 10 | Road Finishes & Street Lighting | Fixed Duration & Units | 0 | 0% | 0% | 10 | 10 | 0% | $0.00 | $0.00 | $0.00 | 2538 | 2021-09-13 | 2021-09-27 | $0.00 | $0.00
A12690 | 2021-09-28 | 2021-11-24 |  |  | 4.9.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [RD & St. L.] | MJ-MSBL-INT-1.14.4.9.9 | 42 | Road Finishes & Street Lighting | Fixed Duration and Units/Time | 0 | 0% | 0% | 42 | 42 | 0% | $0.00 | $0.00 | $0.00 | 2720 | 2021-09-28 | 2021-11-24 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.9.10 Landscape Work | 2020-05-19 | 2022-05-24 | [7 empty] | 507 |  |  | 0 |  | 0% | 507 | 507 | 0% | $20,000.00 | $0.00 | $0.00 | 2538 | 2020-05-19 | 2022-05-24 | $0.00 | $0.00
A12280 | 2020-05-19 | 2020-06-14 |  |  | 4.9.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Prequalifications [Landscape] | MJ-MSBL-INT-1.14.4.9.10 | 15 | Landscape Work | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 2978 | 2020-05-19 | 2020-06-14 | $0.00 | $0.00
A12290 | 2022-03-08 | 2022-03-21 |  |  | 4.9.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Landscape] | MJ-MSBL-INT-1.14.4.9.10 | 10 | Landscape Work | Fixed Duration & Units | 0 | 0% | 0% | 10 | 10 | 0% | $0.00 | $0.00 | $0.00 | 2538 | 2022-03-08 | 2022-03-21 | $0.00 | $0.00
A12300 | 2022-03-22 | 2022-05-24 |  |  | 4.9.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Landscape] | MJ-MSBL-INT-1.14.4.9.10 | 42 | Landscape Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 42 | 42 | 0% | $0.00 | $0.00 | $0.00 | 2538 | 2022-03-22 | 2022-05-24 | $0.00 | $0.00
A12310 | 2022-05-10 | 2022-05-24 | Cost Loading - CASH OUT |  | 4.9.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Landscape] | MJ-MSBL-INT-1.14.4.9.10 | 11 | Landscape Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $20,000.00 | $0.00 | $0.00 | 2538 | 2022-05-10 | 2022-05-24 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3 Secondary Infrastructure Networks | 2020-07-08 | 2025-10-06 | [7 empty] | 1329 |  |  | 0 |  | 0% | 1329 | 1329 | 0% | $120,004.00 | $0.00 | $0.00 | 2213 | 2020-07-08 | 2025-10-06 | $0.00 | $0.00
A11950 | 2020-07-08 | 2020-07-29 |  |  | 4.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Infra. Contractors Prequalifications | MJ-MSBL-INT-1.14.4.3 | 15 | Secondary Infrastructure Networks | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2020-07-08 | 2020-07-29 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2 MOH Beneficiaries' Units | 2020-07-29 | 2024-08-21 | [7 empty] | 1030 |  |  | 0 |  | 0% | 1030 | 1030 | 0% | $94,740.00 | $0.00 | $0.00 | 2497 | 2020-07-29 | 2024-08-21 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.19 Package (01] | 2020-07-29 | 2021-04-19 | [7 empty] | 184 |  |  | 0 |  | 0% | 184 | 184 | 0% | $18,948.00 | $0.00 | $0.00 | 3328 | 2020-07-29 | 2021-04-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.19.1 Priority 01 | 2020-07-29 | 2020-10-01 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 3470 | 2020-07-29 | 2020-10-01 | $0.00 | $0.00
A11940 | 2020-09-15 | 2020-10-01 | Cost Loading - CASH OUT |  | 4.3.2.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 01] | MJ-MSBL-INT-1.14.4.3.2.19.1 | 11 | Priority 01 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 3470 | 2020-09-15 | 2020-10-01 | $0.00 | $0.00
A11960 | 2020-07-29 | 2020-08-10 |  |  | 4.3.2.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Priority 01] | MJ-MSBL-INT-1.14.4.3.2.19.1 | 5 | Priority 01 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2020-07-29 | 2020-08-10 | $0.00 | $0.00
A11970 | 2020-08-10 | 2020-10-01 |  |  | 4.3.2.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 01] | MJ-MSBL-INT-1.14.4.3.2.19.1 | 37 | Priority 01 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 3470 | 2020-08-10 | 2020-10-01 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.19.2 Priority 02 | 2020-11-11 | 2021-01-10 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 3139 | 2020-11-11 | 2021-01-10 | $0.00 | $0.00
A12870 | 2020-11-11 | 2020-11-18 |  |  | 4.3.2.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Priority 02] | MJ-MSBL-INT-1.14.4.3.2.19.2 | 5 | Priority 02 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2020-11-11 | 2020-11-18 | $0.00 | $0.00
A12880 | 2020-11-18 | 2021-01-10 |  |  | 4.3.2.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 02] | MJ-MSBL-INT-1.14.4.3.2.19.2 | 37 | Priority 02 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 3139 | 2020-11-18 | 2021-01-10 | $0.00 | $0.00
A12890 | 2020-12-24 | 2021-01-10 | Cost Loading - CASH OUT |  | 4.3.2.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 02] | MJ-MSBL-INT-1.14.4.3.2.19.2 | 11 | Priority 02 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 3139 | 2020-12-24 | 2021-01-10 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.19.4 Priority 04 | 2021-02-18 | 2021-04-19 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 3070 | 2021-02-18 | 2021-04-19 | $0.00 | $0.00
A12900 | 2021-02-18 | 2021-02-25 |  |  | 4.3.2.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Priority 04] | MJ-MSBL-INT-1.14.4.3.2.19.4 | 5 | Priority 04 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2021-02-18 | 2021-02-25 | $0.00 | $0.00
A12910 | 2021-02-25 | 2021-04-19 |  |  | 4.3.2.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 04] | MJ-MSBL-INT-1.14.4.3.2.19.4 | 37 | Priority 04 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 3070 | 2021-02-25 | 2021-04-19 | $0.00 | $0.00
A12920 | 2021-04-04 | 2021-04-19 | Cost Loading - CASH OUT |  | 4.3.2.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 04] | MJ-MSBL-INT-1.14.4.3.2.19.4 | 11 | Priority 04 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 3070 | 2021-04-04 | 2021-04-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.20 Package (02) | 2021-06-01 | 2022-09-18 | [7 empty] | 326 |  |  | 0 |  | 0% | 326 | 326 | 0% | $31,580.00 | $0.00 | $0.00 | 2988 | 2021-06-01 | 2022-09-18 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.20.5 Priority 05 | 2021-06-01 | 2021-08-04 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 2999 | 2021-06-01 | 2021-08-04 | $0.00 | $0.00
A12930 | 2021-06-01 | 2021-06-08 |  |  | 4.3.2.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Priority 05] | MJ-MSBL-INT-1.14.4.3.2.20.5 | 5 | Priority 05 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2021-06-01 | 2021-06-08 | $0.00 | $0.00
A12940 | 2021-06-08 | 2021-08-04 |  |  | 4.3.2.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 05] | MJ-MSBL-INT-1.14.4.3.2.20.5 | 37 | Priority 05 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2999 | 2021-06-08 | 2021-08-04 | $0.00 | $0.00
A12950 | 2021-07-14 | 2021-08-04 | Cost Loading - CASH OUT |  | 4.3.2.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 05] | MJ-MSBL-INT-1.14.4.3.2.20.5 | 11 | Priority 05 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 2999 | 2021-07-14 | 2021-08-04 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.20.6 Priority 07 | 2021-09-14 | 2021-11-14 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 3189 | 2021-09-14 | 2021-11-14 | $0.00 | $0.00
A12000 | 2021-09-14 | 2021-09-21 |  |  | 4.3.2.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Priority 07] | MJ-MSBL-INT-1.14.4.3.2.20.6 | 5 | Priority 07 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2021-09-14 | 2021-09-21 | $0.00 | $0.00
A12010 | 2021-09-21 | 2021-11-14 |  |  | 4.3.2.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 07] | MJ-MSBL-INT-1.14.4.3.2.20.6 | 37 | Priority 07 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 3189 | 2021-09-21 | 2021-11-14 | $0.00 | $0.00
A12020 | 2021-10-28 | 2021-11-14 | Cost Loading - CASH OUT |  | 4.3.2.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 07] | MJ-MSBL-INT-1.14.4.3.2.20.6 | 11 | Priority 07 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 3189 | 2021-10-28 | 2021-11-14 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.20.8 Priority 08 | 2021-12-23 | 2022-02-21 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 3127 | 2021-12-23 | 2022-02-21 | $0.00 | $0.00
A12960 | 2021-12-23 | 2021-12-30 |  |  | 4.3.2.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Priority 08] | MJ-MSBL-INT-1.14.4.3.2.20.8 | 5 | Priority 08 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2021-12-23 | 2021-12-30 | $0.00 | $0.00
A12970 | 2021-12-30 | 2022-02-21 |  |  | 4.3.2.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 08] | MJ-MSBL-INT-1.14.4.3.2.20.8 | 37 | Priority 08 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 3127 | 2021-12-30 | 2022-02-21 | $0.00 | $0.00
A12980 | 2022-02-06 | 2022-02-21 | Cost Loading - CASH OUT |  | 4.3.2.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 08] | MJ-MSBL-INT-1.14.4.3.2.20.8 | 11 | Priority 08 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 3127 | 2022-02-06 | 2022-02-21 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.20.7 Priority 09 | 2022-04-03 | 2022-06-06 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 3059 | 2022-04-03 | 2022-06-06 | $0.00 | $0.00
A12990 | 2022-04-03 | 2022-04-10 |  |  | 4.3.2.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Priority 09] | MJ-MSBL-INT-1.14.4.3.2.20.7 | 5 | Priority 09 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2022-04-03 | 2022-04-10 | $0.00 | $0.00
A13000 | 2022-04-10 | 2022-06-06 |  |  | 4.3.2.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 09] | MJ-MSBL-INT-1.14.4.3.2.20.7 | 37 | Priority 09 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 3059 | 2022-04-10 | 2022-06-06 | $0.00 | $0.00
A13010 | 2022-05-22 | 2022-06-06 | Cost Loading - CASH OUT |  | 4.3.2.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 09] | MJ-MSBL-INT-1.14.4.3.2.20.7 | 11 | Priority 09 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 3059 | 2022-05-22 | 2022-06-06 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.20.10 Priority 10 | 2022-07-20 | 2022-09-18 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 2985 | 2022-07-20 | 2022-09-18 | $0.00 | $0.00
A13020 | 2022-07-20 | 2022-07-27 |  |  | 4.3.2.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Priority 10] | MJ-MSBL-INT-1.14.4.3.2.20.10 | 5 | Priority 10 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2022-07-20 | 2022-07-27 | $0.00 | $0.00
A13030 | 2022-07-27 | 2022-09-18 |  |  | 4.3.2.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 10] | MJ-MSBL-INT-1.14.4.3.2.20.10 | 37 | Priority 10 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2985 | 2022-07-27 | 2022-09-18 | $0.00 | $0.00
A13040 | 2022-09-01 | 2022-09-18 | Cost Loading - CASH OUT |  | 4.3.2.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 10] | MJ-MSBL-INT-1.14.4.3.2.20.10 | 11 | Priority 10 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 2985 | 2022-09-01 | 2022-09-18 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.21 Package (03) | 2022-10-27 | 2024-01-28 | [7 empty] | 320 |  |  | 0 |  | 0% | 320 | 320 | 0% | $31,580.00 | $0.00 | $0.00 | 2639 | 2022-10-27 | 2024-01-28 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.21.3 Priority 11 | 2022-10-27 | 2022-12-26 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 2911 | 2022-10-27 | 2022-12-26 | $0.00 | $0.00
A13050 | 2022-10-27 | 2022-11-03 |  |  | 4.3.2.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Priority 11] | MJ-MSBL-INT-1.14.4.3.2.21.3 | 5 | Priority 11 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2022-10-27 | 2022-11-03 | $0.00 | $0.00
A13060 | 2022-11-03 | 2022-12-26 |  |  | 4.3.2.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 11] | MJ-MSBL-INT-1.14.4.3.2.21.3 | 37 | Priority 11 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2911 | 2022-11-03 | 2022-12-26 | $0.00 | $0.00
A13070 | 2022-12-11 | 2022-12-26 | Cost Loading - CASH OUT |  | 4.3.2.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 11] | MJ-MSBL-INT-1.14.4.3.2.21.3 | 11 | Priority 11 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 2911 | 2022-12-11 | 2022-12-26 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.21.9 Priority 13 | 2023-01-26 | 2023-03-27 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 2852 | 2023-01-26 | 2023-03-27 | $0.00 | $0.00
A13080 | 2023-01-26 | 2023-02-02 |  |  | 4.3.2.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Priority 13] | MJ-MSBL-INT-1.14.4.3.2.21.9 | 5 | Priority 13 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2023-01-26 | 2023-02-02 | $0.00 | $0.00
A13090 | 2023-02-02 | 2023-03-27 |  |  | 4.3.2.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 13] | MJ-MSBL-INT-1.14.4.3.2.21.9 | 37 | Priority 13 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2852 | 2023-02-02 | 2023-03-27 | $0.00 | $0.00
A13100 | 2023-03-12 | 2023-03-27 | Cost Loading - CASH OUT |  | 4.3.2.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 13] | MJ-MSBL-INT-1.14.4.3.2.21.9 | 11 | Priority 13 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 2852 | 2023-03-12 | 2023-03-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.21.11 Priority 14 | 2023-05-10 | 2023-07-12 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 2781 | 2023-05-10 | 2023-07-12 | $0.00 | $0.00
A12050 | 2023-05-10 | 2023-05-17 |  |  | 4.3.2.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Priority 14] | MJ-MSBL-INT-1.14.4.3.2.21.11 | 5 | Priority 14 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2023-05-10 | 2023-05-17 | $0.00 | $0.00
A12060 | 2023-05-17 | 2023-07-12 |  |  | 4.3.2.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 14] | MJ-MSBL-INT-1.14.4.3.2.21.11 | 37 | Priority 14 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2781 | 2023-05-17 | 2023-07-12 | $0.00 | $0.00
A12070 | 2023-06-22 | 2023-07-12 | Cost Loading - CASH OUT |  | 4.3.2.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 14] | MJ-MSBL-INT-1.14.4.3.2.21.11 | 11 | Priority 14 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 2781 | 2023-06-22 | 2023-07-12 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.21.12 Priority 15 | 2023-08-22 | 2023-10-19 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 2710 | 2023-08-22 | 2023-10-19 | $0.00 | $0.00
A13110 | 2023-08-22 | 2023-08-29 |  |  | 4.3.2.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Package 15] | MJ-MSBL-INT-1.14.4.3.2.21.12 | 5 | Priority 15 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2023-08-22 | 2023-08-29 | $0.00 | $0.00
A13120 | 2023-08-29 | 2023-10-19 |  |  | 4.3.2.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 15] | MJ-MSBL-INT-1.14.4.3.2.21.12 | 37 | Priority 15 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2710 | 2023-08-29 | 2023-10-19 | $0.00 | $0.00
A13130 | 2023-10-04 | 2023-10-19 | Cost Loading - CASH OUT |  | 4.3.2.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Package 15] | MJ-MSBL-INT-1.14.4.3.2.21.12 | 11 | Priority 15 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 2710 | 2023-10-04 | 2023-10-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.21.13 Priority 16 | 2023-11-29 | 2024-01-28 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 2639 | 2023-11-29 | 2024-01-28 | $0.00 | $0.00
A13140 | 2023-11-29 | 2023-12-06 |  |  | 4.3.2.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Package 16] | MJ-MSBL-INT-1.14.4.3.2.21.13 | 5 | Priority 16 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2023-11-29 | 2023-12-06 | $0.00 | $0.00
A13150 | 2023-12-06 | 2024-01-28 |  |  | 4.3.2.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 16] | MJ-MSBL-INT-1.14.4.3.2.21.13 | 37 | Priority 16 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2639 | 2023-12-06 | 2024-01-28 | $0.00 | $0.00
A13160 | 2024-01-11 | 2024-01-28 | Cost Loading - CASH OUT |  | 4.3.2.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Package 16] | MJ-MSBL-INT-1.14.4.3.2.21.13 | 11 | Priority 16 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 2639 | 2024-01-11 | 2024-01-28 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.22 Package (04) | 2024-03-07 | 2024-08-21 | [7 empty] | 113 |  |  | 0 |  | 0% | 113 | 113 | 0% | $12,632.00 | $0.00 | $0.00 | 2497 | 2024-03-07 | 2024-08-21 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.22.14 Priority 17 | 2024-03-07 | 2024-05-09 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 2568 | 2024-03-07 | 2024-05-09 | $0.00 | $0.00
A13170 | 2024-03-07 | 2024-03-14 |  |  | 4.3.2.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Package 17] | MJ-MSBL-INT-1.14.4.3.2.22.14 | 5 | Priority 17 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2024-03-07 | 2024-03-14 | $0.00 | $0.00
A13180 | 2024-03-14 | 2024-05-09 |  |  | 4.3.2.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 17] | MJ-MSBL-INT-1.14.4.3.2.22.14 | 37 | Priority 17 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2568 | 2024-03-14 | 2024-05-09 | $0.00 | $0.00
A13190 | 2024-04-24 | 2024-05-09 | Cost Loading - CASH OUT |  | 4.3.2.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Package 17] | MJ-MSBL-INT-1.14.4.3.2.22.14 | 11 | Priority 17 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 2568 | 2024-04-24 | 2024-05-09 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.2.22.15 Priority 18 | 2024-06-24 | 2024-08-21 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 2497 | 2024-06-24 | 2024-08-21 | $0.00 | $0.00
A13200 | 2024-06-24 | 2024-07-01 |  |  | 4.3.2.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Package 18] | MJ-MSBL-INT-1.14.4.3.2.22.15 | 5 | Priority 18 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2024-06-24 | 2024-07-01 | $0.00 | $0.00
A13210 | 2024-07-01 | 2024-08-21 |  |  | 4.3.2.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 18] | MJ-MSBL-INT-1.14.4.3.2.22.15 | 37 | Priority 18 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2497 | 2024-07-01 | 2024-08-21 | $0.00 | $0.00
A13220 | 2024-08-06 | 2024-08-21 | Cost Loading - CASH OUT |  | 4.3.2.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Package 18] | MJ-MSBL-INT-1.14.4.3.2.22.15 | 11 | Priority 18 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 2497 | 2024-08-06 | 2024-08-21 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.1 Other Beneficiaries' Units | 2024-10-02 | 2025-10-06 | [7 empty] | 255 |  |  | 0 |  | 0% | 255 | 255 | 0% | $25,264.00 | $0.00 | $0.00 | 2213 | 2024-10-02 | 2025-10-06 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.1.2 Packages (01,02,03,04) | 2024-10-02 | 2025-10-06 | [7 empty] | 255 |  |  | 0 |  | 0% | 255 | 255 | 0% | $25,264.00 | $0.00 | $0.00 | 2213 | 2024-10-02 | 2025-10-06 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.1.2.16 Priority 03 | 2024-10-02 | 2024-12-01 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 2426 | 2024-10-02 | 2024-12-01 | $0.00 | $0.00
A13230 | 2024-10-02 | 2024-10-09 |  |  | 4.3.1.2.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Package 03] | MJ-MSBL-INT-1.14.4.3.1.2.16 | 5 | Priority 03 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2024-10-02 | 2024-10-09 | $0.00 | $0.00
A13240 | 2024-10-09 | 2024-12-01 |  |  | 4.3.1.2.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 03] | MJ-MSBL-INT-1.14.4.3.1.2.16 | 37 | Priority 03 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2426 | 2024-10-09 | 2024-12-01 | $0.00 | $0.00
A13250 | 2024-11-14 | 2024-12-01 | Cost Loading - CASH OUT |  | 4.3.1.2.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Package 03] | MJ-MSBL-INT-1.14.4.3.1.2.16 | 11 | Priority 03 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 2426 | 2024-11-14 | 2024-12-01 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.1.2.17 Priority 06 | 2025-01-09 | 2025-03-10 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 2355 | 2025-01-09 | 2025-03-10 | $0.00 | $0.00
A12100 | 2025-01-09 | 2025-01-16 |  |  | 4.3.1.2.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Package 06] | MJ-MSBL-INT-1.14.4.3.1.2.17 | 5 | Priority 06 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2025-01-09 | 2025-01-16 | $0.00 | $0.00
A12110 | 2025-01-16 | 2025-03-10 |  |  | 4.3.1.2.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 06] | MJ-MSBL-INT-1.14.4.3.1.2.17 | 37 | Priority 06 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2355 | 2025-01-16 | 2025-03-10 | $0.00 | $0.00
A12120 | 2025-02-23 | 2025-03-10 | Cost Loading - CASH OUT |  | 4.3.1.2.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Package 06] | MJ-MSBL-INT-1.14.4.3.1.2.17 | 11 | Priority 06 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 2355 | 2025-02-23 | 2025-03-10 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.1.2.18 Priority 12 | 2025-04-24 | 2025-06-26 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 2284 | 2025-04-24 | 2025-06-26 | $0.00 | $0.00
A13260 | 2025-04-24 | 2025-05-01 |  |  | 4.3.1.2.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Package 12] | MJ-MSBL-INT-1.14.4.3.1.2.18 | 5 | Priority 12 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2025-04-24 | 2025-05-01 | $0.00 | $0.00
A13270 | 2025-05-01 | 2025-06-26 |  |  | 4.3.1.2.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 12] | MJ-MSBL-INT-1.14.4.3.1.2.18 | 37 | Priority 12 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2284 | 2025-05-01 | 2025-06-26 | $0.00 | $0.00
A13280 | 2025-06-11 | 2025-06-26 | Cost Loading - CASH OUT |  | 4.3.1.2.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Package 12] | MJ-MSBL-INT-1.14.4.3.1.2.18 | 11 | Priority 12 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 2284 | 2025-06-11 | 2025-06-26 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.3.1.2.1 Priority 19 | 2025-08-06 | 2025-10-06 | [7 empty] | 42 |  |  | 0 |  | 0% | 42 | 42 | 0% | $6,316.00 | $0.00 | $0.00 | 2213 | 2025-08-06 | 2025-10-06 | $0.00 | $0.00
A13290 | 2025-08-06 | 2025-08-13 |  |  | 4.3.1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Contractors Invitations [Package 19] | MJ-MSBL-INT-1.14.4.3.1.2.1 | 5 | Priority 19 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2025-08-06 | 2025-08-13 | $0.00 | $0.00
A13300 | 2025-08-13 | 2025-10-06 |  |  | 4.3.1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 19] | MJ-MSBL-INT-1.14.4.3.1.2.1 | 37 | Priority 19 | Fixed Duration and Units/Time | 0 | 0% | 0% | 37 | 37 | 0% | $0.00 | $0.00 | $0.00 | 2213 | 2025-08-13 | 2025-10-06 | $0.00 | $0.00
A13310 | 2025-09-18 | 2025-10-06 | Cost Loading - CASH OUT |  | 4.3.1.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Package 19] | MJ-MSBL-INT-1.14.4.3.1.2.1 | 11 | Priority 19 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $6,316.00 | $0.00 | $0.00 | 2213 | 2025-09-18 | 2025-10-06 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11 Superstructure Work | 2018-12-16 | 2027-07-05 | [7 empty] | 2670 |  |  | 25 |  | 0% | 2670 | 2444 | 0% | $80,009.00 | $0.00 | $0.00 | 2672 | 16-Oct-18 A | 2027-07-05 | $0.00 | $0.00
A9710 | 2020-07-12 | 2020-08-04 |  |  | 4.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Prequalifications | MJ-MSBL-INT-1.14.4.11 | 15 | Superstructure Work | Fixed Duration & Units | 0 | 0% | 0% | 15 | 15 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2020-07-12 | 2020-08-04 | $0.00 | $0.00
T2000 | 2018-12-16 | 2018-12-23 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 4.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | إعداد خطة إدارة المشروع والتنفيذ | MJ-MSBL-INT-1.14.4.11 | 6 | Superstructure Work | Fixed Duration & Units | 9 | 100% | 100% | 6 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 01-Nov-18 A | 14-Nov-18 A | $0.00 | $0.00
T2010 | 2018-12-16 | 2018-12-31 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 4.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare Feasibility & Ecnomical Stuady Approved by Certified Consultant | MJ-MSBL-INT-1.14.4.11 | 12 | Superstructure Work | Fixed Duration & Units | 11 | 100% | 100% | 12 | 0 | 100% | $0.00 | $0.00 | $0.00 |  | 16-Oct-18 A | 31-Oct-18 A | $0.00 | $0.00
T2020 | 2019-09-15 | 2019-09-29 | Cost Loading - CASH IN, Cost Loading - CASH OUT |  | 4.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | إعداد مستندات الطرح لإختيار إستشاري الإشراف على التنفيذ | MJ-MSBL-INT-1.14.4.11 | 10 | Superstructure Work | Fixed Duration & Units | 0 | 0% | 0% | 10 | 10 | 0% | $0.00 | $0.00 | $0.00 | 781 | 2019-09-15 | 2019-09-29 | $0.00 | $0.00
T2030 | 2019-09-15 | 2019-10-03 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 4.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | إعداد التقييم العقاري لأرض المشروع وإعتماده | MJ-MSBL-INT-1.14.4.11 | 14 | Superstructure Work | Fixed Duration & Units | 0 | 0% | 0% | 14 | 14 | 0% | $0.00 | $0.00 | $0.00 | 4170 | 2019-09-15 | 2019-10-03 | $0.00 | $0.00
T2050 | 2019-10-24 | 2019-10-30 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 4.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | إعداد ملف وثائق المشروع | MJ-MSBL-INT-1.14.4.11 | 4 | Superstructure Work | Fixed Duration & Units | 0 | 0% | 0% | 4 | 4 | 0% | $0.00 | $0.00 | $0.00 | 4138 | 2019-10-24 | 2019-10-30 | $0.00 | $0.00
T2060 | 2019-10-07 | 2019-10-30 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 4.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | تأهيل وتعميد المقاول للتنفيذ | MJ-MSBL-INT-1.14.4.11 | 18 | Superstructure Work | Fixed Duration & Units | 0 | 0% | 0% | 18 | 18 | 0% | $0.00 | $0.00 | $0.00 | 776 | 2019-10-07 | 2019-10-30 | $0.00 | $0.00
T2070 | 2020-10-17 | 2020-10-27 |  |  | 4.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare Maintenance Plane During DLP | MJ-MSBL-INT-1.14.4.11 | 10 | Superstructure Work | Fixed Duration & Units | 0 | 0% | 0% | 10 | 10 | 0% | $0.00 | $0.00 | $0.00 | 2759 | 2020-10-17 | 2020-10-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2 MOH Beneficiaries' Units | 2020-08-05 | 2025-12-15 | [7 empty] | 1363 |  |  | 0 |  | 0% | 1363 | 1363 | 0% | $63,165.00 | $0.00 | $0.00 | 132 | 2020-08-05 | 2025-12-15 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.19 Package (01] | 2020-08-05 | 2021-08-02 | [7 empty] | 252 |  |  | 0 |  | 0% | 252 | 252 | 0% | $12,633.00 | $0.00 | $0.00 | 462 | 2020-08-05 | 2021-08-02 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.19.1 Priority 01 | 2020-08-05 | 2020-10-15 | [7 empty] | 51 |  |  | 0 |  | 0% | 51 | 51 | 0% | $4,211.00 | $0.00 | $0.00 | 532 | 2020-08-05 | 2020-10-15 | $0.00 | $0.00
A11790 | 2020-08-05 | 2020-08-11 |  |  | 4.11.2.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 01] | MJ-MSBL-INT-1.14.4.11.2.19.1 | 5 | Priority 01 | Fixed Duration & Units | 0 | 0% | 0% | 5 | 5 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2020-08-05 | 2020-08-11 | $0.00 | $0.00
A13470 | 2020-10-01 | 2020-10-15 | Cost Loading - CASH OUT |  | 4.11.2.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 01] | MJ-MSBL-INT-1.14.4.11.2.19.1 | 11 | Priority 01 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 532 | 2020-10-01 | 2020-10-15 | $0.00 | $0.00
A9720 | 2020-08-05 | 2020-10-15 |  |  | 4.11.2.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 01] | MJ-MSBL-INT-1.14.4.11.2.19.1 | 51 | Priority 01 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 529 | 2020-08-05 | 2020-10-15 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.19.2 Priority 02 | 2020-11-12 | 2021-03-09 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 494 | 2020-11-12 | 2021-03-09 | $0.00 | $0.00
A11630 | 2020-11-12 | 2020-12-28 |  |  | 4.11.2.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 02] | MJ-MSBL-INT-1.14.4.11.2.19.2 | 33 | Priority 02 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2020-11-12 | 2020-12-28 | $0.00 | $0.00
A11640 | 2020-12-29 | 2021-03-09 |  |  | 4.11.2.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 02] | MJ-MSBL-INT-1.14.4.11.2.19.2 | 51 | Priority 02 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 494 | 2020-12-29 | 2021-03-09 | $0.00 | $0.00
A13480 | 2021-02-23 | 2021-03-09 | Cost Loading - CASH OUT |  | 4.11.2.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 02] | MJ-MSBL-INT-1.14.4.11.2.19.2 | 11 | Priority 02 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 494 | 2021-02-23 | 2021-03-09 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.19.4 Priority 04 | 2021-03-30 | 2021-08-02 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 462 | 2021-03-30 | 2021-08-02 | $0.00 | $0.00
A11750 | 2021-03-30 | 2021-05-17 |  |  | 4.11.2.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 04] | MJ-MSBL-INT-1.14.4.11.2.19.4 | 33 | Priority 04 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2021-03-30 | 2021-05-17 | $0.00 | $0.00
A11760 | 2021-05-18 | 2021-08-02 |  |  | 4.11.2.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 04] | MJ-MSBL-INT-1.14.4.11.2.19.4 | 51 | Priority 04 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 462 | 2021-05-18 | 2021-08-02 | $0.00 | $0.00
A13490 | 2021-07-13 | 2021-08-02 | Cost Loading - CASH OUT |  | 4.11.2.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 04] | MJ-MSBL-INT-1.14.4.11.2.19.4 | 11 | Priority 04 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 462 | 2021-07-13 | 2021-08-02 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.20 Package (02) | 2021-08-23 | 2023-07-09 | [7 empty] | 476 |  |  | 0 |  | 0% | 476 | 476 | 0% | $21,055.00 | $0.00 | $0.00 | 298 | 2021-08-23 | 2023-07-09 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.20.5 Priority 05 | 2021-08-23 | 2021-12-19 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 429 | 2021-08-23 | 2021-12-19 | $0.00 | $0.00
A11510 | 2021-08-23 | 2021-10-07 |  |  | 4.11.2.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 05] | MJ-MSBL-INT-1.14.4.11.2.20.5 | 33 | Priority 05 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2021-08-23 | 2021-10-07 | $0.00 | $0.00
A11520 | 2021-10-10 | 2021-12-19 |  |  | 4.11.2.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 05] | MJ-MSBL-INT-1.14.4.11.2.20.5 | 51 | Priority 05 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 429 | 2021-10-10 | 2021-12-19 | $0.00 | $0.00
A13500 | 2021-12-05 | 2021-12-19 | Cost Loading - CASH OUT |  | 4.11.2.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 05] | MJ-MSBL-INT-1.14.4.11.2.20.5 | 11 | Priority 05 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 429 | 2021-12-05 | 2021-12-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.20.6 Priority 07 | 2022-01-09 | 2022-05-10 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 397 | 2022-01-09 | 2022-05-10 | $0.00 | $0.00
A13510 | 2022-04-20 | 2022-05-10 | Cost Loading - CASH OUT |  | 4.11.2.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 017] | MJ-MSBL-INT-1.14.4.11.2.20.6 | 11 | Priority 07 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 397 | 2022-04-20 | 2022-05-10 | $0.00 | $0.00
A9930 | 2022-01-09 | 2022-02-22 |  |  | 4.11.2.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 07] | MJ-MSBL-INT-1.14.4.11.2.20.6 | 33 | Priority 07 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2022-01-09 | 2022-02-22 | $0.00 | $0.00
A9940 | 2022-02-23 | 2022-05-10 |  |  | 4.11.2.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 07] | MJ-MSBL-INT-1.14.4.11.2.20.6 | 51 | Priority 07 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 397 | 2022-02-23 | 2022-05-10 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.20.8 Priority 08 | 2022-05-31 | 2022-09-28 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 364 | 2022-05-31 | 2022-09-28 | $0.00 | $0.00
A10170 | 2022-05-31 | 2022-07-19 |  |  | 4.11.2.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 08] | MJ-MSBL-INT-1.14.4.11.2.20.8 | 33 | Priority 08 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2022-05-31 | 2022-07-19 | $0.00 | $0.00
A10180 | 2022-07-20 | 2022-09-28 |  |  | 4.11.2.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 08] | MJ-MSBL-INT-1.14.4.11.2.20.8 | 51 | Priority 08 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 364 | 2022-07-20 | 2022-09-28 | $0.00 | $0.00
A13520 | 2022-09-14 | 2022-09-28 | Cost Loading - CASH OUT |  | 4.11.2.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 08] | MJ-MSBL-INT-1.14.4.11.2.20.8 | 11 | Priority 08 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 364 | 2022-09-14 | 2022-09-28 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.20.7 Priority 09 | 2022-10-19 | 2023-02-13 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 331 | 2022-10-19 | 2023-02-13 | $0.00 | $0.00
A10290 | 2022-10-19 | 2022-12-04 |  |  | 4.11.2.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 09] | MJ-MSBL-INT-1.14.4.11.2.20.7 | 33 | Priority 09 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2022-10-19 | 2022-12-04 | $0.00 | $0.00
A10300 | 2022-12-05 | 2023-02-13 |  |  | 4.11.2.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 09] | MJ-MSBL-INT-1.14.4.11.2.20.7 | 51 | Priority 09 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 331 | 2022-12-05 | 2023-02-13 | $0.00 | $0.00
A13530 | 2023-01-30 | 2023-02-13 | Cost Loading - CASH OUT |  | 4.11.2.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 09] | MJ-MSBL-INT-1.14.4.11.2.20.7 | 11 | Priority 09 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 331 | 2023-01-30 | 2023-02-13 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.20.10 Priority 10 | 2023-03-06 | 2023-07-09 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 298 | 2023-03-06 | 2023-07-09 | $0.00 | $0.00
A10410 | 2023-03-06 | 2023-04-19 |  |  | 4.11.2.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 10] | MJ-MSBL-INT-1.14.4.11.2.20.10 | 33 | Priority 10 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2023-03-06 | 2023-04-19 | $0.00 | $0.00
A10420 | 2023-04-20 | 2023-07-09 |  |  | 4.11.2.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 10] | MJ-MSBL-INT-1.14.4.11.2.20.10 | 51 | Priority 10 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 298 | 2023-04-20 | 2023-07-09 | $0.00 | $0.00
A13560 | 2023-06-20 | 2023-07-09 | Cost Loading - CASH OUT |  | 4.11.2.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 10] | MJ-MSBL-INT-1.14.4.11.2.20.10 | 11 | Priority 10 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 298 | 2023-06-20 | 2023-07-09 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.21 Package (03] | 2023-07-30 | 2025-03-04 | [7 empty] | 411 |  |  | 0 |  | 0% | 411 | 411 | 0% | $21,055.00 | $0.00 | $0.00 | 198 | 2023-07-30 | 2025-03-04 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.21.3 Priority 11 | 2023-07-30 | 2023-11-22 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 265 | 2023-07-30 | 2023-11-22 | $0.00 | $0.00
A10050 | 2023-07-30 | 2023-09-12 |  |  | 4.11.2.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 11] | MJ-MSBL-INT-1.14.4.11.2.21.3 | 33 | Priority 11 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2023-07-30 | 2023-09-12 | $0.00 | $0.00
A10060 | 2023-09-13 | 2023-11-22 |  |  | 4.11.2.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 11] | MJ-MSBL-INT-1.14.4.11.2.21.3 | 51 | Priority 11 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 265 | 2023-09-13 | 2023-11-22 | $0.00 | $0.00
A13540 | 2023-11-08 | 2023-11-22 | Cost Loading - CASH OUT |  | 4.11.2.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 11] | MJ-MSBL-INT-1.14.4.11.2.21.3 | 11 | Priority 11 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 265 | 2023-11-08 | 2023-11-22 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.21.9 Priority 13 | 2023-12-13 | 2024-04-08 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 232 | 2023-12-13 | 2024-04-08 | $0.00 | $0.00
A13550 | 2024-03-25 | 2024-04-08 | Cost Loading - CASH OUT |  | 4.11.2.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 13] | MJ-MSBL-INT-1.14.4.11.2.21.9 | 11 | Priority 13 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 232 | 2024-03-25 | 2024-04-08 | $0.00 | $0.00
A9830 | 2023-12-13 | 2024-01-28 |  |  | 4.11.2.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 13] | MJ-MSBL-INT-1.14.4.11.2.21.9 | 33 | Priority 13 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2023-12-13 | 2024-01-28 | $0.00 | $0.00
A9840 | 2024-01-29 | 2024-04-08 |  |  | 4.11.2.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 13] | MJ-MSBL-INT-1.14.4.11.2.21.9 | 51 | Priority 13 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 232 | 2024-01-29 | 2024-04-08 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.21.11 Priority 14 | 2024-01-29 | 2024-05-28 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 264 | 2024-01-29 | 2024-05-28 | $0.00 | $0.00
A10530 | 2024-01-29 | 2024-03-13 |  |  | 4.11.2.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 14] | MJ-MSBL-INT-1.14.4.11.2.21.11 | 33 | Priority 14 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2024-01-29 | 2024-03-13 | $0.00 | $0.00
A10540 | 2024-03-14 | 2024-05-28 |  |  | 4.11.2.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 14] | MJ-MSBL-INT-1.14.4.11.2.21.11 | 51 | Priority 14 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 264 | 2024-03-14 | 2024-05-28 | $0.00 | $0.00
A13580 | 2024-05-14 | 2024-05-28 | Cost Loading - CASH OUT |  | 4.11.2.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 14] | MJ-MSBL-INT-1.14.4.11.2.21.11 | 11 | Priority 14 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 264 | 2024-05-14 | 2024-05-28 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.21.12 Priority 15 | 2024-06-23 | 2024-10-17 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 231 | 2024-06-23 | 2024-10-17 | $0.00 | $0.00
A10650 | 2024-06-23 | 2024-08-06 |  |  | 4.11.2.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 15] | MJ-MSBL-INT-1.14.4.11.2.21.12 | 33 | Priority 15 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2024-06-23 | 2024-08-06 | $0.00 | $0.00
A10660 | 2024-08-07 | 2024-10-17 |  |  | 4.11.2.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 15] | MJ-MSBL-INT-1.14.4.11.2.21.12 | 51 | Priority 15 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 231 | 2024-08-07 | 2024-10-17 | $0.00 | $0.00
A13570 | 2024-10-03 | 2024-10-17 | Cost Loading - CASH OUT |  | 4.11.2.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 15] | MJ-MSBL-INT-1.14.4.11.2.21.12 | 11 | Priority 15 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 231 | 2024-10-03 | 2024-10-17 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.21.13 Priority 16 | 2024-11-07 | 2025-03-04 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 198 | 2024-11-07 | 2025-03-04 | $0.00 | $0.00
A10770 | 2024-11-07 | 2024-12-23 |  |  | 4.11.2.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 16] | MJ-MSBL-INT-1.14.4.11.2.21.13 | 33 | Priority 16 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2024-11-07 | 2024-12-23 | $0.00 | $0.00
A10780 | 2024-12-24 | 2025-03-04 |  |  | 4.11.2.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 16] | MJ-MSBL-INT-1.14.4.11.2.21.13 | 51 | Priority 16 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 198 | 2024-12-24 | 2025-03-04 | $0.00 | $0.00
A13590 | 2025-02-18 | 2025-03-04 | Cost Loading - CASH OUT |  | 4.11.2.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 16] | MJ-MSBL-INT-1.14.4.11.2.21.13 | 11 | Priority 16 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 198 | 2025-02-18 | 2025-03-04 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.22 Package (04) | 2025-03-25 | 2025-12-15 | [7 empty] | 182 |  |  | 0 |  | 0% | 182 | 182 | 0% | $8,422.00 | $0.00 | $0.00 | 132 | 2025-03-25 | 2025-12-15 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.22.14 Priority 17 | 2025-03-25 | 2025-07-29 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 165 | 2025-03-25 | 2025-07-29 | $0.00 | $0.00
A10890 | 2025-03-25 | 2025-05-14 |  |  | 4.11.2.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 17] | MJ-MSBL-INT-1.14.4.11.2.22.14 | 33 | Priority 17 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2025-03-25 | 2025-05-14 | $0.00 | $0.00
A10900 | 2025-05-15 | 2025-07-29 |  |  | 4.11.2.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 17] | MJ-MSBL-INT-1.14.4.11.2.22.14 | 51 | Priority 17 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 165 | 2025-05-15 | 2025-07-29 | $0.00 | $0.00
A13600 | 2025-07-15 | 2025-07-29 | Cost Loading - CASH OUT |  | 4.11.2.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 17] | MJ-MSBL-INT-1.14.4.11.2.22.14 | 11 | Priority 17 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 165 | 2025-07-15 | 2025-07-29 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.2.22.15 Priority 18 | 2025-08-19 | 2025-12-15 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 132 | 2025-08-19 | 2025-12-15 | $0.00 | $0.00
A11010 | 2025-08-19 | 2025-10-05 |  |  | 4.11.2.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 18] | MJ-MSBL-INT-1.14.4.11.2.22.15 | 33 | Priority 18 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2025-08-19 | 2025-10-05 | $0.00 | $0.00
A11020 | 2025-10-06 | 2025-12-15 |  |  | 4.11.2.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 18] | MJ-MSBL-INT-1.14.4.11.2.22.15 | 51 | Priority 18 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 132 | 2025-10-06 | 2025-12-15 | $0.00 | $0.00
A13610 | 2025-12-01 | 2025-12-15 | Cost Loading - CASH OUT |  | 4.11.2.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 18] | MJ-MSBL-INT-1.14.4.11.2.22.15 | 11 | Priority 18 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 132 | 2025-12-01 | 2025-12-15 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.3 Other Beneficiaries' Units | 2026-01-05 | 2027-07-05 | [7 empty] | 378 |  |  | 0 |  | 0% | 378 | 378 | 0% | $16,844.00 | $0.00 | $0.00 | 1 | 2026-01-05 | 2027-07-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.3.1 Packages (01,02,03,04) | 2026-01-05 | 2027-07-05 | [7 empty] | 378 |  |  | 0 |  | 0% | 378 | 378 | 0% | $16,844.00 | $0.00 | $0.00 | 1 | 2026-01-05 | 2027-07-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.3.1.16 Priority 03 | 2026-01-05 | 2026-05-05 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 99 | 2026-01-05 | 2026-05-05 | $0.00 | $0.00
A11130 | 2026-01-05 | 2026-02-18 |  |  | 4.11.3.1.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 03] | MJ-MSBL-INT-1.14.4.11.3.1.16 | 33 | Priority 03 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2026-01-05 | 2026-02-18 | $0.00 | $0.00
A11140 | 2026-02-19 | 2026-05-05 |  |  | 4.11.3.1.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 03] | MJ-MSBL-INT-1.14.4.11.3.1.16 | 51 | Priority 03 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 99 | 2026-02-19 | 2026-05-05 | $0.00 | $0.00
A13640 | 2026-04-21 | 2026-05-05 | Cost Loading - CASH OUT |  | 4.11.3.1.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 03] | MJ-MSBL-INT-1.14.4.11.3.1.16 | 11 | Priority 03 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 99 | 2026-04-21 | 2026-05-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.3.1.17 Priority 06 | 2026-05-31 | 2026-09-24 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 66 | 2026-05-31 | 2026-09-24 | $0.00 | $0.00
A11250 | 2026-05-31 | 2026-07-14 |  |  | 4.11.3.1.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 06] | MJ-MSBL-INT-1.14.4.11.3.1.17 | 33 | Priority 06 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2026-05-31 | 2026-07-14 | $0.00 | $0.00
A11260 | 2026-07-15 | 2026-09-24 |  |  | 4.11.3.1.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 06] | MJ-MSBL-INT-1.14.4.11.3.1.17 | 51 | Priority 06 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 66 | 2026-07-15 | 2026-09-24 | $0.00 | $0.00
A13650 | 2026-09-09 | 2026-09-24 | Cost Loading - CASH OUT |  | 4.11.3.1.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 06] | MJ-MSBL-INT-1.14.4.11.3.1.17 | 11 | Priority 06 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 66 | 2026-09-09 | 2026-09-24 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.3.1.18 Priority 12 | 2026-10-15 | 2027-02-09 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 34 | 2026-10-15 | 2027-02-09 | $0.00 | $0.00
A11370 | 2026-10-15 | 2026-11-30 |  |  | 4.11.3.1.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 12] | MJ-MSBL-INT-1.14.4.11.3.1.18 | 33 | Priority 12 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2026-10-15 | 2026-11-30 | $0.00 | $0.00
A11380 | 2026-12-01 | 2027-02-09 |  |  | 4.11.3.1.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 12] | MJ-MSBL-INT-1.14.4.11.3.1.18 | 51 | Priority 12 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 34 | 2026-12-01 | 2027-02-09 | $0.00 | $0.00
A13620 | 2027-01-26 | 2027-02-09 | Cost Loading - CASH OUT |  | 4.11.3.1.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 12] | MJ-MSBL-INT-1.14.4.11.3.1.18 | 11 | Priority 12 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 34 | 2027-01-26 | 2027-02-09 | $0.00 | $0.00
MJ-MSBL-INT-1.14.4.11.3.1.1 Priority 19 | 2027-03-02 | 2027-07-05 | [7 empty] | 84 |  |  | 0 |  | 0% | 84 | 84 | 0% | $4,211.00 | $0.00 | $0.00 | 1 | 2027-03-02 | 2027-07-05 | $0.00 | $0.00
A12760 | 2027-03-02 | 2027-04-20 |  |  | 4.11.3.1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Contractors Invitations [Priority 19] | MJ-MSBL-INT-1.14.4.11.3.1.1 | 33 | Priority 19 | Fixed Duration & Units | 0 | 0% | 0% | 33 | 33 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2027-03-02 | 2027-04-20 | $0.00 | $0.00
A12770 | 2027-04-21 | 2027-07-05 |  |  | 4.11.3.1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Tenderers preparation/submission of proposals / negotiation & Awarding [Priority 19] | MJ-MSBL-INT-1.14.4.11.3.1.1 | 51 | Priority 19 | Fixed Duration and Units/Time | 0 | 0% | 0% | 51 | 51 | 0% | $0.00 | $0.00 | $0.00 | 1 | 2027-04-21 | 2027-07-05 | $0.00 | $0.00
A13630 | 2027-06-21 | 2027-07-05 | Cost Loading - CASH OUT |  | 4.11.3.1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare / Review / Approve Construction Documents [Priority 19] | MJ-MSBL-INT-1.14.4.11.3.1.1 | 11 | Priority 19 | Fixed Duration and Units/Time | 0 | 0% | 0% | 11 | 11 | 0% | $4,211.00 | $0.00 | $0.00 | 1 | 2027-06-21 | 2027-07-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5 Construction Phase | 2019-09-15 | 1930-02-21 | [7 empty] | 3269 |  |  | 0 |  | 0% | 3269 | 3269 | 0% | $7,271,680,320.61 | $0.00 | $0.00 | 2032 | 2019-09-15 | 1930-02-21 | $0.00 | $0.00
L7120 | 2019-09-15 | 2028-01-27 | Cost Loading - CASH OUT |  | 5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Infrastructure Construction Supervision | MJ-MSBL-INT-1.14.5 | 2548 | Construction Phase | Fixed Duration & Units | 0 | 0% | 0% | 2548 | 2548 | 0% | $48,671,755.11 | $0.00 | $0.00 | 2654 | 2019-09-15 | 2028-01-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.9 Main Infrastructure Networks, Roads & Landscape | 2019-09-15 | 2025-02-24 | [7 empty] | 1661 |  |  | 0 |  | 0% | 1661 | 1661 | 0% | $777,794,301.00 | $0.00 | $0.00 | 3336 | 2019-09-15 | 2025-02-24 | $0.00 | $0.00
L7000 | 2019-09-15 | 2025-02-24 |  |  | 5.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Main Infrastructure Networks, Roads & Landscape | MJ-MSBL-INT-1.14.5.9 | 1661 | Main Infrastructure Networks, Roads & Landscape | Fixed Duration & Units | 0 | 0% | 0% | 1661 | 1661 | 0% | $0.00 | $0.00 | $0.00 | 3041 | 2019-09-15 | 2025-02-24 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.9.3 Site Offices & Security Center | 2019-09-15 | 2020-03-08 | [7 empty] | 150 |  |  | 0 |  | 0% | 150 | 150 | 0% | $4,595,970.00 | $0.00 | $0.00 | 4701 | 2019-09-15 | 2020-03-08 | $0.00 | $0.00
A12340 | 2019-09-15 | 2020-03-08 | Cost Loading - CASH OUT |  | 5.9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Site Offices & Security Center | MJ-MSBL-INT-1.14.5.9.3 | 150 | Site Offices & Security Center | Fixed Duration & Units | 0 | 0% | 0% | 150 | 150 | 0% | $4,595,970.00 | $0.00 | $0.00 | 4701 | 2019-09-15 | 2020-03-08 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.9.1 Rough Grading | 2019-09-15 | 2020-07-07 | [7 empty] | 250 |  |  | 0 |  | 0% | 250 | 250 | 0% | $29,290,785.00 | $0.00 | $0.00 | 4115 | 2019-09-15 | 2020-07-07 | $0.00 | $0.00
A12260 | 2019-09-15 | 2020-07-07 | Cost Loading - CASH OUT |  | 5.9.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Rough Grading | MJ-MSBL-INT-1.14.5.9.1 | 250 | Rough Grading | Fixed Duration & Units | 0 | 0% | 0% | 250 | 250 | 0% | $29,290,785.00 | $0.00 | $0.00 | 4115 | 2019-09-15 | 2020-07-07 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.9.2 Main Infrastructure Networks, Roads & Culverts | 2020-04-02 | 2023-08-26 | [7 empty] | 1030 |  |  | 0 |  | 0% | 1030 | 1030 | 0% | $285,874,056.00 | $0.00 | $0.00 | 3529 | 2020-04-02 | 2023-08-26 | $0.00 | $0.00
A6990 | 2020-04-02 | 2020-06-21 |  |  | 5.9.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Mobilization | MJ-MSBL-INT-1.14.5.9.2 | 65 | Main Infrastructure Networks, Roads & Culverts | Fixed Duration & Units | 0 | 0% | 0% | 65 | 65 | 0% | $0.00 | $0.00 | $0.00 | 3529 | 2020-04-02 | 2020-06-21 | $0.00 | $0.00
T7010 | 2020-04-20 | 2022-12-08 | Cost Loading - CASH OUT |  | 5.9.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Main Networks | MJ-MSBL-INT-1.14.5.9.2 | 800 | Main Infrastructure Networks, Roads & Culverts | Fixed Duration & Units | 0 | 0% | 0% | 800 | 800 | 0% | $209,903,472.00 | $0.00 | $0.00 | 3529 | 2020-04-20 | 2022-12-08 | $0.00 | $0.00
T7850 | 2020-11-26 | 2023-08-26 | Cost Loading - CASH OUT |  | 5.9.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Roads & Cluverts | MJ-MSBL-INT-1.14.5.9.2 | 835 | Main Infrastructure Networks, Roads & Culverts | Fixed Duration & Units | 0 | 0% | 0% | 835 | 835 | 0% | $75,970,584.00 | $0.00 | $0.00 | 3529 | 2020-11-26 | 2023-08-26 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.9.4 Concrete Structures (Northern Entrances) | 2020-07-01 | 2022-12-31 | [7 empty] | 761 |  |  | 0 |  | 0% | 761 | 761 | 0% | $51,750,000.00 | $0.00 | $0.00 | 3760 | 2020-07-01 | 2022-12-31 | $0.00 | $0.00
A12700 | 2020-07-01 | 2022-12-31 | Cost Loading - CASH OUT |  | 5.9.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Concrete Structures (N. Entrances) | MJ-MSBL-INT-1.14.5.9.4 | 761 | Concrete Structures (Northern Entrances) | Fixed Duration & Units | 0 | 0% | 0% | 761 | 761 | 0% | $51,750,000.00 | $0.00 | $0.00 | 3760 | 2020-07-01 | 2022-12-31 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.9.5 HV Substations | 2021-05-20 | 2024-08-22 | [7 empty] | 990 |  |  | 0 |  | 0% | 990 | 990 | 0% | $134,100,000.00 | $0.00 | $0.00 | 3494 | 2021-05-20 | 2024-08-22 | $0.00 | $0.00
A12710 | 2021-05-20 | 2024-08-22 | Cost Loading - CASH OUT |  | 5.9.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for HV S/S | MJ-MSBL-INT-1.14.5.9.5 | 990 | HV Substations | Fixed Duration & Units | 0 | 0% | 0% | 990 | 990 | 0% | $134,100,000.00 | $0.00 | $0.00 | 3494 | 2021-05-20 | 2024-08-22 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.9.6 Sewer Water Treatment Plant [STP] | 2021-05-20 | 2024-01-28 | [7 empty] | 820 |  |  | 0 |  | 0% | 820 | 820 | 0% | $9,000,000.00 | $0.00 | $0.00 | 3428 | 2021-05-20 | 2024-01-28 | $0.00 | $0.00
A12720 | 2021-05-20 | 2024-01-28 | Cost Loading - CASH OUT |  | 5.9.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for STP | MJ-MSBL-INT-1.14.5.9.6 | 820 | Sewer Water Treatment Plant [STP] | Fixed Duration & Units | 0 | 0% | 0% | 820 | 820 | 0% | $9,000,000.00 | $0.00 | $0.00 | 3428 | 2021-05-20 | 2024-01-28 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.9.7 Open Channel [Storm Water Drainage] | 2021-05-20 | 2024-08-22 | [7 empty] | 990 |  |  | 0 |  | 0% | 990 | 990 | 0% | $153,810,000.00 | $0.00 | $0.00 | 3262 | 2021-05-20 | 2024-08-22 | $0.00 | $0.00
A12730 | 2021-05-20 | 2024-08-22 | Cost Loading - CASH OUT |  | 5.9.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for O.C. | MJ-MSBL-INT-1.14.5.9.7 | 990 | Open Channel [Storm Water Drainage] | Fixed Duration & Units | 0 | 0% | 0% | 990 | 990 | 0% | $153,810,000.00 | $0.00 | $0.00 | 3262 | 2021-05-20 | 2024-08-22 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.9.9 Road Finishes, Street Lighting Poles & Traffic Signals | 2021-11-25 | 2024-08-25 | [7 empty] | 835 |  |  | 0 |  | 0% | 835 | 835 | 0% | $70,673,490.00 | $0.00 | $0.00 | 3260 | 2021-11-25 | 2024-08-25 | $0.00 | $0.00
A12740 | 2021-11-25 | 2024-08-25 | Cost Loading - CASH OUT |  | 5.9.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for RD&St.L. | MJ-MSBL-INT-1.14.5.9.9 | 835 | Road Finishes, Street Lighting Poles & Traffic Signals | Fixed Duration & Units | 0 | 0% | 0% | 835 | 835 | 0% | $70,673,490.00 | $0.00 | $0.00 | 3260 | 2021-11-25 | 2024-08-25 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.9.10 Landscape Work | 2022-05-25 | 2025-02-24 | [7 empty] | 840 |  |  | 0 |  | 0% | 840 | 840 | 0% | $38,700,000.00 | $0.00 | $0.00 | 3041 | 2022-05-25 | 2025-02-24 | $0.00 | $0.00
A12320 | 2022-05-25 | 2025-02-24 | Cost Loading - CASH OUT |  | 5.9.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Landscape [Phase I] | MJ-MSBL-INT-1.14.5.9.10 | 840 | Landscape Work | Fixed Duration & Units | 0 | 0% | 0% | 840 | 840 | 0% | $38,700,000.00 | $0.00 | $0.00 | 3041 | 2022-05-25 | 2025-02-24 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3 Secondary Infrastructure Networks | 2020-10-01 | 2028-01-13 | [7 empty] | 2280 |  |  | 0 |  | 0% | 2280 | 2280 | 0% | $548,628,982.00 | $0.00 | $0.00 | 2693 | 2020-10-01 | 2028-01-13 | $0.00 | $0.00
A1440 | 2027-11-18 | 2028-01-13 | Cost Loading - CASH OUT |  | 5.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Prepare Demarcation Plan and Plot Survey Reports | MJ-MSBL-INT-1.14.5.3 | 40 | Secondary Infrastructure Networks | Fixed Duration & Units | 0 | 0% | 0% | 40 | 40 | 0% | $0.00 | $0.00 | $0.00 | 2222 | 2027-11-18 | 2028-01-13 | $0.00 | $0.00
L7100 | 2020-10-01 | 2027-11-18 |  |  | 5.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Secondary Infrastructure Networks | MJ-MSBL-INT-1.14.5.3 | 2170 | Secondary Infrastructure Networks | Fixed Duration & Units | 0 | 0% | 0% | 2170 | 2170 | 0% | $0.00 | $0.00 | $0.00 | 2714 | 2020-10-01 | 2027-11-18 | $0.00 | $0.00
M1425 |  | 2028-01-13 |  |  | 5.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | [Municipality] Approval of Final Demarcation Plan | MJ-MSBL-INT-1.14.5.3 | 0 | Secondary Infrastructure Networks | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2222 |  | 2028-01-13 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1 MOH Beneficiaries' Units | 2020-10-01 | 2026-10-05 | [7 empty] | 1828 |  |  | 0 |  | 0% | 1828 | 1828 | 0% | $436,228,783.00 | $0.00 | $0.00 | 3056 | 2020-10-01 | 2026-10-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.19 Package (01] | 2020-10-01 | 2023-06-05 | [7 empty] | 816 |  |  | 0 |  | 0% | 816 | 816 | 0% | $93,461,188.00 | $0.00 | $0.00 | 3988 | 2020-10-01 | 2023-06-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.19.1 Priority 01 | 2020-10-01 | 2022-11-12 | [7 empty] | 644 |  |  | 0 |  | 0% | 644 | 644 | 0% | $26,192,880.00 | $0.00 | $0.00 | 4160 | 2020-10-01 | 2022-11-12 | $0.00 | $0.00
A11980 | 2020-10-01 | 2022-11-12 | Cost Loading - CASH OUT |  | 5.3.1.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 01] | MJ-MSBL-INT-1.14.5.3.1.19.1 | 644 | Priority 01 | Fixed Duration & Units | 0 | 0% | 0% | 644 | 644 | 0% | $26,192,880.00 | $0.00 | $0.00 | 4160 | 2020-10-01 | 2022-11-12 | $0.00 | $0.00
M13620 |  | 2022-11-12 |  |  | 5.3.1.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 01] | MJ-MSBL-INT-1.14.5.3.1.19.1 | 0 | Priority 01 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4160 |  | 2022-11-12 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.19.2 Priority 02 | 2021-01-10 | 2023-02-25 | [7 empty] | 648 |  |  | 0 |  | 0% | 648 | 648 | 0% | $46,038,876.00 | $0.00 | $0.00 | 3762 | 2021-01-10 | 2023-02-25 | $0.00 | $0.00
A13320 | 2021-01-10 | 2023-02-25 | Cost Loading - CASH OUT |  | 5.3.1.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 02] | MJ-MSBL-INT-1.14.5.3.1.19.2 | 648 | Priority 02 | Fixed Duration & Units | 0 | 0% | 0% | 648 | 648 | 0% | $46,038,876.00 | $0.00 | $0.00 | 3762 | 2021-01-10 | 2023-02-25 | $0.00 | $0.00
M13630 |  | 2023-02-25 |  |  | 5.3.1.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 02] | MJ-MSBL-INT-1.14.5.3.1.19.2 | 0 | Priority 02 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3762 |  | 2023-02-25 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.19.4 Priority 04 | 2021-04-19 | 2023-06-05 | [7 empty] | 645 |  |  | 0 |  | 0% | 645 | 645 | 0% | $21,229,432.00 | $0.00 | $0.00 | 3680 | 2021-04-19 | 2023-06-05 | $0.00 | $0.00
A13330 | 2021-04-19 | 2023-06-05 | Cost Loading - CASH OUT |  | 5.3.1.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 04] | MJ-MSBL-INT-1.14.5.3.1.19.4 | 645 | Priority 04 | Fixed Duration & Units | 0 | 0% | 0% | 645 | 645 | 0% | $21,229,432.00 | $0.00 | $0.00 | 3680 | 2021-04-19 | 2023-06-05 | $0.00 | $0.00
M13640 |  | 2023-06-05 |  |  | 5.3.1.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 04] | MJ-MSBL-INT-1.14.5.3.1.19.4 | 0 | Priority 04 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3680 |  | 2023-06-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.20 Package (02) | 2021-08-04 | 2024-11-05 | [7 empty] | 991 |  |  | 0 |  | 0% | 991 | 991 | 0% | $97,071,627.00 | $0.00 | $0.00 | 3637 | 2021-08-04 | 2024-11-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.20.5 Priority 05 | 2021-08-04 | 2023-09-17 | [7 empty] | 645 |  |  | 0 |  | 0% | 645 | 645 | 0% | $13,009,197.00 | $0.00 | $0.00 | 3983 | 2021-08-04 | 2023-09-17 | $0.00 | $0.00
A13340 | 2021-08-04 | 2023-09-17 | Cost Loading - CASH OUT |  | 5.3.1.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 05] | MJ-MSBL-INT-1.14.5.3.1.20.5 | 645 | Priority 05 | Fixed Duration & Units | 0 | 0% | 0% | 645 | 645 | 0% | $13,009,197.00 | $0.00 | $0.00 | 3595 | 2021-08-04 | 2023-09-17 | $0.00 | $0.00
M13650 |  | 2023-09-17 |  |  | 5.3.1.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 05] | MJ-MSBL-INT-1.14.5.3.1.20.5 | 0 | Priority 05 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3983 |  | 2023-09-17 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.20.6 Priority 07 | 2021-11-14 | 2024-01-14 | [7 empty] | 660 |  |  | 0 |  | 0% | 660 | 660 | 0% | $17,291,759.00 | $0.00 | $0.00 | 3882 | 2021-11-14 | 2024-01-14 | $0.00 | $0.00
A12030 | 2021-11-14 | 2024-01-14 | Cost Loading - CASH OUT |  | 5.3.1.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 07] | MJ-MSBL-INT-1.14.5.3.1.20.6 | 660 | Priority 07 | Fixed Duration & Units | 0 | 0% | 0% | 660 | 660 | 0% | $17,291,759.00 | $0.00 | $0.00 | 3822 | 2021-11-14 | 2024-01-14 | $0.00 | $0.00
M13660 |  | 2024-01-14 |  |  | 5.3.1.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 07] | MJ-MSBL-INT-1.14.5.3.1.20.6 | 0 | Priority 07 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3882 |  | 2024-01-14 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.20.8 Priority 08 | 2022-02-21 | 2024-04-09 | [7 empty] | 649 |  |  | 0 |  | 0% | 649 | 649 | 0% | $24,885,689.00 | $0.00 | $0.00 | 3808 | 2022-02-21 | 2024-04-09 | $0.00 | $0.00
A13350 | 2022-02-21 | 2024-04-09 | Cost Loading - CASH OUT |  | 5.3.1.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 08] | MJ-MSBL-INT-1.14.5.3.1.20.8 | 649 | Priority 08 | Fixed Duration & Units | 0 | 0% | 0% | 649 | 649 | 0% | $24,885,689.00 | $0.00 | $0.00 | 3748 | 2022-02-21 | 2024-04-09 | $0.00 | $0.00
M13670 |  | 2024-04-09 |  |  | 5.3.1.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 08] | MJ-MSBL-INT-1.14.5.3.1.20.8 | 0 | Priority 08 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3808 |  | 2024-04-09 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.20.7 Priority 09 | 2022-06-06 | 2024-07-23 | [7 empty] | 645 |  |  | 0 |  | 0% | 645 | 645 | 0% | $17,344,346.00 | $0.00 | $0.00 | 3726 | 2022-06-06 | 2024-07-23 | $0.00 | $0.00
A13360 | 2022-06-06 | 2024-07-23 | Cost Loading - CASH OUT |  | 5.3.1.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 09] | MJ-MSBL-INT-1.14.5.3.1.20.7 | 645 | Priority 09 | Fixed Duration & Units | 0 | 0% | 0% | 645 | 645 | 0% | $17,344,346.00 | $0.00 | $0.00 | 3666 | 2022-06-06 | 2024-07-23 | $0.00 | $0.00
M13680 |  | 2024-07-23 |  |  | 5.3.1.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 09] | MJ-MSBL-INT-1.14.5.3.1.20.7 | 0 | Priority 09 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3726 |  | 2024-07-23 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.20.10 Priority 10 | 2022-09-18 | 2024-11-05 | [7 empty] | 649 |  |  | 0 |  | 0% | 649 | 649 | 0% | $24,540,636.00 | $0.00 | $0.00 | 3637 | 2022-09-18 | 2024-11-05 | $0.00 | $0.00
A13370 | 2022-09-18 | 2024-11-05 | Cost Loading - CASH OUT |  | 5.3.1.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 10] | MJ-MSBL-INT-1.14.5.3.1.20.10 | 649 | Priority 10 | Fixed Duration & Units | 0 | 0% | 0% | 649 | 649 | 0% | $24,540,636.00 | $0.00 | $0.00 | 3577 | 2022-09-18 | 2024-11-05 | $0.00 | $0.00
M13690 |  | 2024-11-05 |  |  | 5.3.1.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 10] | MJ-MSBL-INT-1.14.5.3.1.20.10 | 0 | Priority 10 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3637 |  | 2024-11-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.21 Package (03) | 2022-12-26 | 2026-03-11 | [7 empty] | 978 |  |  | 0 |  | 0% | 978 | 978 | 0% | $193,179,963.00 | $0.00 | $0.00 | 3224 | 2022-12-26 | 2026-03-11 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.21.3 Priority 11 | 2022-12-26 | 2025-02-16 | [7 empty] | 653 |  |  | 0 |  | 0% | 653 | 653 | 0% | $28,220,945.00 | $0.00 | $0.00 | 3549 | 2022-12-26 | 2025-02-16 | $0.00 | $0.00
A13380 | 2022-12-26 | 2025-02-16 | Cost Loading - CASH OUT |  | 5.3.1.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 11] | MJ-MSBL-INT-1.14.5.3.1.21.3 | 653 | Priority 11 | Fixed Duration & Units | 0 | 0% | 0% | 653 | 653 | 0% | $28,220,945.00 | $0.00 | $0.00 | 3489 | 2022-12-26 | 2025-02-16 | $0.00 | $0.00
M13700 |  | 2025-02-16 |  |  | 5.3.1.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 11] | MJ-MSBL-INT-1.14.5.3.1.21.3 | 0 | Priority 11 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3549 |  | 2025-02-16 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.21.9 Priority 13 | 2023-03-27 | 2025-05-13 | [7 empty] | 645 |  |  | 0 |  | 0% | 645 | 645 | 0% | $21,897,999.00 | $0.00 | $0.00 | 3479 | 2023-03-27 | 2025-05-13 | $0.00 | $0.00
A13390 | 2023-03-27 | 2025-05-13 | Cost Loading - CASH OUT |  | 5.3.1.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 13] | MJ-MSBL-INT-1.14.5.3.1.21.9 | 645 | Priority 13 | Fixed Duration & Units | 0 | 0% | 0% | 645 | 645 | 0% | $21,897,999.00 | $0.00 | $0.00 | 3419 | 2023-03-27 | 2025-05-13 | $0.00 | $0.00
M13710 |  | 2025-05-13 |  |  | 5.3.1.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 13] | MJ-MSBL-INT-1.14.5.3.1.21.9 | 0 | Priority 13 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3479 |  | 2025-05-13 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.21.11 Priority 14 | 2023-07-12 | 2025-08-24 | [7 empty] | 645 |  |  | 0 |  | 0% | 645 | 645 | 0% | $36,591,213.00 | $0.00 | $0.00 | 3395 | 2023-07-12 | 2025-08-24 | $0.00 | $0.00
A12080 | 2023-07-12 | 2025-08-24 | Cost Loading - CASH OUT |  | 5.3.1.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 14] | MJ-MSBL-INT-1.14.5.3.1.21.11 | 645 | Priority 14 | Fixed Duration & Units | 0 | 0% | 0% | 645 | 645 | 0% | $36,591,213.00 | $0.00 | $0.00 | 3335 | 2023-07-12 | 2025-08-24 | $0.00 | $0.00
M13720 |  | 2025-08-24 |  |  | 5.3.1.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 14] | MJ-MSBL-INT-1.14.5.3.1.21.11 | 0 | Priority 14 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3395 |  | 2025-08-24 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.21.12 Priority 15 | 2023-10-19 | 2025-12-01 | [7 empty] | 645 |  |  | 0 |  | 0% | 645 | 645 | 0% | $16,968,562.00 | $0.00 | $0.00 | 3311 | 2023-10-19 | 2025-12-01 | $0.00 | $0.00
A13400 | 2023-10-19 | 2025-12-01 | Cost Loading - CASH OUT |  | 5.3.1.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 15] | MJ-MSBL-INT-1.14.5.3.1.21.12 | 645 | Priority 15 | Fixed Duration & Units | 0 | 0% | 0% | 645 | 645 | 0% | $16,968,562.00 | $0.00 | $0.00 | 3251 | 2023-10-19 | 2025-12-01 | $0.00 | $0.00
M13730 |  | 2025-12-01 |  |  | 5.3.1.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 15] | MJ-MSBL-INT-1.14.5.3.1.21.12 | 0 | Priority 15 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3311 |  | 2025-12-01 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.21.13 Priority 16 | 2024-01-28 | 2026-03-11 | [7 empty] | 646 |  |  | 0 |  | 0% | 646 | 646 | 0% | $89,501,244.00 | $0.00 | $0.00 | 3224 | 2024-01-28 | 2026-03-11 | $0.00 | $0.00
A13410 | 2024-01-28 | 2026-03-11 | Cost Loading - CASH OUT |  | 5.3.1.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 16] | MJ-MSBL-INT-1.14.5.3.1.21.13 | 646 | Priority 16 | Fixed Duration & Units | 0 | 0% | 0% | 646 | 646 | 0% | $89,501,244.00 | $0.00 | $0.00 | 3164 | 2024-01-28 | 2026-03-11 | $0.00 | $0.00
M13740 |  | 2026-03-11 |  |  | 5.3.1.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 16] | MJ-MSBL-INT-1.14.5.3.1.21.13 | 0 | Priority 16 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3224 |  | 2026-03-11 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.22 Package (04) | 2024-05-09 | 2026-10-05 | [7 empty] | 730 |  |  | 0 |  | 0% | 730 | 730 | 0% | $52,516,005.00 | $0.00 | $0.00 | 3056 | 2024-05-09 | 2026-10-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.22.14 Priority 17 | 2024-05-09 | 2026-06-27 | [7 empty] | 645 |  |  | 0 |  | 0% | 645 | 645 | 0% | $23,944,062.00 | $0.00 | $0.00 | 3141 | 2024-05-09 | 2026-06-27 | $0.00 | $0.00
A13420 | 2024-05-09 | 2026-06-27 | Cost Loading - CASH OUT |  | 5.3.1.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 17] | MJ-MSBL-INT-1.14.5.3.1.22.14 | 645 | Priority 17 | Fixed Duration & Units | 0 | 0% | 0% | 645 | 645 | 0% | $23,944,062.00 | $0.00 | $0.00 | 3081 | 2024-05-09 | 2026-06-27 | $0.00 | $0.00
M13750 |  | 2026-06-27 |  |  | 5.3.1.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 17] | MJ-MSBL-INT-1.14.5.3.1.22.14 | 0 | Priority 17 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3141 |  | 2026-06-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.1.22.15 Priority 18 | 2024-08-21 | 2026-10-05 | [7 empty] | 645 |  |  | 0 |  | 0% | 645 | 645 | 0% | $28,571,943.00 | $0.00 | $0.00 | 3056 | 2024-08-21 | 2026-10-05 | $0.00 | $0.00
A13430 | 2024-08-21 | 2026-10-05 | Cost Loading - CASH OUT |  | 5.3.1.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 18] | MJ-MSBL-INT-1.14.5.3.1.22.15 | 645 | Priority 18 | Fixed Duration & Units | 0 | 0% | 0% | 645 | 645 | 0% | $28,571,943.00 | $0.00 | $0.00 | 2996 | 2024-08-21 | 2026-10-05 | $0.00 | $0.00
M13760 |  | 2026-10-05 |  |  | 5.3.1.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 18] | MJ-MSBL-INT-1.14.5.3.1.22.15 | 0 | Priority 18 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3056 |  | 2026-10-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.2 Other Beneficiaries' Units | 2024-12-01 | 2027-11-18 | [7 empty] | 901 |  |  | 0 |  | 0% | 901 | 901 | 0% | $112,400,199.00 | $0.00 | $0.00 | 2714 | 2024-12-01 | 2027-11-18 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.2.2 Packages (01,02,03,04) | 2024-12-01 | 2027-11-18 | [7 empty] | 901 |  |  | 0 |  | 0% | 901 | 901 | 0% | $112,400,199.00 | $0.00 | $0.00 | 2714 | 2024-12-01 | 2027-11-18 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.2.2.16 Priority 03 | 2024-12-01 | 2027-01-13 | [7 empty] | 645 |  |  | 0 |  | 0% | 645 | 645 | 0% | $24,803,207.00 | $0.00 | $0.00 | 2970 | 2024-12-01 | 2027-01-13 | $0.00 | $0.00
A13440 | 2024-12-01 | 2027-01-13 | Cost Loading - CASH OUT |  | 5.3.2.2.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 03] | MJ-MSBL-INT-1.14.5.3.2.2.16 | 645 | Priority 03 | Fixed Duration & Units | 0 | 0% | 0% | 645 | 645 | 0% | $24,803,207.00 | $0.00 | $0.00 | 2910 | 2024-12-01 | 2027-01-13 | $0.00 | $0.00
M13770 |  | 2027-01-13 |  |  | 5.3.2.2.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 03] | MJ-MSBL-INT-1.14.5.3.2.2.16 | 0 | Priority 03 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2970 |  | 2027-01-13 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.2.2.17 Priority 06 | 2025-03-10 | 2027-04-27 | [7 empty] | 645 |  |  | 0 |  | 0% | 645 | 645 | 0% | $23,757,214.00 | $0.00 | $0.00 | 2885 | 2025-03-10 | 2027-04-27 | $0.00 | $0.00
A12130 | 2025-03-10 | 2027-04-27 | Cost Loading - CASH OUT |  | 5.3.2.2.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 06] | MJ-MSBL-INT-1.14.5.3.2.2.17 | 645 | Priority 06 | Fixed Duration & Units | 0 | 0% | 0% | 645 | 645 | 0% | $23,757,214.00 | $0.00 | $0.00 | 2825 | 2025-03-10 | 2027-04-27 | $0.00 | $0.00
M13780 |  | 2027-04-27 |  |  | 5.3.2.2.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 067] | MJ-MSBL-INT-1.14.5.3.2.2.17 | 0 | Priority 06 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2885 |  | 2027-04-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.2.2.18 Priority 12 | 2025-06-26 | 2027-08-09 | [7 empty] | 645 |  |  | 0 |  | 0% | 645 | 645 | 0% | $25,887,510.00 | $0.00 | $0.00 | 2800 | 2025-06-26 | 2027-08-09 | $0.00 | $0.00
A13450 | 2025-06-26 | 2027-08-09 | Cost Loading - CASH OUT |  | 5.3.2.2.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 12] | MJ-MSBL-INT-1.14.5.3.2.2.18 | 645 | Priority 12 | Fixed Duration & Units | 0 | 0% | 0% | 645 | 645 | 0% | $25,887,510.00 | $0.00 | $0.00 | 2740 | 2025-06-26 | 2027-08-09 | $0.00 | $0.00
M13790 |  | 2027-08-09 |  |  | 5.3.2.2.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 12] | MJ-MSBL-INT-1.14.5.3.2.2.18 | 0 | Priority 12 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2800 |  | 2027-08-09 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.3.2.2.1 Priority 19 | 2025-10-06 | 2027-11-18 | [7 empty] | 645 |  |  | 0 |  | 0% | 645 | 645 | 0% | $37,952,268.00 | $0.00 | $0.00 | 2714 | 2025-10-06 | 2027-11-18 | $0.00 | $0.00
A13460 | 2025-10-06 | 2027-11-18 | Cost Loading - CASH OUT |  | 5.3.2.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work for Secondary Networks [Priority 19] | MJ-MSBL-INT-1.14.5.3.2.2.1 | 645 | Priority 19 | Fixed Duration & Units | 0 | 0% | 0% | 645 | 645 | 0% | $37,952,268.00 | $0.00 | $0.00 | 2654 | 2025-10-06 | 2027-11-18 | $0.00 | $0.00
M13800 |  | 2027-11-18 |  |  | 5.3.2.2.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 19] | MJ-MSBL-INT-1.14.5.3.2.2.1 | 0 | Priority 19 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2714 |  | 2027-11-18 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11 Superstructure Work | 2020-10-17 | 1930-02-21 | [7 empty] | 2844 |  |  | 0 |  | 0% | 2844 | 2844 | 0% | $5,896,585,282.50 | $0.00 | $0.00 | 2027 | 2020-10-17 | 1930-02-21 | $0.00 | $0.00
L2100 | 2020-10-17 | 1930-02-21 | Cost Loading - CASH OUT |  | 5.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Superstructure Construction Supervision | MJ-MSBL-INT-1.14.5.11 | 2844 | Superstructure Work | Fixed Duration & Units | 0 | 0% | 0% | 2844 | 2844 | 0% | $96,665,332.50 | $0.00 | $0.00 | 1 | 2020-10-17 | 1930-02-21 | $0.00 | $0.00
L7110 | 2020-10-20 | 1930-01-23 |  |  | 5.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Superstructure Works | MJ-MSBL-INT-1.14.5.11 | 2820 | Superstructure Work | Fixed Duration & Units | 0 | 0% | 0% | 2820 | 2820 | 0% | $0.00 | $0.00 | $0.00 | 2048 | 2020-10-20 | 1930-01-23 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3 MOH Beneficiaries' Units | 2020-10-17 | 1930-02-21 | [7 empty] | 2844 |  |  | 0 |  | 0% | 2844 | 2844 | 0% | $4,798,982,430.00 | $0.00 | $0.00 | 2027 | 2020-10-17 | 1930-02-21 | $0.00 | $0.00
T2200 | 2020-10-17 | 2020-11-14 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 5.11.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Mobilization & Site Prepration | MJ-MSBL-INT-1.14.5.11.3 | 25 | MOH Beneficiaries' Units | Fixed Duration & Units | 0 | 0% | 0% | 25 | 25 | 0% | $0.00 | $0.00 | $0.00 | 639 | 2020-10-17 | 2020-11-14 | $0.00 | $0.00
T2510 | 1930-01-23 | 1930-02-21 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 5.11.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | De-Mobilization | MJ-MSBL-INT-1.14.5.11.3 | 22 | MOH Beneficiaries' Units | Fixed Duration & Units | 0 | 0% | 0% | 22 | 22 | 0% | $0.00 | $0.00 | $0.00 | 2027 | 1930-01-23 | 1930-02-21 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.1 Package (01] | 2020-10-20 | 2024-02-07 | [7 empty] | 1008 |  |  | 0 |  | 0% | 1008 | 1008 | 0% | $878,211,180.00 | $0.00 | $0.00 | 3860 | 2020-10-20 | 2024-02-07 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.1.20 Priority 01 | 2020-10-20 | 2023-04-29 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $260,575,920.00 | $0.00 | $0.00 | 4099 | 2020-10-20 | 2023-04-29 | $0.00 | $0.00
A9730 | 2020-10-20 | 2023-04-29 | Cost Loading - CASH OUT |  | 5.11.3.1.20 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 01] | MJ-MSBL-INT-1.14.5.11.3.1.20 | 769 | Priority 01 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $260,575,920.00 | $0.00 | $0.00 | 636 | 2020-10-20 | 2023-04-29 | $0.00 | $0.00
M9580 |  | 2023-04-29 |  |  | 5.11.3.1.20 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 01] | MJ-MSBL-INT-1.14.5.11.3.1.20 | 0 | Priority 01 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4099 |  | 2023-04-29 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.1.21 Priority 02 | 2021-03-10 | 2023-09-21 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $361,841,040.00 | $0.00 | $0.00 | 3978 | 2021-03-10 | 2023-09-21 | $0.00 | $0.00
A11660 | 2021-03-10 | 2023-09-21 | Cost Loading - CASH OUT |  | 5.11.3.1.21 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 02] | MJ-MSBL-INT-1.14.5.11.3.1.21 | 769 | Priority 02 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $361,841,040.00 | $0.00 | $0.00 | 593 | 2021-03-10 | 2023-09-21 | $0.00 | $0.00
M11550 |  | 2023-09-21 |  |  | 5.11.3.1.21 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 02] | MJ-MSBL-INT-1.14.5.11.3.1.21 | 0 | Priority 02 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3978 |  | 2023-09-21 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.1.22 Priority 04 | 2021-08-03 | 2024-02-07 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $255,794,220.00 | $0.00 | $0.00 | 3860 | 2021-08-03 | 2024-02-07 | $0.00 | $0.00
A11780 | 2021-08-03 | 2024-02-07 | Cost Loading - CASH OUT |  | 5.11.3.1.22 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 04] | MJ-MSBL-INT-1.14.5.11.3.1.22 | 769 | Priority 04 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $255,794,220.00 | $0.00 | $0.00 | 553 | 2021-08-03 | 2024-02-07 | $0.00 | $0.00
M11680 |  | 2024-02-07 |  |  | 5.11.3.1.22 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 04] | MJ-MSBL-INT-1.14.5.11.3.1.22 | 0 | Priority 04 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3860 |  | 2024-02-07 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.2 Package (02) | 2021-12-20 | 2026-01-13 | [7 empty] | 1238 |  |  | 0 |  | 0% | 1238 | 1238 | 0% | $1,160,046,360.00 | $0.00 | $0.00 | 3273 | 2021-12-20 | 2026-01-13 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.2.23 Priority 05 | 2021-12-20 | 2024-07-03 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $130,831,470.00 | $0.00 | $0.00 | 3742 | 2021-12-20 | 2024-07-03 | $0.00 | $0.00
A11540 | 2021-12-20 | 2024-07-03 | Cost Loading - CASH OUT |  | 5.11.3.2.23 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 05] | MJ-MSBL-INT-1.14.5.11.3.2.23 | 769 | Priority 05 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $130,831,470.00 | $0.00 | $0.00 | 513 | 2021-12-20 | 2024-07-03 | $0.00 | $0.00
M11430 |  | 2024-07-03 |  |  | 5.11.3.2.23 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 05] | MJ-MSBL-INT-1.14.5.11.3.2.23 | 0 | Priority 05 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3742 |  | 2024-07-03 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.2.6 Priority 07 | 2022-05-11 | 2024-11-19 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $199,949,310.00 | $0.00 | $0.00 | 1522 | 2022-05-11 | 2024-11-19 | $0.00 | $0.00
A9960 | 2022-05-11 | 2024-11-19 | Cost Loading - CASH OUT |  | 5.11.3.2.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 07] | MJ-MSBL-INT-1.14.5.11.3.2.6 | 769 | Priority 07 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $199,949,310.00 | $0.00 | $0.00 | 473 | 2022-05-11 | 2024-11-19 | $0.00 | $0.00
M9970 |  | 2024-11-19 |  |  | 5.11.3.2.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 07] | MJ-MSBL-INT-1.14.5.11.3.2.6 | 0 | Priority 07 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 1522 |  | 2024-11-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.2.8 Priority 08 | 2022-09-29 | 2025-04-08 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $324,175,500.00 | $0.00 | $0.00 | 680 | 2022-09-29 | 2025-04-08 | $0.00 | $0.00
A10200 | 2022-09-29 | 2025-04-08 | Cost Loading - CASH OUT |  | 5.11.3.2.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 08] | MJ-MSBL-INT-1.14.5.11.3.2.8 | 769 | Priority 08 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $324,175,500.00 | $0.00 | $0.00 | 435 | 2022-09-29 | 2025-04-08 | $0.00 | $0.00
M10210 |  | 2025-04-08 |  |  | 5.11.3.2.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 08] | MJ-MSBL-INT-1.14.5.11.3.2.8 | 0 | Priority 08 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 680 |  | 2025-04-08 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.2.7 Priority 09 | 2023-02-14 | 2025-08-28 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $219,361,230.00 | $0.00 | $0.00 | 3390 | 2023-02-14 | 2025-08-28 | $0.00 | $0.00
A10320 | 2023-02-14 | 2025-08-28 | Cost Loading - CASH OUT |  | 5.11.3.2.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 09] | MJ-MSBL-INT-1.14.5.11.3.2.7 | 769 | Priority 09 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $219,361,230.00 | $0.00 | $0.00 | 395 | 2023-02-14 | 2025-08-28 | $0.00 | $0.00
M10340 |  | 2025-08-28 |  |  | 5.11.3.2.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 09] | MJ-MSBL-INT-1.14.5.11.3.2.7 | 0 | Priority 09 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3390 |  | 2025-08-28 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.2.10 Priority 10 | 2023-07-10 | 2026-01-13 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $285,728,850.00 | $0.00 | $0.00 | 3273 | 2023-07-10 | 2026-01-13 | $0.00 | $0.00
A10440 | 2023-07-10 | 2026-01-13 | Cost Loading - CASH OUT |  | 5.11.3.2.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 10] | MJ-MSBL-INT-1.14.5.11.3.2.10 | 769 | Priority 10 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $285,728,850.00 | $0.00 | $0.00 | 356 | 2023-07-10 | 2026-01-13 | $0.00 | $0.00
M10450 |  | 2026-01-13 |  |  | 5.11.3.2.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 10] | MJ-MSBL-INT-1.14.5.11.3.2.10 | 0 | Priority 10 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3273 |  | 2026-01-13 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.5 Package (03) | 2023-11-23 | 2027-09-18 | [7 empty] | 1161 |  |  | 0 |  | 0% | 1161 | 1161 | 0% | $2,218,102,920.00 | $0.00 | $0.00 | 2765 | 2023-11-23 | 2027-09-18 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.5.9 Priority 11 | 2023-11-23 | 2026-06-07 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $308,205,810.00 | $0.00 | $0.00 | 3157 | 2023-11-23 | 2026-06-07 | $0.00 | $0.00
A10080 | 2023-11-23 | 2026-06-07 | Cost Loading - CASH OUT |  | 5.11.3.5.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 11] | MJ-MSBL-INT-1.14.5.11.3.5.9 | 769 | Priority 11 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $308,205,810.00 | $0.00 | $0.00 | 318 | 2023-11-23 | 2026-06-07 | $0.00 | $0.00
M10090 |  | 2026-06-07 |  |  | 5.11.3.5.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 1] | MJ-MSBL-INT-1.14.5.11.3.5.9 | 0 | Priority 11 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3157 |  | 2026-06-07 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.5.11 Priority 13 | 2024-04-09 | 2026-10-24 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $268,639,470.00 | $0.00 | $0.00 | 2941 | 2024-04-09 | 2026-10-24 | $0.00 | $0.00
A9850 | 2024-04-09 | 2026-10-24 | Cost Loading - CASH OUT |  | 5.11.3.5.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 13] | MJ-MSBL-INT-1.14.5.11.3.5.11 | 769 | Priority 13 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $268,639,470.00 | $0.00 | $0.00 | 278 | 2024-04-09 | 2026-10-24 | $0.00 | $0.00
M9740 |  | 2026-10-24 |  |  | 5.11.3.5.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 13] | MJ-MSBL-INT-1.14.5.11.3.5.11 | 0 | Priority 13 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2941 |  | 2026-10-24 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.5.12 Priority 14 | 2024-07-18 | 2027-01-23 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $428,250,240.00 | $0.00 | $0.00 | 2961 | 2024-07-18 | 2027-01-23 | $0.00 | $0.00
A10560 | 2024-07-18 | 2027-01-23 | Cost Loading - CASH OUT |  | 5.11.3.5.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 14] | MJ-MSBL-INT-1.14.5.11.3.5.12 | 769 | Priority 14 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $428,250,240.00 | $0.00 | $0.00 | 278 | 2024-07-18 | 2027-01-23 | $0.00 | $0.00
M10570 |  | 2027-01-23 |  |  | 5.11.3.5.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 14] | MJ-MSBL-INT-1.14.5.11.3.5.12 | 0 | Priority 14 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2961 |  | 2027-01-23 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.5.13 Priority 15 | 2024-10-19 | 2027-04-28 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $191,481,840.00 | $0.00 | $0.00 | 2883 | 2024-10-19 | 2027-04-28 | $0.00 | $0.00
A10680 | 2024-10-19 | 2027-04-28 | Cost Loading - CASH OUT |  | 5.11.3.5.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 15] | MJ-MSBL-INT-1.14.5.11.3.5.13 | 769 | Priority 15 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $191,481,840.00 | $0.00 | $0.00 | 278 | 2024-10-19 | 2027-04-28 | $0.00 | $0.00
M10690 |  | 2027-04-28 |  |  | 5.11.3.5.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 15] | MJ-MSBL-INT-1.14.5.11.3.5.13 | 0 | Priority 15 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2883 |  | 2027-04-28 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.5.14 Priority 16 | 2025-03-05 | 2027-09-18 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $1,021,525,560.00 | $0.00 | $0.00 | 2765 | 2025-03-05 | 2027-09-18 | $0.00 | $0.00
A10800 | 2025-03-05 | 2027-09-18 | Cost Loading - CASH OUT |  | 5.11.3.5.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 16] | MJ-MSBL-INT-1.14.5.11.3.5.14 | 769 | Priority 16 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $1,021,525,560.00 | $0.00 | $0.00 | 238 | 2025-03-05 | 2027-09-18 | $0.00 | $0.00
M10810 |  | 2027-09-18 |  |  | 5.11.3.5.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 16] | MJ-MSBL-INT-1.14.5.11.3.5.14 | 0 | Priority 16 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2765 |  | 2027-09-18 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.4 Package (04) | 2025-07-30 | 2028-06-29 | [7 empty] | 887 |  |  | 0 |  | 0% | 887 | 887 | 0% | $542,621,970.00 | $0.00 | $0.00 | 2529 | 2025-07-30 | 2028-06-29 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.4.15 Priority 17 | 2025-07-30 | 2028-02-03 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $223,750,890.00 | $0.00 | $0.00 | 2647 | 2025-07-30 | 2028-02-03 | $0.00 | $0.00
A10920 | 2025-07-30 | 2028-02-03 | Cost Loading - CASH OUT |  | 5.11.3.4.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 17] | MJ-MSBL-INT-1.14.5.11.3.4.15 | 769 | Priority 17 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $223,750,890.00 | $0.00 | $0.00 | 198 | 2025-07-30 | 2028-02-03 | $0.00 | $0.00
M10930 |  | 2028-02-03 |  |  | 5.11.3.4.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 17] | MJ-MSBL-INT-1.14.5.11.3.4.15 | 0 | Priority 17 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2647 |  | 2028-02-03 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.3.4.16 Priority 18 | 2025-12-16 | 2028-06-29 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $318,871,080.00 | $0.00 | $0.00 | 2529 | 2025-12-16 | 2028-06-29 | $0.00 | $0.00
A11040 | 2025-12-16 | 2028-06-29 | Cost Loading - CASH OUT |  | 5.11.3.4.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 18] | MJ-MSBL-INT-1.14.5.11.3.4.16 | 769 | Priority 18 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $318,871,080.00 | $0.00 | $0.00 | 158 | 2025-12-16 | 2028-06-29 | $0.00 | $0.00
M11050 |  | 2028-06-29 |  |  | 5.11.3.4.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 18] | MJ-MSBL-INT-1.14.5.11.3.4.16 | 0 | Priority 18 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2529 |  | 2028-06-29 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.7 Other Beneficiaries' Units | 2026-05-06 | 1930-01-23 | [7 empty] | 1133 |  |  | 0 |  | 0% | 1133 | 1133 | 0% | $1,000,937,520.00 | $0.00 | $0.00 | 2048 | 2026-05-06 | 1930-01-23 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.7.6 Packages (01,02,03,04) | 2026-05-06 | 1930-01-23 | [7 empty] | 1133 |  |  | 0 |  | 0% | 1133 | 1133 | 0% | $1,000,937,520.00 | $0.00 | $0.00 | 2048 | 2026-05-06 | 1930-01-23 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.7.6.17 Priority 03 | 2026-05-06 | 2028-11-14 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $197,080,290.00 | $0.00 | $0.00 | 2412 | 2026-05-06 | 2028-11-14 | $0.00 | $0.00
A11160 | 2026-05-06 | 2028-11-14 | Cost Loading - CASH OUT |  | 5.11.7.6.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 03] | MJ-MSBL-INT-1.14.5.11.7.6.17 | 769 | Priority 03 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $197,080,290.00 | $0.00 | $0.00 | 119 | 2026-05-06 | 2028-11-14 | $0.00 | $0.00
M11170 |  | 2028-11-14 |  |  | 5.11.7.6.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 03] | MJ-MSBL-INT-1.14.5.11.7.6.17 | 0 | Priority 03 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2412 |  | 2028-11-14 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.7.6.18 Priority 06 | 2026-09-26 | 2029-04-04 | [7 empty] | 769 |  |  | 0 |  | 0% | 769 | 769 | 0% | $228,104,910.00 | $0.00 | $0.00 | 2295 | 2026-09-26 | 2029-04-04 | $0.00 | $0.00
A11280 | 2026-09-26 | 2029-04-04 | Cost Loading - CASH OUT |  | 5.11.7.6.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 06] | MJ-MSBL-INT-1.14.5.11.7.6.18 | 769 | Priority 06 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $228,104,910.00 | $0.00 | $0.00 | 80 | 2026-09-26 | 2029-04-04 | $0.00 | $0.00
M11290 |  | 2029-04-04 |  |  | 5.11.7.6.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 06] | MJ-MSBL-INT-1.14.5.11.7.6.18 | 0 | Priority 06 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2295 |  | 2029-04-04 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.7.6.19 Priority 12 | 2027-02-10 | 2029-09-08 | [7 empty] | 781 |  |  | 0 |  | 0% | 781 | 781 | 0% | $321,609,420.00 | $0.00 | $0.00 | 63 | 2027-02-10 | 2029-09-08 | $0.00 | $0.00
A11400 | 2027-02-10 | 2029-08-25 | Cost Loading - CASH OUT |  | 5.11.7.6.19 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 12] | MJ-MSBL-INT-1.14.5.11.7.6.19 | 769 | Priority 12 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $321,609,420.00 | $0.00 | $0.00 | 40 | 2027-02-10 | 2029-08-25 | $0.00 | $0.00
M11410 |  | 2029-09-08 |  |  | 5.11.7.6.19 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 12] | MJ-MSBL-INT-1.14.5.11.7.6.19 | 0 | Priority 12 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 63 |  | 2029-09-08 | $0.00 | $0.00
MJ-MSBL-INT-1.14.5.11.7.6.1 Priority 19 | 2027-07-06 | 1930-01-23 | [7 empty] | 781 |  |  | 0 |  | 0% | 781 | 781 | 0% | $254,142,900.00 | $0.00 | $0.00 | 2048 | 2027-07-06 | 1930-01-23 | $0.00 | $0.00
A12790 | 2027-07-06 | 1930-01-09 | Cost Loading - CASH OUT |  | 5.11.7.6.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Work [Priority 19] | MJ-MSBL-INT-1.14.5.11.7.6.1 | 769 | Priority 19 | Fixed Duration & Units | 0 | 0% | 0% | 769 | 769 | 0% | $254,142,900.00 | $0.00 | $0.00 | 1 | 2027-07-06 | 1930-01-09 | $0.00 | $0.00
M12785 |  | 1930-01-23 |  |  | 5.11.7.6.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Execution Completion Date [Priority 19] | MJ-MSBL-INT-1.14.5.11.7.6.1 | 0 | Priority 19 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2048 |  | 1930-01-23 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6 Initial Handing Over Phase | 2020-07-08 | 1930-03-19 | [7 empty] | 2947 |  |  | 0 |  | 0% | 2947 | 2947 | 0% | $788,050,721.00 | $0.00 | $0.00 | 2005 | 2020-07-08 | 1930-03-19 | $0.00 | $0.00
M1800 |  | 2020-09-28 |  |  | 6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Rough Grading] | MJ-MSBL-INT-1.14.6 | 0 | Initial Handing Over Phase | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4886 |  | 2020-09-28 | $0.00 | $0.00
T3120 | 2020-07-08 | 2020-09-28 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over [Rough Grading] | MJ-MSBL-INT-1.14.6 | 66 | Initial Handing Over Phase | Fixed Duration & Units | 0 | 0% | 0% | 66 | 66 | 0% | $0.00 | $0.00 | $0.00 | 4886 | 2020-07-08 | 2020-09-28 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.2 Main Infrastructure Networks, Roads & Landscape | 2023-01-01 | 2025-10-12 | [7 empty] | 844 |  |  | 0 |  | 0% | 844 | 844 | 0% | $82,656,394.00 | $0.00 | $0.00 | 3353 | 2023-01-01 | 2025-10-12 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.2.2 Main Infrastructure Networks, Roads & Culverts | 2023-08-27 | 2024-02-29 | [7 empty] | 160 |  |  | 0 |  | 0% | 160 | 160 | 0% | $31,763,784.00 | $0.00 | $0.00 | 3765 | 2023-08-27 | 2024-02-29 | $0.00 | $0.00
M1270 |  | 2024-02-29 |  |  | 6.2.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Main Networks] | MJ-MSBL-INT-1.14.6.2.2 | 0 | Main Infrastructure Networks, Roads & Culverts | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3765 |  | 2024-02-29 | $0.00 | $0.00
T2550 | 2023-08-27 | 2024-02-29 | Cost Loading - CASH OUT |  | 6.2.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Main Networks [Main Networks] | MJ-MSBL-INT-1.14.6.2.2 | 160 | Main Infrastructure Networks, Roads & Culverts | Fixed Duration & Units | 0 | 0% | 0% | 160 | 160 | 0% | $31,763,784.00 | $0.00 | $0.00 | 3529 | 2023-08-27 | 2024-02-29 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.2.4 Concrete Structures (Northern Entrances) | 2023-01-01 | 2023-05-30 | [7 empty] | 125 |  |  | 0 |  | 0% | 125 | 125 | 0% | $5,750,000.00 | $0.00 | $0.00 | 3996 | 2023-01-01 | 2023-05-30 | $0.00 | $0.00
M1960 |  | 2023-05-30 |  |  | 6.2.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Concrete Structures (N. Entrances)] | MJ-MSBL-INT-1.14.6.2.4 | 0 | Concrete Structures (Northern Entrances) | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3996 |  | 2023-05-30 | $0.00 | $0.00
T3170 | 2023-01-01 | 2023-05-30 | Cost Loading - CASH OUT |  | 6.2.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over [Concrete Structures (N. Entrances)] | MJ-MSBL-INT-1.14.6.2.4 | 125 | Concrete Structures (Northern Entrances) | Fixed Duration & Units | 0 | 0% | 0% | 125 | 125 | 0% | $5,750,000.00 | $0.00 | $0.00 | 3760 | 2023-01-01 | 2023-05-30 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.2.5 HV Substations | 2024-08-24 | 2025-01-21 | [7 empty] | 129 |  |  | 0 |  | 0% | 129 | 129 | 0% | $14,900,000.00 | $0.00 | $0.00 | 3494 | 2024-08-24 | 2025-01-21 | $0.00 | $0.00
M1970 |  | 2025-01-21 |  |  | 6.2.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [HV S/S ] | MJ-MSBL-INT-1.14.6.2.5 | 0 | HV Substations | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3494 |  | 2025-01-21 | $0.00 | $0.00
T3180 | 2024-08-24 | 2025-01-21 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.2.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over [HV S/S ] | MJ-MSBL-INT-1.14.6.2.5 | 129 | HV Substations | Fixed Duration & Units | 0 | 0% | 0% | 129 | 129 | 0% | $14,900,000.00 | $0.00 | $0.00 | 3494 | 2024-08-24 | 2025-01-21 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.2.6 Sewer Water Treatment Plant [STP] | 2024-01-29 | 2024-07-06 | [7 empty] | 129 |  |  | 0 |  | 0% | 129 | 129 | 0% | $1,000,000.00 | $0.00 | $0.00 | 3664 | 2024-01-29 | 2024-07-06 | $0.00 | $0.00
M1980 |  | 2024-07-06 |  |  | 6.2.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [STP] | MJ-MSBL-INT-1.14.6.2.6 | 0 | Sewer Water Treatment Plant [STP] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3664 |  | 2024-07-06 | $0.00 | $0.00
T3190 | 2024-01-29 | 2024-07-06 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.2.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over [STP] | MJ-MSBL-INT-1.14.6.2.6 | 129 | Sewer Water Treatment Plant [STP] | Fixed Duration & Units | 0 | 0% | 0% | 129 | 129 | 0% | $1,000,000.00 | $0.00 | $0.00 | 3428 | 2024-01-29 | 2024-07-06 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.2.7 Open Channel [Storm Water Drainage] | 2024-08-24 | 2025-01-16 | [7 empty] | 125 |  |  | 0 |  | 0% | 125 | 125 | 0% | $17,090,000.00 | $0.00 | $0.00 | 3498 | 2024-08-24 | 2025-01-16 | $0.00 | $0.00
M1990 |  | 2025-01-16 |  |  | 6.2.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [O.C.] | MJ-MSBL-INT-1.14.6.2.7 | 0 | Open Channel [Storm Water Drainage] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3498 |  | 2025-01-16 | $0.00 | $0.00
T3200 | 2024-08-24 | 2025-01-16 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.2.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over [O.C.] | MJ-MSBL-INT-1.14.6.2.7 | 125 | Open Channel [Storm Water Drainage] | Fixed Duration & Units | 0 | 0% | 0% | 125 | 125 | 0% | $17,090,000.00 | $0.00 | $0.00 | 3262 | 2024-08-24 | 2025-01-16 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.2.9 Road Finishes, Street Lighting Poles & Traffic Signals | 2024-08-26 | 2025-01-19 | [7 empty] | 125 |  |  | 0 |  | 0% | 125 | 125 | 0% | $7,852,610.00 | $0.00 | $0.00 | 3496 | 2024-08-26 | 2025-01-19 | $0.00 | $0.00
M2000 |  | 2025-01-19 |  |  | 6.2.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [RD&St.L.] | MJ-MSBL-INT-1.14.6.2.9 | 0 | Road Finishes, Street Lighting Poles & Traffic Signals | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3496 |  | 2025-01-19 | $0.00 | $0.00
T3210 | 2024-08-26 | 2025-01-19 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.2.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over [RD&St.L.] | MJ-MSBL-INT-1.14.6.2.9 | 125 | Road Finishes, Street Lighting Poles & Traffic Signals | Fixed Duration & Units | 0 | 0% | 0% | 125 | 125 | 0% | $7,852,610.00 | $0.00 | $0.00 | 3260 | 2024-08-26 | 2025-01-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.2.10 Landscape Work | 2025-02-25 | 2025-10-12 | [7 empty] | 188 |  |  | 0 |  | 0% | 188 | 188 | 0% | $4,300,000.00 | $0.00 | $0.00 | 3353 | 2025-02-25 | 2025-10-12 | $0.00 | $0.00
M13040 |  | 2025-10-12 |  |  | 6.2.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Landscape] | MJ-MSBL-INT-1.14.6.2.10 | 0 | Landscape Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3353 |  | 2025-10-12 | $0.00 | $0.00
T3130 | 2025-05-18 | 2025-10-12 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.2.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over [Landscape] | MJ-MSBL-INT-1.14.6.2.10 | 122 | Landscape Work | Fixed Duration & Units | 0 | 0% | 0% | 122 | 122 | 0% | $4,300,000.00 | $0.00 | $0.00 | 3041 | 2025-05-18 | 2025-10-12 | $0.00 | $0.00
T7780 | 2025-02-25 | 2025-08-03 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.2.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over [Landscape] | MJ-MSBL-INT-1.14.6.2.10 | 129 | Landscape Work | Fixed Duration & Units | 0 | 0% | 0% | 129 | 129 | 0% | $0.00 | $0.00 | $0.00 | 3412 | 2025-02-25 | 2025-08-03 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3 Secondary Infrastructure Networks | 2022-11-12 | 2028-01-27 | [7 empty] | 1586 |  |  | 0 |  | 0% | 1586 | 1586 | 0% | $60,958,777.00 | $0.00 | $0.00 | 2654 | 2022-11-12 | 2028-01-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2 MOH Beneficiaries' Units | 2022-11-12 | 2028-01-27 | [7 empty] | 1586 |  |  | 0 |  | 0% | 1586 | 1586 | 0% | $48,469,866.00 | $0.00 | $0.00 | 2654 | 2022-11-12 | 2028-01-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.19 Package (01] | 2022-11-12 | 2023-12-16 | [7 empty] | 333 |  |  | 0 |  | 0% | 333 | 333 | 0% | $10,384,577.00 | $0.00 | $0.00 | 3907 | 2022-11-12 | 2023-12-16 | $0.00 | $0.00
L2970 | 2022-11-12 | 2023-12-16 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.19 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Package 01] | MJ-MSBL-INT-1.14.6.3.2.19 | 333 | Package (01] | Fixed Duration & Units | 0 | 0% | 0% | 333 | 333 | 0% | $0.00 | $0.00 | $0.00 | 3595 | 2022-11-12 | 2023-12-16 | $0.00 | $0.00
M1720 |  | 2023-12-16 |  |  | 6.3.2.19 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Package 01] | MJ-MSBL-INT-1.14.6.3.2.19 | 0 | Package (01] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3595 |  | 2023-12-16 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.19.1 Priority 01 | 2022-11-12 | 2023-02-13 | [7 empty] | 80 |  |  | 0 |  | 0% | 80 | 80 | 0% | $2,910,320.00 | $0.00 | $0.00 | 4160 | 2022-11-12 | 2023-02-13 | $0.00 | $0.00
M1280 |  | 2023-02-13 |  |  | 6.3.2.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 01] | MJ-MSBL-INT-1.14.6.3.2.19.1 | 0 | Priority 01 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4160 |  | 2023-02-13 | $0.00 | $0.00
T7800 | 2022-11-12 | 2023-02-13 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 01] | MJ-MSBL-INT-1.14.6.3.2.19.1 | 80 | Priority 01 | Fixed Duration & Units | 0 | 0% | 0% | 80 | 80 | 0% | $2,910,320.00 | $0.00 | $0.00 | 4160 | 2022-11-12 | 2023-02-13 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.19.2 Priority 02 | 2023-02-25 | 2023-05-29 | [7 empty] | 76 |  |  | 0 |  | 0% | 76 | 76 | 0% | $5,115,431.00 | $0.00 | $0.00 | 3762 | 2023-02-25 | 2023-05-29 | $0.00 | $0.00
M1290 |  | 2023-05-29 |  |  | 6.3.2.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 02] | MJ-MSBL-INT-1.14.6.3.2.19.2 | 0 | Priority 02 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3762 |  | 2023-05-29 | $0.00 | $0.00
T7810 | 2023-02-25 | 2023-05-29 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 02] | MJ-MSBL-INT-1.14.6.3.2.19.2 | 76 | Priority 02 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $5,115,431.00 | $0.00 | $0.00 | 3762 | 2023-02-25 | 2023-05-29 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.19.4 Priority 04 | 2023-06-05 | 2023-09-06 | [7 empty] | 76 |  |  | 0 |  | 0% | 76 | 76 | 0% | $2,358,826.00 | $0.00 | $0.00 | 3680 | 2023-06-05 | 2023-09-06 | $0.00 | $0.00
M1300 |  | 2023-09-06 |  |  | 6.3.2.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 04] | MJ-MSBL-INT-1.14.6.3.2.19.4 | 0 | Priority 04 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3680 |  | 2023-09-06 | $0.00 | $0.00
T7820 | 2023-06-05 | 2023-09-06 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 04] | MJ-MSBL-INT-1.14.6.3.2.19.4 | 76 | Priority 04 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $2,358,826.00 | $0.00 | $0.00 | 3680 | 2023-06-05 | 2023-09-06 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.20 Package (02) | 2023-09-17 | 2025-07-27 | [7 empty] | 564 |  |  | 0 |  | 0% | 564 | 564 | 0% | $10,785,737.00 | $0.00 | $0.00 | 3419 | 2023-09-17 | 2025-07-27 | $0.00 | $0.00
L2570 | 2024-01-14 | 2025-07-27 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.20 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Package 02] | MJ-MSBL-INT-1.14.6.3.2.20 | 463 | Package (02) | Fixed Duration & Units | 0 | 0% | 0% | 463 | 463 | 0% | $0.00 | $0.00 | $0.00 | 3419 | 2024-01-14 | 2025-07-27 | $0.00 | $0.00
M1730 |  | 2025-07-27 |  |  | 6.3.2.20 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Package 02] | MJ-MSBL-INT-1.14.6.3.2.20 | 0 | Package (02) | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3419 |  | 2025-07-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.20.5 Priority 05 | 2023-09-17 | 2023-12-16 | [7 empty] | 76 |  |  | 0 |  | 0% | 76 | 76 | 0% | $1,445,466.00 | $0.00 | $0.00 | 3595 | 2023-09-17 | 2023-12-16 | $0.00 | $0.00
M1310 |  | 2023-12-16 |  |  | 6.3.2.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 05] | MJ-MSBL-INT-1.14.6.3.2.20.5 | 0 | Priority 05 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3595 |  | 2023-12-16 | $0.00 | $0.00
T7830 | 2023-09-17 | 2023-12-16 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 05] | MJ-MSBL-INT-1.14.6.3.2.20.5 | 76 | Priority 05 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $1,445,466.00 | $0.00 | $0.00 | 3595 | 2023-09-17 | 2023-12-16 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.20.6 Priority 07 | 2024-01-14 | 2024-03-24 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $1,921,307.00 | $0.00 | $0.00 | 3822 | 2024-01-14 | 2024-03-24 | $0.00 | $0.00
M1320 |  | 2024-03-24 |  |  | 6.3.2.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 07] | MJ-MSBL-INT-1.14.6.3.2.20.6 | 0 | Priority 07 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3822 |  | 2024-03-24 | $0.00 | $0.00
T2600 | 2024-01-14 | 2024-03-24 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 07] | MJ-MSBL-INT-1.14.6.3.2.20.6 | 60 | Priority 07 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $1,921,307.00 | $0.00 | $0.00 | 3822 | 2024-01-14 | 2024-03-24 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.20.8 Priority 08 | 2024-04-09 | 2024-06-27 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $2,765,077.00 | $0.00 | $0.00 | 3748 | 2024-04-09 | 2024-06-27 | $0.00 | $0.00
M1330 |  | 2024-06-27 |  |  | 6.3.2.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 08] | MJ-MSBL-INT-1.14.6.3.2.20.8 | 0 | Priority 08 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3748 |  | 2024-06-27 | $0.00 | $0.00
T2610 | 2024-04-09 | 2024-06-27 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 08] | MJ-MSBL-INT-1.14.6.3.2.20.8 | 60 | Priority 08 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $2,765,077.00 | $0.00 | $0.00 | 3748 | 2024-04-09 | 2024-06-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.20.7 Priority 09 | 2024-07-23 | 2024-10-02 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $1,927,150.00 | $0.00 | $0.00 | 3666 | 2024-07-23 | 2024-10-02 | $0.00 | $0.00
M1340 |  | 2024-10-02 |  |  | 6.3.2.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 09] | MJ-MSBL-INT-1.14.6.3.2.20.7 | 0 | Priority 09 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3666 |  | 2024-10-02 | $0.00 | $0.00
T2620 | 2024-07-23 | 2024-10-02 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 09] | MJ-MSBL-INT-1.14.6.3.2.20.7 | 60 | Priority 09 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $1,927,150.00 | $0.00 | $0.00 | 3666 | 2024-07-23 | 2024-10-02 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.20.10 Priority 10 | 2024-11-05 | 2025-01-14 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $2,726,737.00 | $0.00 | $0.00 | 3577 | 2024-11-05 | 2025-01-14 | $0.00 | $0.00
M1350 |  | 2025-01-14 |  |  | 6.3.2.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 10] | MJ-MSBL-INT-1.14.6.3.2.20.10 | 0 | Priority 10 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3577 |  | 2025-01-14 | $0.00 | $0.00
T2630 | 2024-11-05 | 2025-01-14 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 10] | MJ-MSBL-INT-1.14.6.3.2.20.10 | 60 | Priority 10 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $2,726,737.00 | $0.00 | $0.00 | 3577 | 2024-11-05 | 2025-01-14 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.21 Package (03) | 2025-02-16 | 2027-03-29 | [7 empty] | 639 |  |  | 0 |  | 0% | 639 | 639 | 0% | $21,464,441.00 | $0.00 | $0.00 | 2910 | 2025-02-16 | 2027-03-29 | $0.00 | $0.00
L2580 | 2025-08-24 | 2027-03-29 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.21 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Package 03] | MJ-MSBL-INT-1.14.6.3.2.21 | 485 | Package (03) | Fixed Duration & Units | 0 | 0% | 0% | 485 | 485 | 0% | $0.00 | $0.00 | $0.00 | 2910 | 2025-08-24 | 2027-03-29 | $0.00 | $0.00
M1740 |  | 2027-03-29 |  |  | 6.3.2.21 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Package 03] | MJ-MSBL-INT-1.14.6.3.2.21 | 0 | Package (03) | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2910 |  | 2027-03-29 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.21.3 Priority 11 | 2025-02-16 | 2025-05-01 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $3,135,661.00 | $0.00 | $0.00 | 3489 | 2025-02-16 | 2025-05-01 | $0.00 | $0.00
M1360 |  | 2025-05-01 |  |  | 6.3.2.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 11] | MJ-MSBL-INT-1.14.6.3.2.21.3 | 0 | Priority 11 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3489 |  | 2025-05-01 | $0.00 | $0.00
T2640 | 2025-02-16 | 2025-05-01 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 11] | MJ-MSBL-INT-1.14.6.3.2.21.3 | 60 | Priority 11 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $3,135,661.00 | $0.00 | $0.00 | 3489 | 2025-02-16 | 2025-05-01 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.21.9 Priority 13 | 2025-05-13 | 2025-07-27 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $2,433,111.00 | $0.00 | $0.00 | 3419 | 2025-05-13 | 2025-07-27 | $0.00 | $0.00
M1370 |  | 2025-07-27 |  |  | 6.3.2.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 13] | MJ-MSBL-INT-1.14.6.3.2.21.9 | 0 | Priority 13 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3419 |  | 2025-07-27 | $0.00 | $0.00
T2650 | 2025-05-13 | 2025-07-27 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 13] | MJ-MSBL-INT-1.14.6.3.2.21.9 | 60 | Priority 13 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $2,433,111.00 | $0.00 | $0.00 | 3419 | 2025-05-13 | 2025-07-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.21.11 Priority 14 | 2025-08-24 | 2025-11-03 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $4,065,690.00 | $0.00 | $0.00 | 3335 | 2025-08-24 | 2025-11-03 | $0.00 | $0.00
M1380 |  | 2025-11-03 |  |  | 6.3.2.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 14] | MJ-MSBL-INT-1.14.6.3.2.21.11 | 0 | Priority 14 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3335 |  | 2025-11-03 | $0.00 | $0.00
T2660 | 2025-08-24 | 2025-11-03 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 14] | MJ-MSBL-INT-1.14.6.3.2.21.11 | 60 | Priority 14 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $4,065,690.00 | $0.00 | $0.00 | 3335 | 2025-08-24 | 2025-11-03 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.21.12 Priority 15 | 2025-12-01 | 2026-02-09 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $1,885,396.00 | $0.00 | $0.00 | 3251 | 2025-12-01 | 2026-02-09 | $0.00 | $0.00
M1390 |  | 2026-02-09 |  |  | 6.3.2.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 15] | MJ-MSBL-INT-1.14.6.3.2.21.12 | 0 | Priority 15 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3251 |  | 2026-02-09 | $0.00 | $0.00
T2670 | 2025-12-01 | 2026-02-09 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 15] | MJ-MSBL-INT-1.14.6.3.2.21.12 | 60 | Priority 15 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $1,885,396.00 | $0.00 | $0.00 | 3251 | 2025-12-01 | 2026-02-09 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.21.13 Priority 16 | 2026-03-12 | 2026-05-25 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $9,944,583.00 | $0.00 | $0.00 | 3164 | 2026-03-12 | 2026-05-25 | $0.00 | $0.00
M1400 |  | 2026-05-25 |  |  | 6.3.2.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 16] | MJ-MSBL-INT-1.14.6.3.2.21.13 | 0 | Priority 16 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3164 |  | 2026-05-25 | $0.00 | $0.00
T2680 | 2026-03-12 | 2026-05-25 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 16] | MJ-MSBL-INT-1.14.6.3.2.21.13 | 60 | Priority 16 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $9,944,583.00 | $0.00 | $0.00 | 3164 | 2026-03-12 | 2026-05-25 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.22 Package (04) | 2026-06-27 | 2028-01-27 | [7 empty] | 487 |  |  | 0 |  | 0% | 487 | 487 | 0% | $5,835,111.00 | $0.00 | $0.00 | 2654 | 2026-06-27 | 2028-01-27 | $0.00 | $0.00
L2590 | 2027-04-27 | 2028-01-27 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.22 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Package 04] | MJ-MSBL-INT-1.14.6.3.2.22 | 231 | Package (04) | Fixed Duration & Units | 0 | 0% | 0% | 231 | 231 | 0% | $0.00 | $0.00 | $0.00 | 2654 | 2027-04-27 | 2028-01-27 | $0.00 | $0.00
M1750 |  | 2028-01-27 |  |  | 6.3.2.22 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Package 04] | MJ-MSBL-INT-1.14.6.3.2.22 | 0 | Package (04) | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2654 |  | 2028-01-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.22.14 Priority 17 | 2026-06-27 | 2026-09-05 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $2,660,451.00 | $0.00 | $0.00 | 3081 | 2026-06-27 | 2026-09-05 | $0.00 | $0.00
M1410 |  | 2026-09-05 |  |  | 6.3.2.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 17] | MJ-MSBL-INT-1.14.6.3.2.22.14 | 0 | Priority 17 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3081 |  | 2026-09-05 | $0.00 | $0.00
T2690 | 2026-06-27 | 2026-09-05 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 17] | MJ-MSBL-INT-1.14.6.3.2.22.14 | 60 | Priority 17 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $2,660,451.00 | $0.00 | $0.00 | 3081 | 2026-06-27 | 2026-09-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.2.22.15 Priority 18 | 2026-10-05 | 2026-12-14 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $3,174,660.00 | $0.00 | $0.00 | 2996 | 2026-10-05 | 2026-12-14 | $0.00 | $0.00
M1420 |  | 2026-12-14 |  |  | 6.3.2.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 18] | MJ-MSBL-INT-1.14.6.3.2.22.15 | 0 | Priority 18 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2996 |  | 2026-12-14 | $0.00 | $0.00
T2700 | 2026-10-05 | 2026-12-14 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.2.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 18] | MJ-MSBL-INT-1.14.6.3.2.22.15 | 60 | Priority 18 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $3,174,660.00 | $0.00 | $0.00 | 2996 | 2026-10-05 | 2026-12-14 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.3 Other Beneficiaries' Units | 2027-01-13 | 2028-01-27 | [7 empty] | 316 |  |  | 0 |  | 0% | 316 | 316 | 0% | $12,488,911.00 | $0.00 | $0.00 | 2654 | 2027-01-13 | 2028-01-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.3.1 Packages (01,02,03,04) | 2027-01-13 | 2028-01-27 | [7 empty] | 316 |  |  | 0 |  | 0% | 316 | 316 | 0% | $12,488,911.00 | $0.00 | $0.00 | 2654 | 2027-01-13 | 2028-01-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.3.1.16 Priority 03 | 2027-01-13 | 2027-03-29 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $2,755,912.00 | $0.00 | $0.00 | 2910 | 2027-01-13 | 2027-03-29 | $0.00 | $0.00
M1430 |  | 2027-03-29 |  |  | 6.3.3.1.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 03] | MJ-MSBL-INT-1.14.6.3.3.1.16 | 0 | Priority 03 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2910 |  | 2027-03-29 | $0.00 | $0.00
T2710 | 2027-01-13 | 2027-03-29 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.3.1.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 03] | MJ-MSBL-INT-1.14.6.3.3.1.16 | 60 | Priority 03 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $2,755,912.00 | $0.00 | $0.00 | 2910 | 2027-01-13 | 2027-03-29 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.3.1.17 Priority 06 | 2027-04-27 | 2027-07-11 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $2,639,690.00 | $0.00 | $0.00 | 2825 | 2027-04-27 | 2027-07-11 | $0.00 | $0.00
M1440 |  | 2027-07-11 |  |  | 6.3.3.1.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 067] | MJ-MSBL-INT-1.14.6.3.3.1.17 | 0 | Priority 06 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2825 |  | 2027-07-11 | $0.00 | $0.00
T2720 | 2027-04-27 | 2027-07-11 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.3.1.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 06] | MJ-MSBL-INT-1.14.6.3.3.1.17 | 60 | Priority 06 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $2,639,690.00 | $0.00 | $0.00 | 2825 | 2027-04-27 | 2027-07-11 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.3.1.18 Priority 12 | 2027-08-09 | 2027-10-19 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $2,876,390.00 | $0.00 | $0.00 | 2740 | 2027-08-09 | 2027-10-19 | $0.00 | $0.00
M1450 |  | 2027-10-19 |  |  | 6.3.3.1.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 12 | MJ-MSBL-INT-1.14.6.3.3.1.18 | 0 | Priority 12 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2740 |  | 2027-10-19 | $0.00 | $0.00
T2730 | 2027-08-09 | 2027-10-19 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.3.1.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 12] | MJ-MSBL-INT-1.14.6.3.3.1.18 | 60 | Priority 12 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $2,876,390.00 | $0.00 | $0.00 | 2740 | 2027-08-09 | 2027-10-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.3.3.1.1 Priority 19 | 2027-11-18 | 2028-01-27 | [7 empty] | 60 |  |  | 0 |  | 0% | 60 | 60 | 0% | $4,216,919.00 | $0.00 | $0.00 | 2654 | 2027-11-18 | 2028-01-27 | $0.00 | $0.00
M12810 |  | 2028-01-27 |  |  | 6.3.3.1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 19] | MJ-MSBL-INT-1.14.6.3.3.1.1 | 0 | Priority 19 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2654 |  | 2028-01-27 | $0.00 | $0.00
T3220 | 2027-11-18 | 2028-01-27 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.3.3.1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Secondary Networks [Priority 19] | MJ-MSBL-INT-1.14.6.3.3.1.1 | 60 | Priority 19 | Fixed Duration & Units | 0 | 0% | 0% | 60 | 60 | 0% | $4,216,919.00 | $0.00 | $0.00 | 2654 | 2027-11-18 | 2028-01-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11 Superstructure Work | 2023-04-30 | 1930-03-19 | [7 empty] | 2094 |  |  | 0 |  | 0% | 2094 | 2094 | 0% | $644,435,550.00 | $0.00 | $0.00 | 2005 | 2023-04-30 | 1930-03-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2 MOH Beneficiaries' Units | 2023-04-30 | 2028-10-28 | [7 empty] | 1672 |  |  | 0 |  | 0% | 1672 | 1672 | 0% | $533,220,270.00 | $0.00 | $0.00 | 2427 | 2023-04-30 | 2028-10-28 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.19 Package (01] | 2023-04-30 | 2025-04-24 | [7 empty] | 605 |  |  | 0 |  | 0% | 605 | 605 | 0% | $97,579,020.00 | $0.00 | $0.00 | 3494 | 2023-04-30 | 2025-04-24 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.19.1 Priority 01 | 2023-04-30 | 2025-04-24 | [7 empty] | 605 |  |  | 0 |  | 0% | 605 | 605 | 0% | $28,952,880.00 | $0.00 | $0.00 | 3494 | 2023-04-30 | 2025-04-24 | $0.00 | $0.00
M12830 |  | 2025-04-24 |  |  | 6.11.2.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 01] | MJ-MSBL-INT-1.14.6.11.2.19.1 | 0 | Priority 01 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3494 |  | 2025-04-24 | $0.00 | $0.00
M1460 |  | 2023-07-31 |  |  | 6.11.2.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 01] | MJ-MSBL-INT-1.14.6.11.2.19.1 | 0 | Priority 01 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 4023 |  | 2023-07-31 | $0.00 | $0.00
T2740 | 2023-04-30 | 2023-07-31 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 01] | MJ-MSBL-INT-1.14.6.11.2.19.1 | 76 | Priority 01 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $28,952,880.00 | $0.00 | $0.00 | 3997 | 2023-04-30 | 2023-07-31 | $0.00 | $0.00
T3240 | 2025-01-22 | 2025-04-24 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.19.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 01] | MJ-MSBL-INT-1.14.6.11.2.19.1 | 76 | Priority 01 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $0.00 | $0.00 | $0.00 | 3494 | 2025-01-22 | 2025-04-24 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.19.2 Priority 02 | 2023-09-24 | 2025-04-24 | [7 empty] | 484 |  |  | 0 |  | 0% | 484 | 484 | 0% | $40,204,560.00 | $0.00 | $0.00 | 3494 | 2023-09-24 | 2025-04-24 | $0.00 | $0.00
M12840 |  | 2025-04-24 |  |  | 6.11.2.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 02] | MJ-MSBL-INT-1.14.6.11.2.19.2 | 0 | Priority 02 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3494 |  | 2025-04-24 | $0.00 | $0.00
M1470 |  | 2023-12-16 |  |  | 6.11.2.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 02] | MJ-MSBL-INT-1.14.6.11.2.19.2 | 0 | Priority 02 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3906 |  | 2023-12-16 | $0.00 | $0.00
T2750 | 2023-09-24 | 2023-12-16 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 02] | MJ-MSBL-INT-1.14.6.11.2.19.2 | 72 | Priority 02 | Fixed Duration & Units | 0 | 0% | 0% | 72 | 72 | 0% | $40,204,560.00 | $0.00 | $0.00 | 3884 | 2023-09-24 | 2023-12-16 | $0.00 | $0.00
T3250 | 2023-10-24 | 2024-01-10 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.19.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 02] | MJ-MSBL-INT-1.14.6.11.2.19.2 | 68 | Priority 02 | Fixed Duration & Units | 0 | 0% | 0% | 68 | 68 | 0% | $0.00 | $0.00 | $0.00 | 3884 | 2023-10-24 | 2024-01-10 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.19.4 Priority 04 | 2024-02-08 | 2025-04-24 | [7 empty] | 366 |  |  | 0 |  | 0% | 366 | 366 | 0% | $28,421,580.00 | $0.00 | $0.00 | 3494 | 2024-02-08 | 2025-04-24 | $0.00 | $0.00
M12850 |  | 2025-04-24 |  |  | 6.11.2.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 04] | MJ-MSBL-INT-1.14.6.11.2.19.4 | 0 | Priority 04 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3494 |  | 2025-04-24 | $0.00 | $0.00
M1480 |  | 2024-05-11 |  |  | 6.11.2.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 04] | MJ-MSBL-INT-1.14.6.11.2.19.4 | 0 | Priority 04 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3784 |  | 2024-05-11 | $0.00 | $0.00
T2760 | 2024-02-08 | 2024-05-11 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 04] | MJ-MSBL-INT-1.14.6.11.2.19.4 | 76 | Priority 04 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $28,421,580.00 | $0.00 | $0.00 | 3762 | 2024-02-08 | 2024-05-11 | $0.00 | $0.00
T3260 | 2024-03-10 | 2024-06-05 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.19.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 04] | MJ-MSBL-INT-1.14.6.11.2.19.4 | 72 | Priority 04 | Fixed Duration & Units | 0 | 0% | 0% | 72 | 72 | 0% | $0.00 | $0.00 | $0.00 | 3762 | 2024-03-10 | 2024-06-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.20 Package (02) | 2024-07-04 | 2026-05-12 | [7 empty] | 567 |  |  | 0 |  | 0% | 567 | 567 | 0% | $128,894,040.00 | $0.00 | $0.00 | 3175 | 2024-07-04 | 2026-05-12 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.20.5 Priority 05 | 2024-07-04 | 2025-04-24 | [7 empty] | 248 |  |  | 0 |  | 0% | 248 | 248 | 0% | $14,536,830.00 | $0.00 | $0.00 | 3494 | 2024-07-04 | 2025-04-24 | $0.00 | $0.00
M12860 |  | 2025-04-24 |  |  | 6.11.2.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 05] | MJ-MSBL-INT-1.14.6.11.2.20.5 | 0 | Priority 05 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3494 |  | 2025-04-24 | $0.00 | $0.00
M1490 |  | 2024-10-01 |  |  | 6.11.2.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 05] | MJ-MSBL-INT-1.14.6.11.2.20.5 | 0 | Priority 05 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3666 |  | 2024-10-01 | $0.00 | $0.00
T2770 | 2024-07-04 | 2024-10-01 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 05] | MJ-MSBL-INT-1.14.6.11.2.20.5 | 76 | Priority 05 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $14,536,830.00 | $0.00 | $0.00 | 3640 | 2024-07-04 | 2024-10-01 | $0.00 | $0.00
T3270 | 2024-08-04 | 2024-10-31 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.20.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 05] | MJ-MSBL-INT-1.14.6.11.2.20.5 | 76 | Priority 05 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $0.00 | $0.00 | $0.00 | 3640 | 2024-08-04 | 2024-10-31 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.20.6 Priority 07 | 2024-11-20 | 2025-04-24 | [7 empty] | 130 |  |  | 0 |  | 0% | 130 | 130 | 0% | $22,216,590.00 | $0.00 | $0.00 | 3494 | 2024-11-20 | 2025-04-24 | $0.00 | $0.00
M12870 |  | 2025-04-24 |  |  | 6.11.2.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 07] | MJ-MSBL-INT-1.14.6.11.2.20.6 | 0 | Priority 07 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3494 |  | 2025-04-24 | $0.00 | $0.00
M1500 |  | 2025-02-16 |  |  | 6.11.2.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 07] | MJ-MSBL-INT-1.14.6.11.2.20.6 | 0 | Priority 07 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3548 |  | 2025-02-16 | $0.00 | $0.00
T2780 | 2024-11-20 | 2025-02-16 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 07] | MJ-MSBL-INT-1.14.6.11.2.20.6 | 76 | Priority 07 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $22,216,590.00 | $0.00 | $0.00 | 3526 | 2024-11-20 | 2025-02-16 | $0.00 | $0.00
T3280 | 2024-12-21 | 2025-03-13 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.20.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 07] | MJ-MSBL-INT-1.14.6.11.2.20.6 | 72 | Priority 07 | Fixed Duration & Units | 0 | 0% | 0% | 72 | 72 | 0% | $0.00 | $0.00 | $0.00 | 3526 | 2024-12-21 | 2025-03-13 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.20.8 Priority 08 | 2025-04-09 | 2025-08-09 | [7 empty] | 101 |  |  | 0 |  | 0% | 101 | 101 | 0% | $36,019,500.00 | $0.00 | $0.00 | 3407 | 2025-04-09 | 2025-08-09 | $0.00 | $0.00
M12880 |  | 2025-08-09 |  |  | 6.11.2.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 08] | MJ-MSBL-INT-1.14.6.11.2.20.8 | 0 | Priority 08 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3407 |  | 2025-08-09 | $0.00 | $0.00
M1510 |  | 2025-07-10 |  |  | 6.11.2.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 08] | MJ-MSBL-INT-1.14.6.11.2.20.8 | 0 | Priority 08 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3432 |  | 2025-07-10 | $0.00 | $0.00
T2790 | 2025-04-09 | 2025-07-10 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 08] | MJ-MSBL-INT-1.14.6.11.2.20.8 | 76 | Priority 08 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $36,019,500.00 | $0.00 | $0.00 | 3407 | 2025-04-09 | 2025-07-10 | $0.00 | $0.00
T3290 | 2025-05-10 | 2025-08-09 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.20.8 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 08] | MJ-MSBL-INT-1.14.6.11.2.20.8 | 75 | Priority 08 | Fixed Duration & Units | 0 | 0% | 0% | 75 | 75 | 0% | $0.00 | $0.00 | $0.00 | 3407 | 2025-05-10 | 2025-08-09 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.20.7 Priority 09 | 2025-08-30 | 2025-12-22 | [7 empty] | 98 |  |  | 0 |  | 0% | 98 | 98 | 0% | $24,373,470.00 | $0.00 | $0.00 | 3292 | 2025-08-30 | 2025-12-22 | $0.00 | $0.00
M12890 |  | 2025-12-22 |  |  | 6.11.2.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 09] | MJ-MSBL-INT-1.14.6.11.2.20.7 | 0 | Priority 09 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3292 |  | 2025-12-22 | $0.00 | $0.00
M1520 |  | 2025-11-26 |  |  | 6.11.2.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 09] | MJ-MSBL-INT-1.14.6.11.2.20.7 | 0 | Priority 09 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3314 |  | 2025-11-26 | $0.00 | $0.00
T2800 | 2025-08-30 | 2025-11-26 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 09] | MJ-MSBL-INT-1.14.6.11.2.20.7 | 76 | Priority 09 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $24,373,470.00 | $0.00 | $0.00 | 3292 | 2025-08-30 | 2025-11-26 | $0.00 | $0.00
T3300 | 2025-09-30 | 2025-12-22 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.20.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 09] | MJ-MSBL-INT-1.14.6.11.2.20.7 | 72 | Priority 09 | Fixed Duration & Units | 0 | 0% | 0% | 72 | 72 | 0% | $0.00 | $0.00 | $0.00 | 3292 | 2025-09-30 | 2025-12-22 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.20.10 Priority 10 | 2026-01-14 | 2026-05-12 | [7 empty] | 98 |  |  | 0 |  | 0% | 98 | 98 | 0% | $31,747,650.00 | $0.00 | $0.00 | 3175 | 2026-01-14 | 2026-05-12 | $0.00 | $0.00
M12900 |  | 2026-05-12 |  |  | 6.11.2.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 10] | MJ-MSBL-INT-1.14.6.11.2.20.10 | 0 | Priority 10 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3175 |  | 2026-05-12 | $0.00 | $0.00
M1530 |  | 2026-04-16 |  |  | 6.11.2.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 10] | MJ-MSBL-INT-1.14.6.11.2.20.10 | 0 | Priority 10 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3197 |  | 2026-04-16 | $0.00 | $0.00
T2810 | 2026-01-14 | 2026-04-16 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 10] | MJ-MSBL-INT-1.14.6.11.2.20.10 | 76 | Priority 10 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $31,747,650.00 | $0.00 | $0.00 | 3175 | 2026-01-14 | 2026-04-16 | $0.00 | $0.00
T3310 | 2026-02-14 | 2026-05-12 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.20.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 10] | MJ-MSBL-INT-1.14.6.11.2.20.10 | 72 | Priority 10 | Fixed Duration & Units | 0 | 0% | 0% | 72 | 72 | 0% | $0.00 | $0.00 | $0.00 | 3175 | 2026-02-14 | 2026-05-12 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.21 Package (03) | 2026-06-08 | 2028-01-11 | [7 empty] | 490 |  |  | 0 |  | 0% | 490 | 490 | 0% | $246,455,880.00 | $0.00 | $0.00 | 2667 | 2026-06-08 | 2028-01-11 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.21.3 Priority 11 | 2026-06-08 | 2026-10-05 | [7 empty] | 102 |  |  | 0 |  | 0% | 102 | 102 | 0% | $34,245,090.00 | $0.00 | $0.00 | 3055 | 2026-06-08 | 2026-10-05 | $0.00 | $0.00
M12910 |  | 2026-10-05 |  |  | 6.11.2.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 11] | MJ-MSBL-INT-1.14.6.11.2.21.3 | 0 | Priority 11 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3055 |  | 2026-10-05 | $0.00 | $0.00
M1540 |  | 2026-09-03 |  |  | 6.11.2.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 11] | MJ-MSBL-INT-1.14.6.11.2.21.3 | 0 | Priority 11 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3081 |  | 2026-09-03 | $0.00 | $0.00
T2820 | 2026-06-08 | 2026-09-03 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 11] | MJ-MSBL-INT-1.14.6.11.2.21.3 | 76 | Priority 11 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $34,245,090.00 | $0.00 | $0.00 | 3055 | 2026-06-08 | 2026-09-03 | $0.00 | $0.00
T3320 | 2026-07-08 | 2026-10-05 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.21.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 11] | MJ-MSBL-INT-1.14.6.11.2.21.3 | 76 | Priority 11 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $0.00 | $0.00 | $0.00 | 3055 | 2026-07-08 | 2026-10-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.21.9 Priority 13 | 2026-10-25 | 2027-02-15 | [7 empty] | 98 |  |  | 0 |  | 0% | 98 | 98 | 0% | $29,848,830.00 | $0.00 | $0.00 | 2941 | 2026-10-25 | 2027-02-15 | $0.00 | $0.00
M12920 |  | 2027-02-15 |  |  | 6.11.2.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 13] | MJ-MSBL-INT-1.14.6.11.2.21.9 | 0 | Priority 13 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2941 |  | 2027-02-15 | $0.00 | $0.00
M1550 |  | 2027-01-20 |  |  | 6.11.2.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 13] | MJ-MSBL-INT-1.14.6.11.2.21.9 | 0 | Priority 13 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2963 |  | 2027-01-20 | $0.00 | $0.00
T2830 | 2026-10-25 | 2027-01-20 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 13] | MJ-MSBL-INT-1.14.6.11.2.21.9 | 76 | Priority 13 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $29,848,830.00 | $0.00 | $0.00 | 2941 | 2026-10-25 | 2027-01-20 | $0.00 | $0.00
T3330 | 2026-11-24 | 2027-02-15 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.21.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 13] | MJ-MSBL-INT-1.14.6.11.2.21.9 | 72 | Priority 13 | Fixed Duration & Units | 0 | 0% | 0% | 72 | 72 | 0% | $0.00 | $0.00 | $0.00 | 2941 | 2026-11-24 | 2027-02-15 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.21.11 Priority 14 | 2027-01-24 | 2027-05-29 | [7 empty] | 100 |  |  | 0 |  | 0% | 100 | 100 | 0% | $47,583,360.00 | $0.00 | $0.00 | 2861 | 2027-01-24 | 2027-05-29 | $0.00 | $0.00
M12930 |  | 2027-05-29 |  |  | 6.11.2.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 14] | MJ-MSBL-INT-1.14.6.11.2.21.11 | 0 | Priority 14 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2861 |  | 2027-05-29 | $0.00 | $0.00
M1560 |  | 2027-04-26 |  |  | 6.11.2.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 14] | MJ-MSBL-INT-1.14.6.11.2.21.11 | 0 | Priority 14 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2885 |  | 2027-04-26 | $0.00 | $0.00
T2840 | 2027-01-24 | 2027-04-26 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 14] | MJ-MSBL-INT-1.14.6.11.2.21.11 | 76 | Priority 14 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $47,583,360.00 | $0.00 | $0.00 | 2861 | 2027-01-24 | 2027-04-26 | $0.00 | $0.00
T3340 | 2027-02-23 | 2027-05-29 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.21.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 14] | MJ-MSBL-INT-1.14.6.11.2.21.11 | 74 | Priority 14 | Fixed Duration & Units | 0 | 0% | 0% | 74 | 74 | 0% | $0.00 | $0.00 | $0.00 | 2861 | 2027-02-23 | 2027-05-29 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.21.12 Priority 15 | 2027-04-29 | 2027-08-29 | [7 empty] | 101 |  |  | 0 |  | 0% | 101 | 101 | 0% | $21,275,760.00 | $0.00 | $0.00 | 2782 | 2027-04-29 | 2027-08-29 | $0.00 | $0.00
M12940 |  | 2027-08-29 |  |  | 6.11.2.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 15] | MJ-MSBL-INT-1.14.6.11.2.21.12 | 0 | Priority 15 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2782 |  | 2027-08-29 | $0.00 | $0.00
M1570 |  | 2027-07-31 |  |  | 6.11.2.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 15] | MJ-MSBL-INT-1.14.6.11.2.21.12 | 0 | Priority 15 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2807 |  | 2027-07-31 | $0.00 | $0.00
T2850 | 2027-04-29 | 2027-07-31 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 15] | MJ-MSBL-INT-1.14.6.11.2.21.12 | 76 | Priority 15 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $21,275,760.00 | $0.00 | $0.00 | 2782 | 2027-04-29 | 2027-07-31 | $0.00 | $0.00
T3350 | 2027-06-03 | 2027-08-29 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.21.12 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 15] | MJ-MSBL-INT-1.14.6.11.2.21.12 | 75 | Priority 15 | Fixed Duration & Units | 0 | 0% | 0% | 75 | 75 | 0% | $0.00 | $0.00 | $0.00 | 2782 | 2027-06-03 | 2027-08-29 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.21.13 Priority 16 | 2027-09-19 | 2028-01-11 | [7 empty] | 98 |  |  | 0 |  | 0% | 98 | 98 | 0% | $113,502,840.00 | $0.00 | $0.00 | 2667 | 2027-09-19 | 2028-01-11 | $0.00 | $0.00
M12950 |  | 2028-01-11 |  |  | 6.11.2.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 16] | MJ-MSBL-INT-1.14.6.11.2.21.13 | 0 | Priority 16 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2667 |  | 2028-01-11 | $0.00 | $0.00
M1580 |  | 2027-12-16 |  |  | 6.11.2.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 16] | MJ-MSBL-INT-1.14.6.11.2.21.13 | 0 | Priority 16 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2689 |  | 2027-12-16 | $0.00 | $0.00
T2860 | 2027-09-19 | 2027-12-16 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 16] | MJ-MSBL-INT-1.14.6.11.2.21.13 | 76 | Priority 16 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $113,502,840.00 | $0.00 | $0.00 | 2667 | 2027-09-19 | 2027-12-16 | $0.00 | $0.00
T3360 | 2027-10-20 | 2028-01-11 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.21.13 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 16] | MJ-MSBL-INT-1.14.6.11.2.21.13 | 72 | Priority 16 | Fixed Duration & Units | 0 | 0% | 0% | 72 | 72 | 0% | $0.00 | $0.00 | $0.00 | 2667 | 2027-10-20 | 2028-01-11 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.22 Package (04) | 2028-02-05 | 2028-10-28 | [7 empty] | 220 |  |  | 0 |  | 0% | 220 | 220 | 0% | $60,291,330.00 | $0.00 | $0.00 | 2427 | 2028-02-05 | 2028-10-28 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.22.14 Priority 17 | 2028-02-05 | 2028-06-11 | [7 empty] | 102 |  |  | 0 |  | 0% | 102 | 102 | 0% | $24,861,210.00 | $0.00 | $0.00 | 2545 | 2028-02-05 | 2028-06-11 | $0.00 | $0.00
M12960 |  | 2028-06-11 |  |  | 6.11.2.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 17] | MJ-MSBL-INT-1.14.6.11.2.22.14 | 0 | Priority 17 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2545 |  | 2028-06-11 | $0.00 | $0.00
M1590 |  | 2028-05-11 |  |  | 6.11.2.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 17] | MJ-MSBL-INT-1.14.6.11.2.22.14 | 0 | Priority 17 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2571 |  | 2028-05-11 | $0.00 | $0.00
T2870 | 2028-02-05 | 2028-05-11 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 17] | MJ-MSBL-INT-1.14.6.11.2.22.14 | 76 | Priority 17 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $24,861,210.00 | $0.00 | $0.00 | 2545 | 2028-02-05 | 2028-05-11 | $0.00 | $0.00
T3370 | 2028-03-11 | 2028-06-11 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.22.14 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 17] | MJ-MSBL-INT-1.14.6.11.2.22.14 | 76 | Priority 17 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $0.00 | $0.00 | $0.00 | 2545 | 2028-03-11 | 2028-06-11 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.2.22.15 Priority 18 | 2028-07-01 | 2028-10-28 | [7 empty] | 102 |  |  | 0 |  | 0% | 102 | 102 | 0% | $35,430,120.00 | $0.00 | $0.00 | 2427 | 2028-07-01 | 2028-10-28 | $0.00 | $0.00
M12970 |  | 2028-10-28 |  |  | 6.11.2.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 18] | MJ-MSBL-INT-1.14.6.11.2.22.15 | 0 | Priority 18 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2427 |  | 2028-10-28 | $0.00 | $0.00
M1600 |  | 2028-09-27 |  |  | 6.11.2.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 18] | MJ-MSBL-INT-1.14.6.11.2.22.15 | 0 | Priority 18 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2453 |  | 2028-09-27 | $0.00 | $0.00
T2880 | 2028-07-01 | 2028-09-27 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 18] | MJ-MSBL-INT-1.14.6.11.2.22.15 | 76 | Priority 18 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $35,430,120.00 | $0.00 | $0.00 | 2427 | 2028-07-01 | 2028-09-27 | $0.00 | $0.00
T3380 | 2028-07-31 | 2028-10-28 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.2.22.15 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 18] | MJ-MSBL-INT-1.14.6.11.2.22.15 | 76 | Priority 18 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $0.00 | $0.00 | $0.00 | 2427 | 2028-07-31 | 2028-10-28 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.3 Other Beneficiaries' Units | 2028-11-15 | 1930-03-19 | [7 empty] | 407 |  |  | 0 |  | 0% | 407 | 407 | 0% | $111,215,280.00 | $0.00 | $0.00 | 2005 | 2028-11-15 | 1930-03-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.3.1 Packages (01,02,03,04) | 2028-11-15 | 1930-03-19 | [7 empty] | 407 |  |  | 0 |  | 0% | 407 | 407 | 0% | $111,215,280.00 | $0.00 | $0.00 | 2005 | 2028-11-15 | 1930-03-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.3.1.16 Priority 03 | 2028-11-15 | 2029-03-13 | [7 empty] | 98 |  |  | 0 |  | 0% | 98 | 98 | 0% | $21,897,810.00 | $0.00 | $0.00 | 2314 | 2028-11-15 | 2029-03-13 | $0.00 | $0.00
M12980 |  | 2029-03-13 |  |  | 6.11.3.1.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 03] | MJ-MSBL-INT-1.14.6.11.3.1.16 | 0 | Priority 03 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2314 |  | 2029-03-13 | $0.00 | $0.00
M1610 |  | 2029-02-11 |  |  | 6.11.3.1.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 03] | MJ-MSBL-INT-1.14.6.11.3.1.16 | 0 | Priority 03 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2336 |  | 2029-02-11 | $0.00 | $0.00
T2890 | 2028-11-15 | 2029-02-11 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.3.1.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 03] | MJ-MSBL-INT-1.14.6.11.3.1.16 | 76 | Priority 03 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $21,897,810.00 | $0.00 | $0.00 | 2314 | 2028-11-15 | 2029-02-11 | $0.00 | $0.00
T3390 | 2028-12-16 | 2029-03-13 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.3.1.16 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 03] | MJ-MSBL-INT-1.14.6.11.3.1.16 | 72 | Priority 03 | Fixed Duration & Units | 0 | 0% | 0% | 72 | 72 | 0% | $0.00 | $0.00 | $0.00 | 2314 | 2028-12-16 | 2029-03-13 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.3.1.17 Priority 06 | 2029-04-05 | 2029-08-05 | [7 empty] | 101 |  |  | 0 |  | 0% | 101 | 101 | 0% | $25,344,990.00 | $0.00 | $0.00 | 2194 | 2029-04-05 | 2029-08-05 | $0.00 | $0.00
M12990 |  | 2029-08-05 |  |  | 6.11.3.1.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 06] | MJ-MSBL-INT-1.14.6.11.3.1.17 | 0 | Priority 06 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2194 |  | 2029-08-05 | $0.00 | $0.00
M1620 |  | 2029-07-07 |  |  | 6.11.3.1.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 06] | MJ-MSBL-INT-1.14.6.11.3.1.17 | 0 | Priority 06 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2219 |  | 2029-07-07 | $0.00 | $0.00
T2900 | 2029-04-05 | 2029-07-07 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.3.1.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 06] | MJ-MSBL-INT-1.14.6.11.3.1.17 | 76 | Priority 06 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $25,344,990.00 | $0.00 | $0.00 | 2194 | 2029-04-05 | 2029-07-07 | $0.00 | $0.00
T3400 | 2029-05-10 | 2029-08-05 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.3.1.17 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 06] | MJ-MSBL-INT-1.14.6.11.3.1.17 | 75 | Priority 06 | Fixed Duration & Units | 0 | 0% | 0% | 75 | 75 | 0% | $0.00 | $0.00 | $0.00 | 2194 | 2029-05-10 | 2029-08-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.3.1.18 Priority 12 | 2029-09-09 | 1930-01-01 | [7 empty] | 98 |  |  | 0 |  | 0% | 98 | 98 | 0% | $35,734,380.00 | $0.00 | $0.00 | 2067 | 2029-09-09 | 1930-01-01 | $0.00 | $0.00
M1240 |  | 2029-12-06 |  |  | 6.11.3.1.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 12] | MJ-MSBL-INT-1.14.6.11.3.1.18 | 0 | Priority 12 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2089 |  | 2029-12-06 | $0.00 | $0.00
M13000 |  | 1930-01-01 |  |  | 6.11.3.1.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 12] | MJ-MSBL-INT-1.14.6.11.3.1.18 | 0 | Priority 12 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2067 |  | 1930-01-01 | $0.00 | $0.00
T2500 | 2029-09-09 | 2029-12-06 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.3.1.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 12] | MJ-MSBL-INT-1.14.6.11.3.1.18 | 76 | Priority 12 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $35,734,380.00 | $0.00 | $0.00 | 63 | 2029-09-09 | 2029-12-06 | $0.00 | $0.00
T3410 | 2029-10-10 | 1930-01-01 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.3.1.18 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 12] | MJ-MSBL-INT-1.14.6.11.3.1.18 | 72 | Priority 12 | Fixed Duration & Units | 0 | 0% | 0% | 72 | 72 | 0% | $0.00 | $0.00 | $0.00 | 2067 | 2029-10-10 | 1930-01-01 | $0.00 | $0.00
MJ-MSBL-INT-1.14.6.11.3.1.1 Priority 19 | 2029-11-21 | 1930-03-19 | [7 empty] | 98 |  |  | 0 |  | 0% | 98 | 98 | 0% | $28,238,100.00 | $0.00 | $0.00 | 2005 | 2029-11-21 | 1930-03-19 | $0.00 | $0.00
M12820 |  | 1930-02-21 |  |  | 6.11.3.1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish I.H.O. [Priority 19] | MJ-MSBL-INT-1.14.6.11.3.1.1 | 0 | Priority 19 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2027 |  | 1930-02-21 | $0.00 | $0.00
M13010 |  | 1930-03-19 |  |  | 6.11.3.1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish Clients T.O. [Priority 19] | MJ-MSBL-INT-1.14.6.11.3.1.1 | 0 | Priority 19 | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2005 |  | 1930-03-19 | $0.00 | $0.00
T3230 | 2029-11-21 | 1930-02-21 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.3.1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Initial Handing Over for Superstructure [Priority 19] | MJ-MSBL-INT-1.14.6.11.3.1.1 | 76 | Priority 19 | Fixed Duration & Units | 0 | 0% | 0% | 76 | 76 | 0% | $28,238,100.00 | $0.00 | $0.00 | 1 | 2029-11-21 | 1930-02-21 | $0.00 | $0.00
T3420 | 2029-12-22 | 1930-03-19 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 6.11.3.1.1 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Clients Taking Over for Superstructure [Priority 19] | MJ-MSBL-INT-1.14.6.11.3.1.1 | 72 | Priority 19 | Fixed Duration & Units | 0 | 0% | 0% | 72 | 72 | 0% | $0.00 | $0.00 | $0.00 | 2005 | 2029-12-22 | 1930-03-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9 Maintenance Phase & Final Handing Over | 2021-11-25 | 1931-02-02 | [7 empty] | 2877 |  |  | 0 |  | 0% | 2877 | 2877 | 0% | $0.00 | $0.00 | $0.00 | 1736 | 2021-11-25 | 1931-02-02 | $0.00 | $0.00
L2540 | 2021-11-25 | 1930-03-19 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Defects Liability Period | MJ-MSBL-INT-1.14.9 | 2527 | Maintenance Phase & Final Handing Over | Fixed Duration & Units | 0 | 0% | 0% | 2527 | 2527 | 0% | $0.00 | $0.00 | $0.00 | 2005 | 2021-11-25 | 1930-03-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.9 Main Infrastructure Networks, Roads & Landscape | 2023-05-31 | 1930-03-19 | [7 empty] | 2067 |  |  | 0 |  | 0% | 2067 | 2067 | 0% | $0.00 | $0.00 | $0.00 | 2005 | 2023-05-31 | 1930-03-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.9.2 Main Infrastructure Networks, Roads & Culverts | 2024-03-02 | 1930-03-19 | [7 empty] | 1836 |  |  | 0 |  | 0% | 1836 | 1836 | 0% | $0.00 | $0.00 | $0.00 | 2005 | 2024-03-02 | 1930-03-19 | $0.00 | $0.00
L3140 | 2024-03-02 | 1930-03-19 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 9.9.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Defects Liability Period [M. Infra] | MJ-MSBL-INT-1.14.9.9.2 | 1836 | Main Infrastructure Networks, Roads & Culverts | Fixed Duration & Units | 0 | 0% | 0% | 1836 | 1836 | 0% | $0.00 | $0.00 | $0.00 | 2005 | 2024-03-02 | 1930-03-19 | $0.00 | $0.00
M3170 | 2024-03-02 |  |  |  | 9.9.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start DLP [M. Inf.] | MJ-MSBL-INT-1.14.9.9.2 | 0 | Main Infrastructure Networks, Roads & Culverts | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3529 | 2024-03-02 |  | $0.00 | $0.00
M3180 |  | 2025-03-10 |  |  | 9.9.2 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish DLP [M. Inf.] | MJ-MSBL-INT-1.14.9.9.2 | 0 | Main Infrastructure Networks, Roads & Culverts | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3529 |  | 2025-03-10 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.9.4 Concrete Structures (Northern Entrances) | 2023-05-31 | 2024-06-08 | [7 empty] | 312 |  |  | 0 |  | 0% | 312 | 312 | 0% | $0.00 | $0.00 | $0.00 | 3760 | 2023-05-31 | 2024-06-08 | $0.00 | $0.00
L7090 | 2023-05-31 | 2024-06-08 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 9.9.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Defects Liability Period [Concrete Structures (N. Entrances)] | MJ-MSBL-INT-1.14.9.9.4 | 312 | Concrete Structures (Northern Entrances) | Fixed Duration & Units | 0 | 0% | 0% | 312 | 312 | 0% | $0.00 | $0.00 | $0.00 | 3760 | 2023-05-31 | 2024-06-08 | $0.00 | $0.00
M13570 | 2023-05-31 |  |  |  | 9.9.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start DLP [Concrete Structures (N. Entrances)] | MJ-MSBL-INT-1.14.9.9.4 | 0 | Concrete Structures (Northern Entrances) | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3760 | 2023-05-31 |  | $0.00 | $0.00
M13580 |  | 2024-06-08 |  |  | 9.9.4 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish DLP [Concrete Structures (N. Entrances)] | MJ-MSBL-INT-1.14.9.9.4 | 0 | Concrete Structures (Northern Entrances) | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3760 |  | 2024-06-08 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.9.5 HV Substations | 2023-05-31 | 1930-03-19 | [7 empty] | 2067 |  |  | 0 |  | 0% | 2067 | 2067 | 0% | $0.00 | $0.00 | $0.00 | 2005 | 2023-05-31 | 1930-03-19 | $0.00 | $0.00
L7030 | 2023-05-31 | 1930-03-19 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 9.9.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Defects Liability Period [HV S/S ] | MJ-MSBL-INT-1.14.9.9.5 | 2067 | HV Substations | Fixed Duration & Units | 0 | 0% | 0% | 2067 | 2067 | 0% | $0.00 | $0.00 | $0.00 | 2005 | 2023-05-31 | 1930-03-19 | $0.00 | $0.00
M13440 | 2023-05-31 |  |  |  | 9.9.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start DLP [HV S/S ] | MJ-MSBL-INT-1.14.9.9.5 | 0 | HV Substations | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3760 | 2023-05-31 |  | $0.00 | $0.00
M13460 |  | 2024-06-08 |  |  | 9.9.5 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish DLP [HV S/S ] | MJ-MSBL-INT-1.14.9.9.5 | 0 | HV Substations | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3760 |  | 2024-06-08 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.9.6 Sewer Water Treatment Plant [STP] | 2024-07-07 | 2025-07-15 | [7 empty] | 312 |  |  | 0 |  | 0% | 312 | 312 | 0% | $0.00 | $0.00 | $0.00 | 3428 | 2024-07-07 | 2025-07-15 | $0.00 | $0.00
L7040 | 2024-07-07 | 2025-07-15 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 9.9.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Defects Liability Period [STP] | MJ-MSBL-INT-1.14.9.9.6 | 312 | Sewer Water Treatment Plant [STP] | Fixed Duration & Units | 0 | 0% | 0% | 312 | 312 | 0% | $0.00 | $0.00 | $0.00 | 3428 | 2024-07-07 | 2025-07-15 | $0.00 | $0.00
M13470 | 2024-07-07 |  |  |  | 9.9.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start DLP [STP] | MJ-MSBL-INT-1.14.9.9.6 | 0 | Sewer Water Treatment Plant [STP] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3428 | 2024-07-07 |  | $0.00 | $0.00
M13480 |  | 2025-07-15 |  |  | 9.9.6 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish DLP [STP] | MJ-MSBL-INT-1.14.9.9.6 | 0 | Sewer Water Treatment Plant [STP] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3428 |  | 2025-07-15 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.9.7 Open Channel [Storm Water Drainage] | 2025-01-18 | 2026-01-26 | [7 empty] | 312 |  |  | 0 |  | 0% | 312 | 312 | 0% | $0.00 | $0.00 | $0.00 | 3262 | 2025-01-18 | 2026-01-26 | $0.00 | $0.00
L7050 | 2025-01-18 | 2026-01-26 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 9.9.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Defects Liability Period [O.C.] | MJ-MSBL-INT-1.14.9.9.7 | 312 | Open Channel [Storm Water Drainage] | Fixed Duration & Units | 0 | 0% | 0% | 312 | 312 | 0% | $0.00 | $0.00 | $0.00 | 3262 | 2025-01-18 | 2026-01-26 | $0.00 | $0.00
M13490 | 2025-01-18 |  |  |  | 9.9.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start DLP [O.C.] | MJ-MSBL-INT-1.14.9.9.7 | 0 | Open Channel [Storm Water Drainage] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3262 | 2025-01-18 |  | $0.00 | $0.00
M13500 |  | 2026-01-26 |  |  | 9.9.7 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish DLP [O.C.] | MJ-MSBL-INT-1.14.9.9.7 | 0 | Open Channel [Storm Water Drainage] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3262 |  | 2026-01-26 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.9.9 Road Finishes, Street Lighting Poles & Traffic Signals | 2025-01-20 | 2026-01-28 | [7 empty] | 312 |  |  | 0 |  | 0% | 312 | 312 | 0% | $0.00 | $0.00 | $0.00 | 3260 | 2025-01-20 | 2026-01-28 | $0.00 | $0.00
L7060 | 2025-01-20 | 2026-01-28 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 9.9.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Defects Liability Period [RD&St.L.] | MJ-MSBL-INT-1.14.9.9.9 | 312 | Road Finishes, Street Lighting Poles & Traffic Signals | Fixed Duration & Units | 0 | 0% | 0% | 312 | 312 | 0% | $0.00 | $0.00 | $0.00 | 3260 | 2025-01-20 | 2026-01-28 | $0.00 | $0.00
M13510 | 2025-01-20 |  |  |  | 9.9.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start DLP [RD&St.L.] | MJ-MSBL-INT-1.14.9.9.9 | 0 | Road Finishes, Street Lighting Poles & Traffic Signals | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3260 | 2025-01-20 |  | $0.00 | $0.00
M13520 |  | 2026-01-28 |  |  | 9.9.9 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish DLP [RD&St.L.] | MJ-MSBL-INT-1.14.9.9.9 | 0 | Road Finishes, Street Lighting Poles & Traffic Signals | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3260 |  | 2026-01-28 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.9.10 Landscape Work | 2025-10-13 | 2026-10-21 | [7 empty] | 312 |  |  | 0 |  | 0% | 312 | 312 | 0% | $0.00 | $0.00 | $0.00 | 3041 | 2025-10-13 | 2026-10-21 | $0.00 | $0.00
L7070 | 2025-10-13 | 2026-10-21 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 9.9.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Defects Liability Period [Landscape] | MJ-MSBL-INT-1.14.9.9.10 | 312 | Landscape Work | Fixed Duration & Units | 0 | 0% | 0% | 312 | 312 | 0% | $0.00 | $0.00 | $0.00 | 3041 | 2025-10-13 | 2026-10-21 | $0.00 | $0.00
M13530 | 2025-10-13 |  |  |  | 9.9.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start DLP [Landscape] | MJ-MSBL-INT-1.14.9.9.10 | 0 | Landscape Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3041 | 2025-10-13 |  | $0.00 | $0.00
M13540 |  | 2026-10-21 |  |  | 9.9.10 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish DLP [Landscape] | MJ-MSBL-INT-1.14.9.9.10 | 0 | Landscape Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3041 |  | 2026-10-21 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.3 Secondary Infrastructure Networks | 2023-12-16 | 2029-02-05 | [7 empty] | 1610 |  |  | 0 |  | 0% | 1610 | 1610 | 0% | $0.00 | $0.00 | $0.00 | 2360 | 2023-12-16 | 2029-02-05 | $0.00 | $0.00
L3150 | 2023-12-16 | 2029-02-05 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 9.3 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S. Inf. Defects Liability Period | MJ-MSBL-INT-1.14.9.3 | 1565 | Secondary Infrastructure Networks | Fixed Duration & Units | 0 | 0% | 0% | 1565 | 1565 | 0% | $0.00 | $0.00 | $0.00 | 2342 | 2023-12-16 | 2029-02-05 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.3.2 MOH Beneficiaries' Units | 2023-12-16 | 2028-01-27 | [7 empty] | 1289 |  |  | 0 |  | 0% | 1289 | 1289 | 0% | $0.00 | $0.00 | $0.00 | 2681 | 2023-12-16 | 2028-01-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.3.2.19 Package (01] | 2023-12-16 | 2028-01-27 | [7 empty] | 1253 |  |  | 0 |  | 0% | 1253 | 1253 | 0% | $0.00 | $0.00 | $0.00 | 2654 | 2023-12-16 | 2028-01-27 | $0.00 | $0.00
M13020 | 2023-12-16 |  |  |  | 9.3.2.19 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Start DLP [S. Inf.] | MJ-MSBL-INT-1.14.9.3.2.19 | 0 | Package (01] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 3595 | 2023-12-16 |  | $0.00 | $0.00
M13030 |  | 2028-01-27 |  |  | 9.3.2.19 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Finish DLP [S. Inf.] | MJ-MSBL-INT-1.14.9.3.2.19 | 0 | Package (01] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2654 |  | 2028-01-27 | $0.00 | $0.00
M1840 |  | 2028-01-27 |  |  | 9.3.2.19 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Final H.O & Contract Closure [S. Infrastructure] | MJ-MSBL-INT-1.14.9.3.2.19 | 0 | Package (01] | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2654 |  | 2028-01-27 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.3.2.20 Package (02) | [9 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.3.2.21 Package (03) | [9 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.3.2.22 Package (04) | [9 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.3.3 Other Beneficiaries' Units | [9 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.3.3.1 Packages (01,02,03,04) | [9 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.11 Superstructure Work | 2023-04-30 | 1931-02-02 | [7 empty] | 2431 |  |  | 0 |  | 0% | 2431 | 2431 | 0% | $0.00 | $0.00 | $0.00 | 1736 | 2023-04-30 | 1931-02-02 | $0.00 | $0.00
L3160 | 2023-04-30 | 1931-02-02 | Cost Loading - CASH OUT, Cost Loading - CASH IN |  | 9.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | S.S. Defects Liability Period | MJ-MSBL-INT-1.14.9.11 | 2363 | Superstructure Work | Fixed Duration & Units | 0 | 0% | 0% | 2363 | 2363 | 0% | $0.00 | $0.00 | $0.00 | 1736 | 2023-04-30 | 1931-02-02 | $0.00 | $0.00
M1820 |  | 1930-03-19 |  |  | 9.11 | Morooj Jeddah Northern Part Master Schedule Rev. 14 [01-10-2019] | MJ-MSBL-INT-1.14 | Final H.O & Contract Closure [Superstructure] | MJ-MSBL-INT-1.14.9.11 | 0 | Superstructure Work | Fixed Duration and Units/Time | 0 | 0% | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 2005 |  | 1930-03-19 | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.11.2 MOH Beneficiaries' Units | [9 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.11.2.19 Package (01] | [9 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.11.2.20 Package (02) | [9 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.11.2.21 Package (03) | [9 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.11.2.22 Package (04) | [9 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.11.3 Other Beneficiaries' Units | [9 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  |  | $0.00 | $0.00
MJ-MSBL-INT-1.14.9.11.3.1 Packages (01,02,03,04) | [9 empty] | 0 |  |  | 0 |  | 0% | 0 | 0 | 0% | $0.00 | $0.00 | $0.00 | 0 |  |  | $0.00 | $0.00